## Assumptions
PROJECT INFORMATION
Parameter | Value | Notes
Project Name | DEMO 220/66/11 kV GIS Substation | e.g., ND10 Substation
Project Start Date | 2026-01-01 | First month of timeline (e.g., Oct-2024)
Number of Months | 15 | Timeline duration
USD to EGP Exchange Rate | 47.63 | For EQU equivalent conversion
EUR to EGP Exchange Rate | 55.4747 | For EQU equivalent conversion
CONTRACT VALUE
(USD) | (EUR) | (EGP)
9679087.1 | 1056599.41 | 493381743.93
CASH IN - PAYMENT TERMS
Currency / Category | Milestone | Percentage (%) | Cash Duration (Days)
Material USD
| Advanced Payment | 20% | 45
| Site Delivery USD | 70% | 45
| Retention | 10% | 45
Material EGP
| Advanced Payment | 20% | 45
| Site Delivery EGP | 70% | 45
| Retention | 10% | 45
Material EUR
| Advanced Payment | 20% | 45
| Site Delivery EUR | 70% | 45
| Retention | 10% | 45
Services EGP
| Advanced Payment | 20% | 45
| Progress | 70% | 45
| Retention | 10% | 45
Civil Works EGP
| Advanced Payment | 20% | 45
| Progress | 70% | 45
| Retention | 10% | 45
CASH OUT - PAYMENT TERMS
Currency / Budget Catergory | Milestone | Percentage (%) | Cash Duration (Days)
Material USD
| Advanced Payment PO USD | 10% | 0
| Shipping MAT USD | 40% | 15
| Delivery MAT USD | 40% | 30
| CCC | 10% | 0
Material EGP
| Advanced Payment PO EGP | 20% | 0
| Site Delivery | 80% | 30
Material EUR
| Advanced Payment PO EUR | 10% | 0
| Shipping MAT EUR | 40% | 15
| Delivery MAT EUR | 40% | 30
| CCC | 10% | 0
S/C
| Advanced Payment Installation | 5% | 0
| Installation Progress | 85% | 30
| Subcontractor Retention | 10% | 0
SERVICES - EQ - LABOUR
| Advanced Payment Installation | 10% | 0
| Progress | 90% | 30
CASH IN SUMMARY - DEDUCTIONS
Deduction Type | Percentage (%) | Notes
VAT | 0% | Applied on gross invoicing
Advanced Payment Deduction (AP) | 0% | Deducted from each invoice
Stamp Duties & Additional Stamp Duties | 0% | On net before VAT
Governmental Deductions | 0.9%
Viva Egypt | 0%
CASH OUT - INDIRECT COSTS
These are fixed-value line items in the Cash Out sheet. Enter the total budget for each.
Indirect Cost Item | Total Budget (EGP) | Notes
1. STAFF SALARIES AND WAGES | 13553062
2. EMPLOYER AND/OR ENGINEER REQUIREMENTS | 441458.3333
3. CONTRACTOR OFFICES AND SITE FACILITIES | 3354125
4. ACCOMMODATION | 2926250
5. MOBILIZATION AND DE-MOBILIZATION | 160000
6. IT & COMMUNICATIONS | 147083.3333
7. TRANSPORTATIONS | 6000000
8. GENERAL SITE EQUIPMENT | 0
9. SAFETY AND QUALITY REQUIREMENTS | 647500
10. CONSULTANCIES | 213325
10. WARRANITY PERIOD COST | 300000
CASH OUT - PROJECT OVERHEADS
Percentage-based costs applied on total contract value, distributed across project timeline.
Overhead Type | Percentage (%) | Applied On | (USD) | (EUR) | (EGP)
INSURANCE POLICIES | 0.5% | Total contract value
ADVANCE PAYMENT COST | 0.1% | Total contract value
PERFORMANCE BOND COST | 0.26% | Total contract value
RETENTION COST | 2.64% | Total contract value
SOCIAL INSURANCE | 1.3% | Total contract value
CASUAL LABOR TAX | 0.45% | Total contract value
STAMP DUTIES & ADDITIONAL STAMP DUTIES 2.43% | 0% | Total contract value
GOVERNMENTAL DEDUCTIONS 0.9% | 0.9% | Total contract value
VIVA EGYPT 1% | 0% | Total contract value
CASH OUT - RISKS & CONTINGENCIES
Fixed-value items for project risk reserves and company overheads.
Item | Total Budget | Notes | (USD) | (EUR) | (EGP)
RISKS & CONTINGENCIES | 2% | Project risk reserve
COMPANY OVERHEADS | 4% | Corporate overhead allocation