## Activities
Activity ID | Activity Name | Start | Finish
BSKDGNGENGR07 | Project Completion |  | 2027-04-07
BSTSELGENGR60 | Energization For 220 KV GIS | 2027-04-07 | 2027-04-07
BSTSELGENGR57 | Final Trip Test (11 kV ) | 2027-04-04 | 2027-04-07
BSTSELGENGR59 | Energization For 66 KV GIS | 2027-04-01 | 2027-04-01
BSTSELGENGR55 | Final Trip Test (220 KV) | 2027-03-30 | 2027-04-06
BSTSELCRBCP15 | Closed Loop Test (11 kV ) | 2027-03-30 | 2027-04-02
BSTSELGENGR56 | Final Trip Test (66 KV) | 2027-03-25 | 2027-03-31
BSTSELCRBCP13 | Closed Loop Test (220 KV) | 2027-03-25 | 2027-03-29
BSTSELCRBCP12 | Protection Relays Alarm Test to SAS HMI (11 kV ) | 2027-03-25 | 2027-03-29
BSTSELCRBCP03 | Alarm And Indication Check Up To SAS HMI For 11 kV | 2027-03-25 | 2027-03-29
BSTSELCRBCP07 | Measurement Test (220 KV) | 2027-03-19 | 2027-03-23
BSTSELCRBCP01 | Alarm And Indication Check Up To SAS HMI For 220 KV | 2027-03-19 | 2027-03-24
BSTSELGENGR41 | HV Synchronizing System Relay Test (220 KV) | 2027-03-18 | 2027-03-22
BSTSELGENVT08 | HV CCVT Secondary Circuit Injection Test (220 KV) | 2027-03-18 | 2027-03-22
BSTSELCRBCP14 | Closed Loop Test (66 KV) | 2027-03-16 | 2027-03-24
BSTSELGENGR52 | Relays Final Settings Review (220 KV) | 2027-03-15 | 2027-03-18
BSTSELGENGR43 | HV Synchro-Check Relay Test (220 kV) | 2027-03-14 | 2027-03-17
BSTSELGENVT07 | HV CCVT Test (220 KV) | 2027-03-14 | 2027-03-17
BSTSELCRBCP10 | Protection Relays Alarm Test to SAS HMI (220 KV) | 2027-03-10 | 2027-03-14
BSTSELCRBCP08 | Measurement Test (66 KV) | 2027-03-10 | 2027-03-14
BSTSELCRBCP02 | Alarm And Indication Check Up To SAS HMI For 66 KV | 2027-03-10 | 2027-03-15
BSTSELGENGR37 | HV Bus Bar Stability Test (220 KV) | 2027-03-10 | 2027-03-14
BSCNARGI2--30 | Epoxy Paint for SOG - 220 KV GIS Building ( 2 Layer ) | 2027-03-09 | 2027-03-14
BSTSELGENGR45 | HV Synchronizing Scheme Check Test (220 KV) | 2027-03-09 | 2027-03-12
BSERELGN2OH01 | Installation of Overhead Connection between Gantry and 220 KV GIS | 2027-03-09 | 2027-03-12
BSTSELGENGR22 | Low Impedance BB & BF Protection Relay Final Setting Test | 2027-03-07 | 2027-03-09
BSTSELGI2G212 | HV Test - 220 KV GIS | 2027-03-07 | 2027-03-08
BSTSELGENGR53 | Relays Final Settings Review (66 KV) | 2027-03-05 | 2027-03-09
BSTSELGENGR39 | HV Power Transformer Differential /REF Stability Test (175 MVA Transformer) | 2027-03-05 | 2027-03-09
BSTSELGENGR20 | Overcurrent Relay Final Setting Test | 2027-03-05 | 2027-03-05
BSTSELGI2G206 | DS&ES Timing Test | 2027-03-03 | 2027-03-04
BSTSELGI2G205 | CB Timing Test | 2027-03-03 | 2027-03-05
BSERELCRBCP03 | SAS Installation [CTRL-R] | 2027-03-01 | 2027-03-24
BSTSELGENGR36 | Common Alarm Panel Scheme Check | 2027-03-01 | 2027-03-04
BSTSELGENGR13 | Restricted Earth Fault Relay Final Setting Test - Secondary Side (220 KV SIDE) | 2027-03-01 | 2027-03-04
BSTSELCRBCP11 | Protection Relays Alarm Test to SAS HMI (66 KV) | 2027-02-28 | 2027-03-04
BSTSELGENGR38 | HV Bus Bar Stability Test (66 KV) | 2027-02-28 | 2027-03-03
BSTSELGI2G209 | CT Primary Injection Test | 2027-02-28 | 2027-03-01
BSTSELGENGR42 | HV Synchronizing System Relay Test (66 KV) | 2027-02-26 | 2027-03-02
BSTSELGENGR47 | Operation and Interlocking Test (220 KV) | 2027-02-25 | 2027-03-02
BSTSELGI2G213 | LCC Scheme Check | 2027-02-25 | 2027-03-03
BSTSELGI2G208 | CT Secondary Circuit Injection | 2027-02-25 | 2027-02-26
BSTSELGENGR12 | Restricted Earth Fault Relay Final Setting Test - Primary Side (220 KV SIDE) | 2027-02-24 | 2027-02-28
BSTSELGENDS03 | MV Neutral Disconnector Switch Test - Secondary Side (11 kV SIDE) | 2027-02-24 | 2027-02-24
BSTSELGENVT06 | MV Neutral CT Primary Injection Test - Secondary Side (11 kV SIDE) | 2027-02-24 | 2027-02-24
BSERELGENLV28 | Cables Termination [Trans.40 to FFR] | 2027-02-24 | 2027-02-28
BSERELGENLV20 | Cables Termination [CTRL to FFR 40] | 2027-02-24 | 2027-02-28
BSCNARMFN--29 | Side Walks Around the Fence - Fence - West | 2027-02-24 | 2027-03-04
BSTSELGENGR23 | Low Impedance BB & BF Protection Relay Final Setting Test | 2027-02-23 | 2027-02-26
BSTSELGI2G211 | VT Secondary Circuit Injection & Burden Test | 2027-02-23 | 2027-02-26
BSTSELGENGR44 | HV Synchro-Check Relay Test (66kV) | 2027-02-22 | 2027-02-25
BSCNCVGEN--10 | Installation of Mesh Wire Fence - Wire mesh Fence - 220 KV Area | 2027-02-22 | 2027-03-02
BSERMEGENSS01 | Installation of Camera System - Security System | 2027-02-22 | 2027-03-09
BSTSELGI2G210 | VT Test | 2027-02-21 | 2027-02-22
BSTSELGI2G207 | CT Test | 2027-02-21 | 2027-02-24
BSCNCVROD--16 | Joints Filling - Secondary Roads | 2027-02-21 | 2027-02-24
BSTSELGENGR11 | Main 2 Differential Relay Final Setting Test | 2027-02-19 | 2027-02-23
BSERELGENLV27 | Pulling LV & Control Cables [Trans.40 to FFR] | 2027-02-19 | 2027-02-23
BSERELGENLV19 | Pulling LV & Control Cables [CTRL to FFR 40] | 2027-02-19 | 2027-02-23
BSERELGENLV12 | Cables Termination [CTRL to Trans.40 & Outdoor Equipment] | 2027-02-19 | 2027-02-23
BSERELTR4LS01 | Install Lightening System for the Fire Wall [Trans.40] | 2027-02-19 | 2027-02-19
BSCNCVROD--24 | Joints Filling - Access Road | 2027-02-19 | 2027-02-23
BSTSELGENGR46 | HV Synchronizing Scheme Check Test (66 KV) | 2027-02-17 | 2027-02-21
BSTSELGENGR35 | HV BB Protection Panel Scheme Check (66 KV) | 2027-02-17 | 2027-02-22
BSTSELGENGR17 | Overcurrent Relay Final Setting Test | 2027-02-17 | 2027-02-17
BSTSELGENHV02 | HV Cable High Voltage Test | 2027-02-17 | 2027-02-17
BSTSELGENHV01 | HV Cable Electrical Test | 2027-02-16 | 2027-02-16
BSCNCVROD--15 | road drainage installation- Secondary Roads | 2027-02-16 | 2027-02-19
BSCNARMFN--28 | Wiring & Installation of Lighting Fixtures & Distribution Panel - Fence - West | 2027-02-16 | 2027-02-21
BSTSELGENGR51 | HV Line Feeder Main 2 Distance Relay | 2027-02-15 | 2027-02-18
BSTSELGENGR50 | HV Line Feeder Main 1 Distance Relay | 2027-02-15 | 2027-02-18
BSTSELGENGR34 | HV BB Protection Panel Scheme Check (220 KV) | 2027-02-15 | 2027-02-18
BSTSELGENGR10 | Main 1 Differential Relay Final Setting Test | 2027-02-15 | 2027-02-18
BSTSELGENNR01 | Neutral Earthing Resistance Test | 2027-02-15 | 2027-02-15
BSCNCVROD--23 | road drainage installation- Access Road | 2027-02-15 | 2027-02-19
BSERELTY4OH01 | Installation of Overhead Connection between 40 MVA Transformers and outdoor Equipment | 2027-02-15 | 2027-02-18
BSERELGENLV11 | Pulling LV & Control Cables [CTRL to Trans.40 & Outdoor Equipment] | 2027-02-15 | 2027-02-18
BSERELTR4ES01 | Install Secondary Earthing for the Transformer [Trans.40] | 2027-02-15 | 2027-02-18
BSERELFFRFS04 | Connections for Fire Fighting System [FFR - Trans.40] | 2027-02-15 | 2027-02-18
BSCNCVGEN--22 | Installation of Mesh Wire Fence - Wire mesh Fence - 40 MVA Area | 2027-02-15 | 2027-02-22
BSCNCVROD--22 | RC Slab for Roads - Access Road | 2027-02-15 | 2027-02-18
BSCNCVROD--14 | RC Slab for Roads - Secondary Roads | 2027-02-15 | 2027-02-19
BSTSELGENGR40 | HV Power Transformer Differential /REF Stability Test (40 MVA Transformer) | 2027-02-14 | 2027-02-14
BSCNCVGEN--09 | RC Foundation for Wire mesh fence - Wire mesh Fence - 220 KV Area | 2027-02-14 | 2027-02-21
BSTSELTR4T412 | On-Load Tap-Changer (OLTC) Test | 2027-02-12 | 2027-02-15
BSTSELTR4T410 | BCT Secondary Circuit Injection Test | 2027-02-12 | 2027-02-15
BSTSELTR4T409 | BCT Test | 2027-02-12 | 2027-02-15
BSTSELTR4T407 | Calibration Of Winding and Oil Temperature Gauges | 2027-02-12 | 2027-02-15
BSTSELGENVT03 | MV Neutral CT Test - Secondary Side (11 kV SIDE) | 2027-02-12 | 2027-02-12
BSTSELGENGR32 | HV Transformer Incomer Control & Protection Panel Scheme Check (66 KV SIDE) | 2027-02-11 | 2027-02-16
BSTSELGENGR21 | Overcurrent Relay Final Setting Test | 2027-02-11 | 2027-02-11
BSTSELGI2G203 | Function of SF6 Gas Density Gauge Test | 2027-02-11 | 2027-02-14
BSTSELGENGR26 | HV Bus Coupler Protection Panel Scheme Check (220 KV) | 2027-02-10 | 2027-02-14
BSTSELGENGR07 | Main 2 Distance Relay Final Setting Test | 2027-02-10 | 2027-02-14
BSTSELTR4T413 | Dissolved Gas Analysis Device (DGA) Test | 2027-02-10 | 2027-02-11
BSTSELTR4T411 | Measurement Of Frequency Response Test (SFRA) | 2027-02-10 | 2027-02-11
BSTSELTR4T408 | Oil Dielectric Breakdown Test | 2027-02-10 | 2027-02-11
BSTSELTR4T406 | Mechanical Protection Devices Test and LCP Function Check | 2027-02-10 | 2027-02-11
BSERELTY4TI02 | Install Post Insulators [Trans.40 Area - PI] | 2027-02-10 | 2027-02-10
BSERELTY4CT02 | Installation of Current Transformers [Trans.40 Area - CT] | 2027-02-10 | 2027-02-11
BSERELTY4DS02 | Installation of Disconnecting Switches [Trans.40 Area - DS] | 2027-02-10 | 2027-02-10
BSERELTY4NR02 | Install NER [Trans.40 Area - NER] | 2027-02-10 | 2027-02-14
BSTSELGENGR33 | HV Bus Coupler Control & Protection Panel Scheme Check (66 KV) | 2027-02-09 | 2027-02-10
BSTSELGENGR19 | AVR Relay Final Setting Test (40 MVA Transformer) | 2027-02-09 | 2027-02-09
BSTSELGENGR16 | Neutral Earth Fault Relay Final Setting Test | 2027-02-09 | 2027-02-09
BSTSELGENGR15 | Overcurrent and Earth Fault Relay Final Setting Test (Backup Protection) | 2027-02-09 | 2027-02-09
BSTSELGENGR14 | Differential Relay Final Setting Test | 2027-02-09 | 2027-02-12
BSTSELGI2G202 | SF6 Gas Leakage Test | 2027-02-09 | 2027-02-10
BSCNCVROD--20 | 2nd layer 10 cm crushed stone & Compaction - Access Road | 2027-02-09 | 2027-02-14
BSCNCVROD--21 | Curbstones installation works - Access Road | 2027-02-09 | 2027-02-14
BSCNCVROD--13 | 2nd layer 10 cm crushed stone & Compaction - Secondary Roads | 2027-02-09 | 2027-02-14
BSCNCVROD--12 | Curbstones installation works - Secondary Roads | 2027-02-09 | 2027-02-14
BSTSELTR4T405 | Measurement Of Dissipation Factor (Tan Delta) | 2027-02-08 | 2027-02-09
BSTSELTR4T404 | Measurement Of Transformer Turns Ratio | 2027-02-08 | 2027-02-10
BSERELGENHV01 | 66 kV Cable Termination (CSE GIS (Wet Type-SF6) Installation) | 2027-02-08 | 2027-02-15
BSERELGENLV06 | Cables Termination [CTRL to Outdoor Equipment Gantry Area 220] | 2027-02-08 | 2027-02-11
BSTSELGI1G112 | HV Test - 66 KV GIS | 2027-02-07 | 2027-02-07
BSCNARMFN--27 | Installation of upper wire mesh Fence - Fence - West | 2027-02-07 | 2027-02-15
BSCNARMFN--26 | Internal & External Drymix - Fence - West | 2027-02-07 | 2027-02-23
BSTSELGENGR25 | HV Power Transformer Protection Panel Scheme Check (175 MVA Transformer) | 2027-02-05 | 2027-02-09
BSTSELGENGR06 | Main 1 Distance Relay Final Setting Test | 2027-02-05 | 2027-02-09
BSCNCVGEN--08 | PC Foundation for Wire mesh fence - Wire mesh Fence - 220 KV Area | 2027-02-05 | 2027-02-12
BSERELFFRFS03 | Installation of Fire Fighting System [FFR - Trans.40] | 2027-02-05 | 2027-02-14
BSTSELGI2G201 | SF6 Gas purity and Dew Point Test | 2027-02-04 | 2027-02-08
BSTSELTR4T403 | Measurement Of Winding Resistance | 2027-02-04 | 2027-02-07
BSTSELTR4T402 | Measurement Of D.C Insulation Resistance | 2027-02-04 | 2027-02-07
BSTSELTR4T401 | Visual Inspection | 2027-02-04 | 2027-02-07
BSCNCVROD--07 | road drainage installation Main Roads | 2027-02-04 | 2027-02-10
BSERELGI2GR02 | Cable Termination - 220 KV GIS Building | 2027-02-04 | 2027-02-19
BSCNCVGEN--14 | Installation of Mesh Wire Fence - Wire mesh Fence - 66 KV Area | 2027-02-04 | 2027-02-12
BSCNCVROD--19 | PC for Curbstones - Access Road | 2027-02-04 | 2027-02-08
BSCNCVROD--11 | PC for Curbstones - Secondary Roads | 2027-02-04 | 2027-02-08
BSCNCVROD--08 | Joints Filling - Main Roads | 2027-02-04 | 2027-02-10
BSTSELGENGR31 | HV Power Transformer Control & Protection (40 MVA Transformer) | 2027-02-03 | 2027-02-08
BSTSELGENGR09 | Overcurrent and Earth Fault Relay Final Setting Test (Backup Protection) | 2027-02-03 | 2027-02-03
BSTSELGENGR08 | Distance Relay Final Setting Test | 2027-02-03 | 2027-02-07
BSTSELCRBSG09 | HV Pot Test | 2027-02-03 | 2027-02-03
BSTSELGENMV01 | MV Cable Test ( VLF ) | 2027-02-03 | 2027-02-07
BSERELGENLV05 | Pulling LV & Control Cables [CTRL to Outdoor Equipment Gantry Area 220] | 2027-02-03 | 2027-02-07
BSERELTR4T418 | Connection between FF Piping System & FF Room - [TRF.40 - No.02] | 2027-02-03 | 2027-02-04
BSERELFFRLS01 | Install Lightening System for the Building [FFR - Trans.40] | 2027-02-03 | 2027-02-03
BSCNCVROD--06 | RC Slab for Roads - Main Roads | 2027-02-03 | 2027-02-10
BSTSELGI1G109 | CT Primary Injection Test | 2027-02-02 | 2027-02-05
BSERELGN2LT02 | Install Line Trap [Gantry 220KV - Line Trap] | 2027-02-02 | 2027-02-02
BSTSELGENGR24 | HV Line Protection Panel Scheme Check (220 KV) | 2027-02-01 | 2027-02-04
BSERELTR4T417 | Installation of Valves, Nozzles, Sprinklers & Accessories - [TRF.40 - No.02] | 2027-02-01 | 2027-02-02
BSERELTY4TI01 | Fix & Erect Structural Steel Parts of Post Insulators [Trans.40 Area - PI] | 2027-02-01 | 2027-02-09
BSERELTY4DS01 | Fix & Erect Structural Steel Parts of DS [Trans.40 Area - DS] | 2027-02-01 | 2027-02-09
BSERELTY4NR01 | Fix & Erect Structural Steel Parts of NER [Trans.40 Area - NER] | 2027-02-01 | 2027-02-09
BSERELTY4CT01 | Fix & Erect Structural Steel Parts of CT [Trans.40 Area - CT] | 2027-02-01 | 2027-02-09
BSTSELGENDS02 | HV Neutral Disconnector Switch Test - Secondary Side (66 KV SIDE) | 2027-01-29 | 2027-01-29
BSTSELGENDS01 | HV Neutral Disconnector Switch Test - Primary Side (220 KV SIDE) | 2027-01-29 | 2027-01-29
BSTSELGENVT05 | HV Neutral CT Primary Injection Test - Secondary Side (66 KV SIDE) | 2027-01-29 | 2027-01-29
BSTSELGENVT04 | HV Neutral CT Primary Injection Test - Primary Side (220 KV SIDE) | 2027-01-29 | 2027-01-29
BSERELTR4T416 | Installation of Firefighting Pipes & Fittings - [TRF.40 - No.02] | 2027-01-29 | 2027-01-31
BSERELFFRES01 | Install Secondary Earthing for the Building [FFR - Trans.40] | 2027-01-29 | 2027-02-02
BSCNCVROD--18 | 1st layer 10 cm crushed stone & Compaction - Access Road | 2027-01-29 | 2027-02-03
BSCNCVROD--10 | 1st layer 10 cm crushed stone & Compaction - Secondary Roads | 2027-01-29 | 2027-02-03
BSERELTY4OH02 | Installation of Overhead Connection between 66 kV GIS and Transformers 40 MVA | 2027-01-29 | 2027-02-02
BSERELTR4T409 | Connection between FF Piping System & FF Room - [TRF.40 - No.01] | 2027-01-29 | 2027-01-31
BSTSELGENGR30 | HV Line Control & Protection Panel Scheme Check (66 KV) | 2027-01-28 | 2027-02-02
BSTSELGI1G111 | VT Secondary Circuit Injection & Burden Test | 2027-01-28 | 2027-02-01
BSTSELGI1G108 | CT Secondary Circuit Injection , Burden Test & Single Earth Point | 2027-01-28 | 2027-02-01
BSTSELGENSA01 | HV Surge Arrestor Test | 2027-01-28 | 2027-02-01
BSERELGN2VT04 | Install Capacitive Voltage Transformer (CCVT) [Gantry 220KV - CCVT] | 2027-01-28 | 2027-02-01
BSCNCVGEN--07 | Excavation for Wire mesh fence - Wire mesh Fence - 220 KV Area | 2027-01-28 | 2027-02-04
BSERELGENMV07 | 11 kV MV Cables from 40 MVA Transformers to MVSG Hall ( Termination work ) | 2027-01-28 | 2027-02-02
BSCNARMFN--25 | Internal & External Plastering - Fence - West | 2027-01-28 | 2027-02-05
BSCNCVROD--05 | Curbstones installation works - Main Roads | 2027-01-28 | 2027-02-02
BSTSELGENGR29 | HV Bus Coupler Control Panel Scheme Check (220 KV) | 2027-01-27 | 2027-01-31
BSTSELGENGR18 | AVR Relay Final Setting Test (175 MVA Transformer) | 2027-01-27 | 2027-01-27
BSCNCVROD--04 | 2nd layer 10 cm crushed stone & Compaction - Main Roads | 2027-01-27 | 2027-02-02
BSERELTR4T408 | Installation of Valves, Nozzles, Sprinklers & Accessories - [TRF.40 - No.01] | 2027-01-27 | 2027-01-28
BSERELTR4T415 | Installation of Oil Treatment Panel with related connections - [TRF.40 - No.02] | 2027-01-26 | 2027-01-28
BSCNCVGEN--13 | RC Foundation for Wire mesh fence - Wire mesh Fence - 66 KV Area | 2027-01-26 | 2027-02-03
BSERELTR4T407 | Installation of Firefighting Pipes & Fittings - [TRF.40 - No.01] | 2027-01-25 | 2027-01-26
BSERELGN2VT03 | Fix & Erect Structural Steel Parts of CCVT [Gantry 220KV - CCVT] | 2027-01-24 | 2027-01-27
BSERELGENLV09 | Cables Termination [CTRL to Trans.175 & Outdoor Equipment] | 2027-01-24 | 2027-01-28
BSERELGN2SA02 | Installation of Surge Arresters - [Gantry 220 KV - SA] | 2027-01-24 | 2027-01-27
BSCNCVROD--17 | Ground Leveling - Access Road | 2027-01-24 | 2027-01-28
BSCNCVROD--09 | Ground Leveling - Secondary Roads | 2027-01-24 | 2027-01-28
BSCNCVTRN--1155 | RC Covers laying - Trenches - 11 KV Outgoing | 2027-01-22 | 2027-01-31
BSTSELGENGR28 | HV Transformer Control Panel Scheme Check (220 KV SIDE) | 2027-01-22 | 2027-01-26
BSERELTR7LS01 | Install Lightening System for the Fire Wall [Trans.175] | 2027-01-22 | 2027-01-22
BSERELTR4T414 | Cable pulling & Terminations - [TRF.40 - No.02] | 2027-01-22 | 2027-01-25
BSERELGENMV03 | 11 kV MV Cables from 40 MVA Transformers to MVSG Hall | 2027-01-22 | 2027-01-27
BSCNCVROD--03 | PC for Curbstones - Main Roads | 2027-01-22 | 2027-01-26
BSTSELTR7T711 | Measurement Of Frequency Response Test (SFRA) | 2027-01-21 | 2027-01-21
BSERELTR4T406 | Installation of Oil Treatment Panel with related connections - [TRF.40 - No.01] | 2027-01-21 | 2027-01-24
BSCNCVGEN--12 | PC Foundation for Wire mesh fence - Wire mesh Fence - 66 KV Area | 2027-01-21 | 2027-01-25
BSTSELCRBSG06 | CT Primary Injection Test | 2027-01-20 | 2027-01-24
BSTSELTR7T713 | Dissolved Gas Analysis Device (DGA) Test | 2027-01-20 | 2027-01-20
BSTSELTR7T708 | Oil Dielectric Breakdown Test | 2027-01-20 | 2027-01-20
BSTSELTR7T707 | Calibration Of Winding and Oil Temperature Gauges | 2027-01-20 | 2027-01-20
BSERMEGENFS04 | Installation of Fire Hose Cabinets - Fire Hydrant | 2027-01-20 | 2027-01-26
BSTSELTR7T712 | On-Load Tap-Changer (OLTC) Test | 2027-01-19 | 2027-01-19
BSTSELTR7T710 | BCT Secondary Circuit Injection Test | 2027-01-19 | 2027-01-19
BSTSELTR7T709 | BCT Test | 2027-01-19 | 2027-01-19
BSERELTY7OH02 | Installation of Overhead Connection between 175 MVA Transformers and outdoor Equipment | 2027-01-19 | 2027-01-22
BSERELGENLV10 | Pulling LV & Control Cables [CTRL to Trans.175 & Outdoor Equipment] | 2027-01-19 | 2027-01-22
BSCNCVGEN--18 | Installation of Mesh Wire Fence - Wire mesh Fence - 175 MVA Area | 2027-01-19 | 2027-01-26
BSERELGN2SA01 | Fix & Erect Structural Steel Parts of Surge Arrestor [Gantry 220 KV - SA] | 2027-01-19 | 2027-01-22
BSERELFFRLS03 | Install Lightening System for the Building [FHR] | 2027-01-19 | 2027-01-19
BSERELTR4T413 | Oil Processing - [TRF.40 - No.02] | 2027-01-19 | 2027-01-22
BSCNMPCRB--153 | Fire Alarm Cable Termination - Control Building | 2027-01-18 | 2027-01-21
BSCNARCRB--110 | Installing Fire Extinguishers of Control Room For control - Control Building | 2027-01-18 | 2027-01-18
BSCNARCRB--29 | Internal painting final coat of Control Room For control - Control Building | 2027-01-18 | 2027-01-21
BSCNMPCRB--20 | Fire Alarm Cable Termination - Control Building | 2027-01-18 | 2027-01-21
BSTSELGENGR27 | HV Line Control Panel Scheme Check (220 KV) | 2027-01-18 | 2027-01-21
BSERELTR7ES01 | Install Secondary Earthing for the Transformer [Trans.175] | 2027-01-18 | 2027-01-21
BSERELTY7TI02 | Install Post Insulators [Trans.175 Area - PI] | 2027-01-18 | 2027-01-18
BSERELTR4T405 | Cable pulling & Terminations - [TRF.40 - No.01] | 2027-01-18 | 2027-01-20
BSERELTR4RW02 | Install Cable Trays & Accessories of LV & Control Cables [TRF.40 - No.02] | 2027-01-18 | 2027-01-21
BSCNMPCRB--05 | Normal, Emergency Lighting and Sockets Wire Termination - Control Building | 2027-01-17 | 2027-01-21
BSTSELCRBCP09 | Measurement Test (11 kV ) | 2027-01-17 | 2027-01-20
BSTSELGI1G113 | LCC Scheme Check | 2027-01-17 | 2027-01-24
BSERELTY7TI01 | Fix & Erect Structural Steel Parts of Post Insulators [Trans.175 Area - PI] | 2027-01-17 | 2027-01-17
BSERELTY7DS02 | Installation of Disconnecting Switches [Trans.175 Area - DS] | 2027-01-17 | 2027-01-17
BSERELTR4T412 | HV & LV Bushing Installation - [TRF.40 - No.02] | 2027-01-17 | 2027-01-17
BSERELCRBFA01 | Fire Alarm Sub-Panels Erection [CTRL-OUT R] | 2027-01-15 | 2027-01-19
BSTSELCRBSG11 | Protection Relays Final Setting Test | 2027-01-15 | 2027-01-20
BSTSELCRBSG08 | VT Secondary Circuit Injection Test | 2027-01-15 | 2027-01-15
BSTSELCRBSG05 | CT Secondary Circuit Injection Test | 2027-01-15 | 2027-01-19
BSERELTY7DS01 | Fix & Erect Structural Steel Parts of DS [Trans.175 Area - DS] | 2027-01-15 | 2027-01-15
BSERELTY7SE02 | Install NER [Trans.175 Area - NER] | 2027-01-15 | 2027-01-15
BSCNCVROD--02 | 1st layer 10 cm crushed stone & Compaction - Main Roads | 2027-01-15 | 2027-01-21
BSCNARCRB--78 | Internal painting final coat of Offices For control - Control Building | 2027-01-14 | 2027-01-18
BSCNARCRB--77 | Installing Fire Extinguishers of Offices For control - Control Building | 2027-01-14 | 2027-01-14
BSCNARCRB--76 | Installing Windows of Offices For control - Control Building | 2027-01-14 | 2027-01-18
BSCNARCRB--75 | Installing doors of Offices For control - Control Building | 2027-01-14 | 2027-01-18
BSERELCRBRW04 | Install Cable Trays & Accessories of Telecommunication Cables [CTRL-TELE] | 2027-01-14 | 2027-01-18
BSTSELTR7T706 | Mechanical Protection Devices Test and LCP Function Check | 2027-01-14 | 2027-01-18
BSTSELGENVT10 | HV CVT Secondary Circuit Injection Test (66 KV) | 2027-01-14 | 2027-01-14
BSERELFFRES03 | Install Secondary Earthing for the Building [FHR] | 2027-01-14 | 2027-01-18
BSERELTR4RW01 | Install Cable Trays & Accessories of LV & Control Cables [TRF.40 - No.01] | 2027-01-14 | 2027-01-17
BSERELTR4T411 | Erection of transformer Accessories (Radiator -conservator-pipes and fans ) - [TRF.40 - No.02] | 2027-01-14 | 2027-01-15
BSERELTR4T404 | Oil Processing - [TRF.40 - No.01] | 2027-01-14 | 2027-01-18
BSCNMPCRB--163 | Installing Fire Detectors - Control Building | 2027-01-13 | 2027-01-17
BSCNARCRB--44 | Internal painting final coat of Kitchen and Bathrooms For control - Control Building | 2027-01-13 | 2027-01-18
BSERELCRBTL02 | Install Telecommunication [CTRL-TELE] | 2027-01-13 | 2027-01-13
BSCNMPCRB--19 | Installing Fire Detectors - Control Building | 2027-01-13 | 2027-01-17
BSCNARCRB--74 | False Ceiling Final Fix - Control Building | 2027-01-13 | 2027-01-13
BSCNARCRB--107 | Raised Floor Final Fix - Control Building | 2027-01-13 | 2027-01-17
BSCNARCRB--25 | Raised Floor Final Fix of Control Room For control - Control Building | 2027-01-13 | 2027-01-17
BSTSELTR7T705 | Measurement Of Dissipation Factor (Tan Delta) | 2027-01-13 | 2027-01-13
BSTSELTR7T704 | Measurement Of Transformer Turns Ratio | 2027-01-13 | 2027-01-13
BSTSELTR7T703 | Measurement Of Winding Resistance | 2027-01-13 | 2027-01-13
BSTSELTR7T702 | Measurement Of D.C Insulation Resistance | 2027-01-13 | 2027-01-13
BSTSELGENVT09 | HV CVT Test (66 KV) | 2027-01-13 | 2027-01-13
BSTSELGENGR05 | Energy Meter Test | 2027-01-13 | 2027-01-17
BSTSELGENGR03 | ACDB Scheme Check | 2027-01-13 | 2027-01-13
BSTSELGENGR02 | DCDB Scheme Check | 2027-01-13 | 2027-01-13
BSCNCVGEN--11 | Excavation for Wire mesh fence - Wire mesh Fence - 66 KV Area | 2027-01-13 | 2027-01-20
BSERELGN1SA02 | Installation of Surge Arresters | 2027-01-13 | 2027-01-13
BSERELTR4T403 | HV & LV Bushing Installation - [TRF.40 - No.01] | 2027-01-13 | 2027-01-13
BSTSELGENGR54 | Relays Final Settings Review (11 kV ) | 2027-01-12 | 2027-01-15
BSTSELCRBSG01 | BB Contact Resistance Test | 2027-01-12 | 2027-01-15
BSTSELGI1G110 | VT Test | 2027-01-12 | 2027-01-12
BSTSELGI1G107 | CT Test | 2027-01-12 | 2027-01-15
BSTSELGI1G106 | DS&ES Timing Test | 2027-01-12 | 2027-01-15
BSTSELGI1G103 | Function of SF6 Gas Density Gauge Test | 2027-01-12 | 2027-01-15
BSTSELTR7T701 | Visual Inspection | 2027-01-12 | 2027-01-12
BSTSELGENAX01 | Auxiliary Transformer Test | 2027-01-12 | 2027-01-17
BSTSELGENCB01 | MV Capacitor Bank Test | 2027-01-12 | 2027-01-15
BSTSELGENVT02 | HV Neutral CT Test - Secondary Side (66 KV SIDE) | 2027-01-12 | 2027-01-12
BSTSELGENVT01 | HV Neutral CT Test - Primary Side (220 KV SIDE) | 2027-01-12 | 2027-01-12
BSTSELGENGR04 | Energy Meter Panel Scheme Check | 2027-01-12 | 2027-01-12
BSTSELGENBR02 | Battery Charger Test | 2027-01-12 | 2027-01-12
BSTSELGENBR01 | Substation Battery Bank Test | 2027-01-12 | 2027-01-15
BSERELGENLV04 | Cables Termination [CTRL to GIS 66] | 2027-01-12 | 2027-01-27
BSERMEGENFS03 | Pipes Laying, Supports & Fittings Installation - Fire Hydrant | 2027-01-12 | 2027-01-19
BSCNCVTRN--1145 | Concrete Pouring for Trenches Covers - Trenches - 11 KV Outgoing | 2027-01-11 | 2027-01-21
BSCNMPCRB--15 | Installation Of Wiring Devices | 2027-01-11 | 2027-01-15
BSERELCRBPB01 | Outdoor Operation Sub-Panels Erection [CTRL-OUT R] | 2027-01-11 | 2027-01-14
BSCNMPCRB--04 | Installing Lighting Fixtures - Control Building | 2027-01-11 | 2027-01-15
BSERELGI2FS01 | Install Fire Extinguisher Units [GIS 220] | 2027-01-11 | 2027-01-11
BSERELTY7SE01 | Fix & Erect Structural Steel Parts of NER [Trans.175 Area - NER] | 2027-01-11 | 2027-01-14
BSERELTY7CT02 | Installation of Current Transformers [Trans.175 Area - CT] | 2027-01-11 | 2027-01-11
BSCNCVMFN--40 | Backfilling Works - Fence - West | 2027-01-11 | 2027-01-27
BSERELTR4T402 | Erection of transformer Accessories (Radiator -conservator-pipes and fans ) - [TRF.40 - No.01] | 2027-01-11 | 2027-01-12
BSTSELCRBSG10 | LCC Scheme Check | 2027-01-10 | 2027-01-14
BSTSELCRBSG02 | CB Contact Resistance Test | 2027-01-10 | 2027-01-13
BSERELGENHV03 | 66 kV Cable Termination (CSE TRF. (Porcelain Type) Installation) | 2027-01-10 | 2027-01-17
BSERMEGENFS05 | Connections with Pump Rooms & UGWT - Fire Hydrant | 2027-01-10 | 2027-01-13
BSERELTR4T410 | Positioning - [TRF.40 - No.02] | 2027-01-10 | 2027-01-10
BSERELTR4T401 | Positioning - [TRF.40 - No.01] | 2027-01-10 | 2027-01-10
BSCNMPCRB--143 | Fire Alarm Cable Pulling - Control Building | 2027-01-08 | 2027-01-12
BSCNMPCRB--103 | Earthing Cable Termination - Control Building | 2027-01-08 | 2027-01-12
BSCNMPCRB--83 | Earthing Cable Pulling - Control Building | 2027-01-08 | 2027-01-12
BSCNARCRB--111 | Internal painting final coat of Control Room For control - Control Building | 2027-01-08 | 2027-01-19
BSCNARCRB--109 | Installing Windows of Control Room For control - Control Building | 2027-01-08 | 2027-01-12
BSCNARCRB--108 | Installing doors of Control Room For control - Control Building | 2027-01-08 | 2027-01-12
BSCNARCRB--43 | Installing Fire Extinguishers of Kitchen and Bathrooms For control - Control Building | 2027-01-08 | 2027-01-12
BSERELCRBTL01 | Install Telecommunication Panel Frames [CTRL-TELE] | 2027-01-08 | 2027-01-12
BSCNMPCRB--18 | Fire Alarm Cable Pulling - Control Building | 2027-01-08 | 2027-01-12
BSCNMPCRB--17 | Earthing Cable Termination - Control Building | 2027-01-08 | 2027-01-12
BSCNARCRB--106 | Raised Floor First Fix - Control Building | 2027-01-08 | 2027-01-12
BSCNARCRB--24 | Raised Floor First Fix of Control Room For control - Control Building | 2027-01-08 | 2027-01-12
BSCNMPCRB--16 | Earthing Cable Pulling - Control Building | 2027-01-08 | 2027-01-12
BSERELGN1SA01 | Fix & Erect Structural Steel Parts of Surge Arrestor | 2027-01-08 | 2027-01-12
BSTSELGI1G102 | SF6 Gas Leakage Test | 2027-01-07 | 2027-01-07
BSTSELGI1G101 | SF6 Gas purity and Dew Point Test | 2027-01-07 | 2027-01-11
BSERELGI2G204 | Vacuum & Fill SF6 Gas for GIS [GIS 220] | 2027-01-07 | 2027-02-03
BSERELTY7OH01 | Installation of Overhead Connection between 220 kV GIS and Transformers 175 MVA | 2027-01-07 | 2027-01-11
BSERELGENLV22 | Cables Termination [CTRL to Guard Room] | 2027-01-07 | 2027-01-11
BSERELGI1FS01 | Install Fire Extinguisher Units [GIS 66] | 2027-01-07 | 2027-01-11
BSERELCRBRW05 | Install Cable Trays & Accessories of Outdoor Sub-Panels Cables [CTRL-OUT R] | 2027-01-06 | 2027-01-10
BSERELTY7CT01 | Fix & Erect Structural Steel Parts of CT [Trans.175 Area - CT] | 2027-01-06 | 2027-01-10
BSERELTY7SA02 | Installation of Surge Arresters [Trans.175 Area - SA] | 2027-01-06 | 2027-01-06
BSCNCVROD--01 | Ground Leveling - Main Roads | 2027-01-06 | 2027-01-14
BSCNCVGEN--28 | Drainage System for Roof - Shed Roof - Capacitor Bank | 2027-01-05 | 2027-01-06
BSERELGENMV08 | 11 kV MV Cables from Aux Transformers to MVSG Hall (Termination works) | 2027-01-05 | 2027-01-10
BSERELGENMV10 | 11 kV MV Cables Internal inside MVSWG Termination works | 2027-01-05 | 2027-01-11
BSCNMPCRB--113 | Normal, Emergency Lighting and Sockets Wire Termination - Control Building | 2027-01-05 | 2027-01-10
BSCNMPCRB--02 | Installation of Building Service Panels | 2027-01-05 | 2027-01-10
BSCNARCRB--40 | Installation of Sanitary Fixtures - Control Building | 2027-01-05 | 2027-01-08
BSTSELCRBSG07 | VT Test | 2027-01-05 | 2027-01-05
BSTSELCRBSG04 | CT Test | 2027-01-05 | 2027-01-08
BSTSELCRBSG03 | CB Timing Test | 2027-01-05 | 2027-01-08
BSERELCRBGR02 | Cable Termination - Control Building | 2027-01-05 | 2027-01-08
BSERELGENLV21 | Pulling LV & Control Cables [CTRL to Guard Room] | 2027-01-05 | 2027-01-06
BSCNCVTRN--1135 | Backfilling Works - 11 KV Outgoing | 2027-01-04 | 2027-01-10
BSCNMPCRB--53 | Installation of Ventilation Equipments HVAC Inside Building - Control Building | 2027-01-04 | 2027-01-08
BSCNARCRB--99 | Internal painting final coat of Telecommunication For control - Control Building | 2027-01-04 | 2027-01-07
BSCNARCRB--98 | Installing Fire Extinguishers of Telecommunication For control - Control Building | 2027-01-04 | 2027-01-04
BSCNARCRB--97 | Installing Windows of Telecommunication For control - Control Building | 2027-01-04 | 2027-01-07
BSCNARCRB--96 | Installing doors of Telecommunication For control - Control Building | 2027-01-04 | 2027-01-07
BSCNARCRB--42 | Installing Windows of Kitchen and Bathrooms For control - Control Building | 2027-01-04 | 2027-01-07
BSCNARCRB--41 | Installing doors of Kitchen and Bathrooms For control - Control Building | 2027-01-04 | 2027-01-07
BSCNARCRB--39 | False Ceiling Final Fix - Control Building | 2027-01-04 | 2027-01-04
BSCNARCRB--105 | False Ceiling Final Fix - Control Building | 2027-01-04 | 2027-01-07
BSCNARCRB--23 | False Ceiling Final Fix of Control Room For control - Control Building | 2027-01-04 | 2027-01-07
BSCNMPCRB--13 | Installation of Ventilation Equipments HVAC Inside Building - Control Building | 2027-01-04 | 2027-01-08
BSERMEGENFS02 | Concrete Pads - Fire Hydrant | 2027-01-04 | 2027-01-11
BSCNCVMFN--39 | Bitumen isolation - Fence - West | 2027-01-04 | 2027-01-10
BSCNARCRB--95 | Raised Floor Final FixTelecommunication For control - Control Building | 2027-01-03 | 2027-01-03
BSCNARCRB--94 | Raised Floor First FixTelecommunication For control - Control Building | 2027-01-01 | 2027-01-01
BSERELGENLV02 | Cables Termination [CTRL to GIS 220] | 2027-01-01 | 2027-01-17
BSERELGI2GB03 | Erect GIB To Gantry Yard[GIS 220] | 2027-01-01 | 2027-01-18
BSERELTY7SA01 | Fix & Erect Structural Steel Parts of Surge Arrestor [Trans.175 Area - SA] | 2027-01-01 | 2027-01-05
BSCNCVGEN--27 | Installation of Corrugated sheet for Roof - Shed Roof - Capacitor Bank | 2026-12-31 | 2027-01-05
BSERELGENLV16 | Cables Termination [CTRL to CAP] | 2026-12-31 | 2027-01-10
BSERELGENMV04 | 11 kV MV Cables from Aux Transformers to MVSG Hall | 2026-12-31 | 2027-01-05
BSERELGENMV06 | 11 kV MV Cables from MVSG Hall to Capacitor Banks (Termination works) | 2026-12-31 | 2027-01-05
BSPRELGENCP68 | Delivery to Site - Transformers 40 | 2026-12-31 | 2027-01-09
BSCNARCRB--93 | False Ceiling Final FixTelecommunication For control - Control Building | 2026-12-31 | 2026-12-31
BSCNMPCRB--14 | Installing of Monorail Crane - Control Building | 2026-12-31 | 2027-01-04
BSTSELGI1G104 | Contact Resistance Test | 2026-12-31 | 2027-01-07
BSTSELGI2G204 | Contact Resistance Test | 2026-12-31 | 2027-01-06
BSCNMPGUR--13 | Installation of Telephone & Data Equipment - Guard Room | 2026-12-31 | 2027-01-06
BSCNMPGUR--12 | Installation of Fire Alarm Equipment - Guard Room | 2026-12-31 | 2027-01-04
BSERELCRBGR01 | Cable Laying - Control Building | 2026-12-31 | 2027-01-04
BSCNMPCRB--133 | Installing Lighting Fixtures - Control Building | 2026-12-30 | 2027-01-04
BSCNARCRB--38 | False Ceiling First Fix - Control Building | 2026-12-30 | 2027-01-03
BSCNARCRB--73 | False Ceiling First Fix - Control Building | 2026-12-30 | 2027-01-03
BSCNARCRB--104 | False Ceiling First Fix - Control Building | 2026-12-30 | 2027-01-03
BSCNARCRB--92 | False Ceiling First FixTelecommunication For control - Control Building | 2026-12-30 | 2026-12-30
BSCNARCRB--22 | False Ceiling First Fix of Control Room For control - Control Building | 2026-12-30 | 2027-01-03
BSERELGI2LS01 | Install Lightening System for the Building [GIS 220] | 2026-12-30 | 2027-01-03
BSERMEGENFS01 | Installation of Fire Hydrant System (Inside Pump Room) | 2026-12-29 | 2027-01-08
BSERELGENHV02 | 66 kV Power Cables Laying from CSE to 66 kV GIS Building | 2026-12-29 | 2027-01-08
BSERELGENLV03 | Pulling LV & Control Cables [CTRL to GIS 66] | 2026-12-29 | 2027-01-11
BSERELGI1LS01 | Install Lightening System for the Building [GIS 66] | 2026-12-29 | 2027-01-01
BSERELGI1GB03 | Erect GIB [GIS 66] | 2026-12-29 | 2027-01-07
BSCNCVTRN--1125 | Bitumen Isolation - 11 KV Outgoing | 2026-12-28 | 2027-01-03
BSCNCVTRN--125 | Backfilling Works - Road Crossing- 11 kV Outgoing | 2026-12-28 | 2027-01-05
BSCNARGUT--28 | Lighting & Power & Telephone - Guard Towers - Side D | 2026-12-28 | 2027-01-03
BSCNCVGEN--26 | Installation of wire mesh fence - Capacitor Bank | 2026-12-27 | 2026-12-31
BSERELGENLV15 | Pulling LV & Control Cables [CTRL to CAP] | 2026-12-27 | 2026-12-31
BSERELGENMV02 | 11 kV MV Cables from MVSG Hall to Capacitor Banks | 2026-12-27 | 2026-12-31
BSERELCRBRW02 | Install Cable Trays & Accessories of Control & Protection Cables [CTRL-AC/DC R] | 2026-12-27 | 2026-12-30
BSPRMPGENSS04 | Delivery to Site - Security system | 2026-12-27 | 2026-12-27
BSCNMPGUR--11 | Installation of HVAC Equipment - Guard Room | 2026-12-27 | 2026-12-30
BSCNARMFN--24 | Masonry Works till bottom of top beam - Fence - West | 2026-12-25 | 2027-01-03
BSCNMPCRB--123 | Mechanical Equipment Wires Termination - Control Building | 2026-12-24 | 2026-12-30
BSCNMPCRB--93 | Mechanical Equipment Wires Pulling - Control Building | 2026-12-24 | 2026-12-29
BSCNMPCRB--63 | Installation Ducts HVAC - Control Building | 2026-12-24 | 2026-12-29
BSCNMPCRB--33 | Normal, Emergency Lighting and Sockets Wire Pulling - Control Building | 2026-12-24 | 2026-12-29
BSCNARCRB--86 | Installing Windows of Corridor - Control Building | 2026-12-24 | 2026-12-28
BSCNARCRB--85 | Installing doors of Corridor - Control Building | 2026-12-24 | 2026-12-28
BSCNMPCRB--12 | Mechanical Equipment Wires Termination - Control Building | 2026-12-24 | 2026-12-30
BSCNMPCRB--11 | Mechanical Equipment Wires Pulling - Control Building | 2026-12-24 | 2026-12-29
BSCNMPCRB--10 | Installation Ducts HVAC - Control Building | 2026-12-24 | 2026-12-29
BSCNMPCRB--03 | Normal, Emergency Lighting and Sockets Wire Pulling - Control Building | 2026-12-24 | 2026-12-28
BSPRELGENCP58 | FAT - Transformers 40 | 2026-12-23 | 2026-12-30
BSCNARCRB--212 | Installing Fire Extinguishers For Future Room SWG - Control Building | 2026-12-22 | 2026-12-22
BSCNMPGUR--06 | Installation of water closet components & Basins - Guard Room | 2026-12-22 | 2026-12-25
BSCNARCRB--37 | Ceramic for Floor - Control Building | 2026-12-21 | 2026-12-24
BSCNARGUT--27 | Roof Insulation & Tiles - Guard Towers - Side D | 2026-12-21 | 2026-12-27
BSCNARCRB--87 | Installing Fire Extinguishers of Corridor - Control Building | 2026-12-20 | 2026-12-20
BSERELCRBAD01 | Install Battery Chargers | 2026-12-20 | 2026-12-25
BSERELCRBAD03 | Install AC/DC Panels [CTRL-AC/DC R] | 2026-12-20 | 2026-12-23
BSCNARCRB--83 | Installing Tiles - Control Building | 2026-12-20 | 2026-12-23
BSTSELGI1G105 | CB Timing Test | 2026-12-20 | 2026-12-23
BSCNCVGEN--25 | RC Footings - Shed Roof - Capacitor Bank | 2026-12-20 | 2026-12-25
BSERELGI1GR02 | Cable Termination - 66 KV GIS Building | 2026-12-20 | 2027-01-01
BSERELGI1ES01 | Install Secondary Earthing for the Building [GIS 66] | 2026-12-20 | 2026-12-28
BSERELGI1GB02 | Vacuum & Fill SF6 Gas for GIB [GIS 66] | 2026-12-20 | 2027-01-06
BSERELGI1GB01 | Erect GIB to Transformers 40 Yard [GIS 66] | 2026-12-20 | 2026-12-28
BSERELGI1GR01 | Cable Laying - 66 KV GIS Building | 2026-12-20 | 2027-01-05
BSPRMPGENSS03 | Manufacturing - Security system | 2026-12-19 | 2026-12-26
BSCNCVTRN--1115 | RC Walls & Raceway - Trenches - 11 KV Outgoing | 2026-12-18 | 2026-12-27
BSERELGI2ES01 | Install Secondary Earthing for the Building [GIS 220] | 2026-12-18 | 2026-12-29
BSERELGENLV01 | Pulling LV & Control Cables [CTRL to GIS 220] | 2026-12-18 | 2026-12-31
BSERELGI2GB02 | Vacuum & Fill SF6 Gas for GIB [GIS 220] | 2026-12-18 | 2027-01-10
BSERELGI2GB01 | Erect GIB to Transformers 175 Yard [GIS 220] | 2026-12-18 | 2026-12-31
BSCNCVTRN--124 | Bitumen Isolation - Road Crossing- 11 kV Outgoing | 2026-12-18 | 2026-12-27
BSERELGI2GR01 | Cable Laying - 220 KV GIS Building | 2026-12-18 | 2026-12-27
BSCNARGUR--15 | Cage Ladder for Roof - Guard Room | 2026-12-18 | 2026-12-18
BSCNMPGI2--14 | Installation of Fire Alarm devices - 220 KV GIS Building | 2026-12-17 | 2026-12-22
BSCNMPGI1--09 | Installation of Outdoor Lighting Fixtures - 66 KV GIS Building | 2026-12-17 | 2026-12-30
BSCNARMFN--23 | Embedded conduits for Lighting system - Fence - West | 2026-12-17 | 2026-12-25
BSCNCVMFN--38 | RC Top beams - Fence - West | 2026-12-17 | 2026-12-24
BSCNMPGI1--13 | Installation of HVAC Equipment - 66 KV GIS Building | 2026-12-17 | 2026-12-30
BSCNMPGI1--14 | Installation of Fire Alarm devices - 66 KV GIS Building | 2026-12-17 | 2026-12-30
BSCNMPGI1--12 | Installation of sockets - 66 KV GIS Building | 2026-12-17 | 2026-12-30
BSCNARCRB--36 | Ceramic for Walls - Control Building | 2026-12-16 | 2026-12-20
BSERELCRBES01 | Install Secondary Earthing for the Building [CTRL - Aux R] | 2026-12-16 | 2026-12-20
BSCNCVTRN--120 | Backfilling Works - Road Crossing - 40MVA Transformers to Control Building | 2026-12-16 | 2026-12-20
BSCNARGUR--03 | Floor Tiles Works & Walls Ceramics Cladding - Guard Room | 2026-12-16 | 2026-12-21
BSKDGNGEN--01 | Ready for Erection - Capacitor Bank |  | 2026-12-15
BSERELGENGR01 | Installation of Capacitors Banks - Capacitor Bank | 2026-12-15 | 2026-12-27
BSCNARCRB--192 | Epoxy Paint on Floor For Future Room SWG - Control Building | 2026-12-15 | 2026-12-21
BSCNMPCRB--223 | Installation of Telephone & Data | 2026-12-15 | 2026-12-18
BSCNARCRB--84 | Internal painting final coat of Corridor - Control Building | 2026-12-15 | 2026-12-18
BSCNARCRB--81 | Screed on floor of Corridor - Control Building | 2026-12-15 | 2026-12-18
BSCNMPCRB--09 | Installation of Telephone & Data | 2026-12-15 | 2026-12-18
BSERELCRBCP02 | Control and Protection Panels Erection [CTRL-R] | 2026-12-15 | 2026-12-28
BSPRMEGENFS45 | Delivery to Site - Fire hydrant system | 2026-12-15 | 2026-12-28
BSCNCVGEN--24 | PC Footings - Shed Roof - Capacitor Bank | 2026-12-15 | 2026-12-18
BSCNMPGUR--10 | Installation of Lighting Fixtures - Guard Room | 2026-12-15 | 2026-12-18
BSCNARGUR--14 | Drainage System for Roofing - Guard Room | 2026-12-14 | 2026-12-17
BSCNARGUT--26 | Installation of Windows & Doors - Guard Towers - West | 2026-12-14 | 2026-12-20
BSCNARCRB--72 | Installing Tiles - Control Building | 2026-12-13 | 2026-12-16
BSCNCVSRP--10 | Drainage System for Roof - Shed Roof - Vehicles | 2026-12-13 | 2026-12-16
BSERELCRBAD02 | Install Panel Frames [CTRL-AC/DC R] | 2026-12-11 | 2026-12-18
BSERELCRBBR02 | Filling Batteries [CTRL-Bat R] | 2026-12-11 | 2026-12-17
BSCNARCRB--35 | Embedding Sanitary Pipes Inside Walls in Bathroom and Kitchen - Control Building | 2026-12-11 | 2026-12-15
BSCNCVTRN--123 | RC Raft & Pipes positioning - Road Crossing- 11 kV Outgoing | 2026-12-11 | 2026-12-17
BSCNMPFFR--17 | Installation of Telephone & Data - 66/11 kV Firefighting Room | 2026-12-11 | 2026-12-15
BSCNCVTRN--119 | Bitumen Isolation - Road Crossing - 40MVA Transformers to Control Building | 2026-12-11 | 2026-12-15
BSCNCVGUR--09 | RC SOG Works - Guard Room | 2026-12-11 | 2026-12-15
BSCNMPGUR--09 | Installation of sockets - Guard Room | 2026-12-11 | 2026-12-14
BSCNMPFFR--16 | Installation of Fire Alarm Devices - 66/11 kV Firefighting Room | 2026-12-11 | 2026-12-15
BSKDGNCRB--06 | Ready for Erection - AC/DC Room |  | 2026-12-10
BSCNARCRB--222 | Installing Windows For Future Room SWG - Control Building | 2026-12-10 | 2026-12-14
BSCNARCRB--202 | Installing doors For Future Room SWG - Control Building | 2026-12-10 | 2026-12-14
BSERELCRBAX02 | Aux. Transformer NO.02 Erection [CTRL-AUX] | 2026-12-10 | 2026-12-15
BSERELCRBAX01 | Aux. Transformer NO.01 Erection [CTRL-AUX] | 2026-12-10 | 2026-12-15
BSCNCVGEN--23 | Excavation Works - Shed Roof - Capacitor Bank | 2026-12-10 | 2026-12-14
BSERELGENMV09 | 11 kV MV Cables Internal inside MVSWG | 2026-12-10 | 2026-12-14
BSKDGNCRB--03 | Ready for Erection - Aux Transformers |  | 2026-12-09
BSCNMPCRB--193 | Installing Telephone Fixtures - Control Building | 2026-12-09 | 2026-12-14
BSCNMPCRB--08 | Installing Telephone Fixtures - Control Building | 2026-12-09 | 2026-12-14
BSCNMPGI2--13 | Installation of HVAC Equipment - 220 KV GIS Building | 2026-12-09 | 2026-12-22
BSCNMPGI2--12 | Installation of sockets - 220 KV GIS Building | 2026-12-09 | 2026-12-15
BSCNMPPUR--09 | Installation of Lighting fixtures - Fire Hydrant | 2026-12-09 | 2026-12-13
BSCNARSPT--05 | Installation of Metal cover for opening & Maintenece ladder - Septic Tank | 2026-12-09 | 2026-12-13
BSCNCVGUR--08 | 2 layers of Bituminous membrane including preparation paint & Screed Layer - Guard Room | 2026-12-09 | 2026-12-10
BSCNMPGUR--01 | Water Tank, pipes system & Pumps Installation - Guard Room | 2026-12-09 | 2026-12-15
BSCNCVMFN--37 | RC Columns - Fence - West | 2026-12-09 | 2026-12-16
BSCNARCRB--70 | Screed on floor of Offices For control - Control Building | 2026-12-08 | 2026-12-11
BSERELCRBCP01 | Install Control & Protection Panel Frames [CTRL-R] | 2026-12-08 | 2026-12-14
BSERELCRBRW01 | Install Cable Trays & Accessories of Control & Protection Cables [CTRL-R] | 2026-12-08 | 2026-12-14
BSCNARGUR--09 | Side Walks - Guard Room | 2026-12-08 | 2026-12-13
BSKDGNCRB--05 | Ready for Erection - Control Room |  | 2026-12-07
BSCNCVTRN--1105 | RC Raft - Trenches - 11 KV Outgoing | 2026-12-07 | 2026-12-17
BSCNCVGEN--55 | Back Filling External & Internal | 2026-12-07 | 2026-12-15
BSCNARCRB--102 | Screed on floor of Control Room For control - Control Building | 2026-12-07 | 2026-12-10
BSCNARCRB--34 | Insulation & protection for Bathroom and Kitchen Floor - Control Building | 2026-12-07 | 2026-12-10
BSCNMPGUR--07 | Installation Of Wiring Devices | 2026-12-07 | 2026-12-10
BSERELGENLV26 | Cables Termination [Trans.175 to FFR] | 2026-12-07 | 2026-12-10
BSERELGENLV17 | Cables Termination [CTRL to FFR 175] | 2026-12-07 | 2026-12-10
BSCNCVGUR--07 | PC for SOG & polyethylene sheet under PC of SOG - Guard Room | 2026-12-07 | 2026-12-08
BSCNARGUT--25 | Internal Tiles - Guard Towers - West | 2026-12-07 | 2026-12-13
BSCNMPFFR--15 | Installation of HVAC Equipment - 66/11 kV Firefighting Room | 2026-12-07 | 2026-12-10
BSERELGI1G105 | LCC Installation - 66 KV GIS Building | 2026-12-07 | 2026-12-15
BSERELGURLS01 | Install Lightening System for the Building [Guard Room] | 2026-12-06 | 2026-12-06
BSCNARFFR--188 | Epoxy Layer -AUX Room | 2026-12-04 | 2026-12-09
BSCNMPCRB--183 | Telephone Cable Termination - Control Building | 2026-12-04 | 2026-12-08
BSCNARCRB--56 | Installing Fire Extinguishers of Battery room - Control Building | 2026-12-04 | 2026-12-04
BSERELCRBBR01 | Install Batteries with accessories [CTRL-Bat R] | 2026-12-04 | 2026-12-10
BSCNMPCRB--07 | Telephone Cable Termination - Control Building | 2026-12-04 | 2026-12-08
BSCNARSPT--03 | Internal Surface Epoxy Paint - Septic Tank | 2026-12-04 | 2026-12-08
BSKDGNCRB--04 | Ready for Erection - Batteries Room |  | 2026-12-03
BSCNMPFFR--88 | Installation of Telephone & Data - AUX Room | 2026-12-03 | 2026-12-07
BSCNMPFFR--78 | Installation of Fire Alarm Devices - AUX Room | 2026-12-03 | 2026-12-07
BSCNMPFFR--68 | Installation of HVAC Equipment - AUX Room | 2026-12-03 | 2026-12-07
BSCNMPFFR--58 | Installation of Lighting fixtures - AUX Room | 2026-12-03 | 2026-12-07
BSCNARCRB--82 | Internal painting for Walls of Corridor - Control Building | 2026-12-03 | 2026-12-14
BSCNMPGI1--06 | Installation of Building Service Panels | 2026-12-03 | 2026-12-16
BSCNMPGI1--05 | Installation Of Wiring Devices | 2026-12-03 | 2026-12-16
BSENMPGENSS05 | Material approval - Security system | 2026-12-03 | 2026-12-18
BSERELTR7T709 | Connection between FF Piping System & FF Room - [TRF.175 - No.01] | 2026-12-03 | 2026-12-09
BSCNMPGI1--10 | Installation of Telephone & Data devices - 66 KV GIS Building | 2026-12-03 | 2026-12-16
BSERELGI1G104 | Vacuum & Fill SF6 Gas for GIS [GIS 66] | 2026-12-03 | 2026-12-20
BSERELGI1G103 | Install GIS 66 KV Bay [GIS 66] | 2026-12-03 | 2026-12-18
BSCNCVSRP--09 | Installation of Corrugated sheet for Roof - Shed Roof - Vehicles | 2026-12-03 | 2026-12-11
BSCNMPGI1--08 | Installation of Indoor Lighting Fixtures - 66 KV GIS Building | 2026-12-03 | 2026-12-16
BSCNMPGI1--07 | Wiring & Terminations - 66 KV GIS Building | 2026-12-03 | 2026-12-16
BSCNCVTRN--1095 | PC Raft - Trenches - 11 KV Outgoing | 2026-12-02 | 2026-12-06
BSCNARCRB--32 | Screed on floor of Kitchen and Bathrooms For control - Control Building | 2026-12-02 | 2026-12-06
BSCNARCRB--28 | Installing Fire Extinguishers of Control Room For control - Control Building | 2026-12-02 | 2026-12-02
BSCNARCRB--27 | Installing Windows of Control Room For control - Control Building | 2026-12-02 | 2026-12-06
BSCNARCRB--26 | Installing doors of Control Room For control - Control Building | 2026-12-02 | 2026-12-06
BSCNARCRB--20 | Screed on floor of Control Room - Control Building | 2026-12-02 | 2026-12-07
BSCNARCRB--118 | Side Walks - Control Building | 2026-12-02 | 2026-12-10
BSCNMPCRB--23 | Termination for Outdoor Lighting - Control Building | 2026-12-02 | 2026-12-06
BSCNMPGI2--10 | Installation of Telephone & Data devices - 220 KV GIS Building | 2026-12-02 | 2026-12-06
BSCNCVTRN--122 | PC Raft - Road Crossing- 11 kV Outgoing | 2026-12-02 | 2026-12-10
BSERELGENLV25 | Pulling LV & Control Cables [Trans.175 to FFR] | 2026-12-02 | 2026-12-06
BSERELGENLV18 | Pulling LV & Control Cables [CTRL to FFR 175] | 2026-12-02 | 2026-12-06
BSCNCVTRN--118 | RC Raft & Pipes positioning - Road Crossing - 40MVA Transformers to Control Building | 2026-12-02 | 2026-12-10
BSCNMPPUR--05 | Wiring & Terminations - Fire Hydrant | 2026-12-02 | 2026-12-08
BSCNARGUR--05 | Installation of Doors - Guard Room | 2026-12-02 | 2026-12-02
BSCNARGUR--04 | Installation of Windows - Guard Room | 2026-12-02 | 2026-12-02
BSCNARGUR--06 | Internal Painting Works - Guard Room | 2026-12-02 | 2026-12-06
BSCNARGUR--13 | Tile works for roofing & Joints filling - Guard Room | 2026-12-02 | 2026-12-08
BSCNARGUR--08 | Dry mix for Facades including Plinth painting - Guard Room | 2026-12-02 | 2026-12-07
BSCNCVGN1--17 | Decorative Painting - 66 KV Outdoor Equipment- Equipment Foundation | 2026-12-02 | 2026-12-06
BSCNMPFFR--14 | Installation of Lighting fixtures - 66/11 kV Firefighting Room | 2026-12-02 | 2026-12-06
BSCNARCRB--71 | Internal painting for Walls of Offices For control - Control Building | 2026-12-01 | 2026-12-07
BSCNMPGUR--08 | Installation of Building Service Panels | 2026-12-01 | 2026-12-06
BSCNMPGI2--07 | Wiring & Terminations - 220 KV GIS Building | 2026-12-01 | 2026-12-08
BSCNMPPUR--07 | Installation of Telephone & Data Devices - Fire Hydrant | 2026-12-01 | 2026-12-04
BSERELGURES01 | Install Secondary Earthing for the Building [Guard Room] | 2026-12-01 | 2026-12-04
BSCNMPPUR--06 | Installation of Fire Alarm Devices - Fire Hydrant | 2026-12-01 | 2026-12-04
BSCNMPGUR--05 | Wiring & Terminations - Guard Room | 2026-12-01 | 2026-12-06
BSCNARGUR--12 | Thermal Insulation Layer - Guard Room | 2026-12-01 | 2026-12-01
BSCNCVMFN--36 | RC middle Beams - Fence - West | 2026-12-01 | 2026-12-08
BSCNCVSWN--05 | Backfilling Works - Sewage Network | 2026-12-01 | 2026-12-07
BSCNMPCRB--173 | Telephone Cable Pulling - Control Building | 2026-11-30 | 2026-12-03
BSCNARCRB--54 | Installing doors of Battery room - Control Building | 2026-11-30 | 2026-12-03
BSCNARCRB--90 | Screed on floor of Telecommunication For control - Control Building | 2026-11-30 | 2026-12-03
BSCNMPCRB--06 | Telephone Cable Pulling - Control Building | 2026-11-30 | 2026-12-03
BSCNMPFFR--08 | Installation of Telephone & Data - 220/66 KV Firefighting Room | 2026-11-30 | 2026-12-03
BSCNMPFFR--07 | Installation of Fire Alarm Devices - 220/66 KV Firefighting Room | 2026-11-30 | 2026-12-03
BSCNMPFFR--06 | Installation of HVAC Equipment - 220/66 KV Firefighting Room | 2026-11-30 | 2026-12-03
BSCNMPFFR--05 | Installation of Lighting fixtures - 220/66 KV Firefighting Room | 2026-11-30 | 2026-12-03
BSCNARSPT--02 | Internal Surface preparation & Rendering - Septic Tank | 2026-11-30 | 2026-12-03
BSCNARGUT--07 | Lighting & Power & Telephone - Guard Towers - north | 2026-11-30 | 2026-12-06
BSCNARGUT--24 | Internal Painting - Guard Towers - West | 2026-11-30 | 2026-12-06
BSCNARGI1--11 | Installation of Internal Caged Steel Ladder with Platform - 66 KV GIS Building | 2026-11-30 | 2026-11-30
BSCNARFFR--178 | Screed Layer -AUX Room | 2026-11-29 | 2026-12-03
BSCNCVGEN--45 | Beams Works - Capacitor Bank | 2026-11-27 | 2026-12-06
BSERELGI1G115 | LCC Support- 66 KV GIS Building | 2026-11-27 | 2026-12-06
BSCNMPFFR--98 | Installation Of Wiring Devices | 2026-11-27 | 2026-12-02
BSCNMPFFR--38 | Wiring & Terminations - AUX Room | 2026-11-27 | 2026-12-01
BSCNARCRB--103 | Internal painting for Walls of Control Room For control - Control Building | 2026-11-27 | 2026-12-06
BSCNARCRB--80 | Plastering for Internal Walls and Ceiling of Corridor - Control Building | 2026-11-27 | 2026-12-02
BSCNARCRB--79 | Embedding Electric Sleeves Inside Walls of Corridor - Control Building | 2026-11-27 | 2026-12-01
BSCNARCRB--30 | Embedding Electric Sleeves Inside Walls of Kitchen and Bathrooms For control - Control Building | 2026-11-27 | 2026-12-01
BSCNMPCRB--22 | Installing Lighting Fixtures and Accessories - Control Building | 2026-11-27 | 2026-12-01
BSCNMPFFR--18 | Installation of Building Service Panels | 2026-11-27 | 2026-12-02
BSCNMPFFR--12 | Installation Of Wiring Devices | 2026-11-27 | 2026-12-02
BSERELGI1G102 | Enter Bays & Adjustment Leveling and alignment all GIS 66 KV Bay Components [GIS 66] | 2026-11-27 | 2026-12-02
BSCNCVTRN--117 | PC Raft - Road Crossing - 40MVA Transformers to Control Building | 2026-11-27 | 2026-12-01
BSCNMPFFR--13 | Wiring & Terminations - 66/11 kV Firefighting Room | 2026-11-27 | 2026-12-01
BSCNARCRB--152 | Internal painting Walls For Future Room SWG - Control Building | 2026-11-26 | 2026-12-09
BSCNMPPUR--08 | Installation of Building Service Panels | 2026-11-26 | 2026-12-01
BSCNMPPUR--03 | Installation Of Wiring Devices | 2026-11-26 | 2026-12-01
BSCNMPGI2--06 | Installation of Building Service Panels | 2026-11-26 | 2026-12-01
BSCNMPGI2--05 | Installation Of Wiring Devices | 2026-11-26 | 2026-12-01
BSCNMPGI2--09 | Installation of Outdoor Lighting Fixtures - 220 KV GIS Building | 2026-11-26 | 2026-11-30
BSPRMPGENTD04 | Delivery to Site - Telephone & Data System | 2026-11-26 | 2026-11-29
BSERELTR7T708 | Installation of Valves, Nozzles, Sprinklers & Accessories - [TRF.175 - No.01] | 2026-11-26 | 2026-12-02
BSCNMPGI2--08 | Installation of Indoor Lighting Fixtures - 220 KV GIS Building | 2026-11-26 | 2026-12-01
BSCNCVSWN--04 | Pipes Testing - Sewage Network | 2026-11-26 | 2026-11-30
BSCNCVSRP--08 | Installation of Vertical Supports - Shed Roof - Vehicles | 2026-11-26 | 2026-12-02
BSCNMPPUR--04 | Installation of HVAC Equipment - Fire Hydrant | 2026-11-26 | 2026-11-30
BSCNARGUR--11 | 2 layers of Bituminous membrane insulation including Screed Layer (Including testing) - Guard Room | 2026-11-26 | 2026-11-30
BSCNARCRB--69 | Plastering for Internal Walls and Ceiling of Offices For control - Control Building | 2026-11-25 | 2026-11-30
BSERELGI2G205 | LCC Installation - 220 KV GIS Building | 2026-11-25 | 2026-12-06
BSCNARSPT--04 | Backfilling - Septic Tank | 2026-11-25 | 2026-11-29
BSCNARGUR--02 | Internal Plastering Works - Guard Room | 2026-11-25 | 2026-12-01
BSCNCVGN1--18 | Graveling Works - 66 KV Outdoor Equipment- Equipment Foundation | 2026-11-25 | 2026-11-30
BSCNCVGN1--16 | Grouting for top of Pedestals - 66 KV Outdoor Equipment- Equipment Foundation | 2026-11-25 | 2026-12-01
BSCNCVFFR--144 | RC SOG & Upstand Concrete Foundation for Equipment - AUX Room | 2026-11-24 | 2026-11-27
BSCNMPFFR--02 | Installation Of Wiring Devices | 2026-11-24 | 2026-11-29
BSCNMPFFR--04 | Wiring & Terminations - 220/66 KV Firefighting Room | 2026-11-24 | 2026-11-27
BSCNCVGN2--17 | Decorative Painting - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-11-24 | 2026-11-27
BSCNCVTRN--1085 | Excavation Works - Trenches - 11 KV Outgoing | 2026-11-23 | 2026-12-01
BSCNCVTRN--635 | RC Covers laying - Trenches - 175MVA Transformers to CB | 2026-11-23 | 2026-12-01
BSCNARCRB--91 | Internal painting for Walls of Telecommunication For control - Control Building | 2026-11-23 | 2026-11-29
BSCNARCRB--21 | Internal painting for Walls of Control Room - Control Building | 2026-11-23 | 2026-12-01
BSCNARCRB--117 | Harmonic Stone for External Facade - Control Building | 2026-11-23 | 2026-12-01
BSCNMPCRB--21 | Wiring for Outdoor Lighting - Control Building | 2026-11-23 | 2026-11-26
BSCNARCRB--116 | External Roof Drain and Split Units Drain Pipe - Control Building | 2026-11-23 | 2026-11-26
BSCNARCRB--115 | Granite Entrance Walls and Stairs - Control Building | 2026-11-23 | 2026-12-01
BSCNARGI1--33 | Epoxy Paint for SOG - 66 KV GIS Building ( 2 Layer ) | 2026-11-23 | 2026-11-29
BSERELGENMV01 | Install MV Cables Steel Support For Transfromer 40 MVA | 2026-11-23 | 2026-11-27
BSERELGI2G203 | Install GIS 220 KV Bay [GIS 220] | 2026-11-23 | 2026-12-17
BSCNCVTRN--121 | Excavation Works - Road Crossing- 11 kV Outgoing | 2026-11-23 | 2026-12-01
BSERELGI1RW01 | Install Cable Trays & Accessories of LV & Control Cables [GIS 66] | 2026-11-23 | 2026-12-01
BSERELGI1G101 | Prepare & Mark Floor before Installing GIS Bay [GIS 66] | 2026-11-23 | 2026-11-26
BSCNCVTRN--116 | Excavation Works - Road Crossing - 40MVA Transformers to Control Building | 2026-11-23 | 2026-11-26
BSCNMPGUR--04 | Installation of Sub-Panel - Guard Room | 2026-11-23 | 2026-11-30
BSCNMPGUR--03 | Sanitary Works (Water Supply & Sewage) - Guard Room | 2026-11-23 | 2026-11-30
BSCNMPGUR--02 | Embedded Conduits Works - Guard Room | 2026-11-23 | 2026-11-24
BSCNARGUR--07 | External Plastering Works - Guard Room | 2026-11-23 | 2026-12-01
BSCNARGUT--06 | Roof Insulation & Tiles - Guard Towers - north | 2026-11-23 | 2026-11-29
BSCNARGUT--23 | Internal Plastering - Guard Towers - West | 2026-11-23 | 2026-11-29
BSKDGNGI1--01 | Ready for Erection - 66KV GIS |  | 2026-11-22
BSCNCVFFR--134 | 2 layer of bituminous membrane & Screed Layer - AUX Room | 2026-11-22 | 2026-11-23
BSCNARCRB--17 | Installing Fire Extinguishers For Ground Floor SWG - Control Building | 2026-11-22 | 2026-11-22
BSPRELGENTL07 | Delivery to Site - Complete Telecommunication System With All accessories and Spare Parts | 2026-11-22 | 2026-11-22
BSCNARGUR--10 | Light Weight Concrete for Roofing - Guard Room | 2026-11-22 | 2026-11-25
BSCNCVMFN--35 | Masonry Works till bottom of middle beam - Fence - West | 2026-11-22 | 2026-11-30
BSCNCVCRB--138 | Masonry Works For Corridor - Control Building | 2026-11-20 | 2026-11-26
BSCNCVCRB--118 | Masonry Works For Control Building - First Floor | 2026-11-20 | 2026-11-26
BSCNCVTRN--485 | Backfilling Works - Trenches - Road Crossing - 175MVA Transformers to CB | 2026-11-20 | 2026-11-25
BSCNARFFR--78 | Door Installation -AUX Room | 2026-11-20 | 2026-11-20
BSCNARCRB--68 | Embedding Electric Sleeves Inside Walls of Offices For control - Control Building | 2026-11-20 | 2026-11-24
BSCNCVGN2--26 | Decorative Painting - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-11-20 | 2026-11-24
BSCNARSPT--01 | 2 layers of Bituminous membrane insulation for walls & Masonry Works - Septic Tank | 2026-11-20 | 2026-11-24
BSCNCVFFR--124 | PC for SOG - AUX Room | 2026-11-19 | 2026-11-20
BSCNCVGEN--35 | Masonary works - Capacitor Bank | 2026-11-19 | 2026-11-27
BSCNMPFFR--108 | Installation of Building Service Panels | 2026-11-19 | 2026-11-24
BSCNMPFFR--48 | Installation of Sub-panels & Control panel - AUX Room | 2026-11-19 | 2026-11-26
BSCNARFFR--68 | Windows Installation -AUX Room | 2026-11-19 | 2026-11-19
BSCNMPCRB--43 | Installing Sub-Panels - Control Building | 2026-11-19 | 2026-11-23
BSCNARCRB--132 | Internal Plastering For Parapet For Control Room - Control Building | 2026-11-19 | 2026-11-23
BSCNMPCRB--01 | Installing Sub-Panels - Control Building | 2026-11-19 | 2026-11-23
BSCNMPFFR--09 | Installation of Building Service Panels | 2026-11-19 | 2026-11-24
BSERELFFRFS02 | Connections for Fire Fighting System [FFR - Trans.175] | 2026-11-19 | 2026-11-27
BSERELTR7T707 | Installation of Firefighting Pipes & Fittings - [TRF.175 - No.01] | 2026-11-19 | 2026-11-25
BSCNMPFFR--01 | Installation of Sub-panels & Control panel - 220/66 KV Firefighting Room | 2026-11-19 | 2026-11-23
BSCNMPGI2--04 | Installation of Sub-Panel - 220 KV GIS Building | 2026-11-19 | 2026-11-25
BSCNMPPUR--02 | Installation of Sub-panels - Fire Hydrant | 2026-11-19 | 2026-11-25
BSCNCVSPT--09 | Installation of Pipes & fiitings - Septic Tank | 2026-11-19 | 2026-11-19
BSCNCVGEN--05 | Bitumen Isolation - Foundation - Capacitor Bank | 2026-11-19 | 2026-11-23
BSCNMPFFR--10 | Installation of Sub-panels & Control panel - 66/11 kV Firefighting Room | 2026-11-19 | 2026-11-26
BSCNMPGI1--04 | Installation of Sub-Panel - 66 KV GIS Building | 2026-11-19 | 2026-12-02
BSCNARCRB--172 | Screed on floor For Future Room SWG - Control Building | 2026-11-18 | 2026-11-25
BSCNARCRB--52 | Anti Acid Ceramic for Floors - Control Building | 2026-11-18 | 2026-11-29
BSCNCVSRP--07 | RC Concrete for floor - Shed Roof - Vehicles | 2026-11-18 | 2026-11-25
BSCNCVTRN--105 | Backfilling Works - Duct Bank- 40MVA Transformers | 2026-11-18 | 2026-11-24
BSPRELGENAD315 | Delivery to Site - 48V Battery bank | 2026-11-17 | 2026-11-23
BSPRELGENAD305 | Delivery to Site - 220V DC battery bank | 2026-11-17 | 2026-11-23
BSCNARCRB--89 | Plastering for Internal Walls and Ceiling of Telecommunication For control - Control Building | 2026-11-17 | 2026-11-22
BSERELCRBRW03 | Install Cable Trays & Ladder Accessories of 11 kV Switch Gear Cables [CTRL-SWG] | 2026-11-17 | 2026-11-30
BSERELCRBSG01 | 11 kV Switch Gear Erection [CTRL-SWG] | 2026-11-17 | 2026-12-09
BSPRMPGENTD03 | Manufacturing - Telephone & Data System | 2026-11-17 | 2026-11-25
BSENMPGENSS04 | Material submittal - Security system | 2026-11-17 | 2026-12-02
BSERELGN2GR01 | Fix & Erect Structural Steel Parts of Gantry [Gantry 220 KV - Area] | 2026-11-17 | 2026-12-03
BSCNCVGN2--18 | Graveling Works - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-11-17 | 2026-11-22
BSCNCVGN2--16 | Grouting for top of Pedestals - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-11-17 | 2026-11-23
BSCNARGUR--01 | Masonry works & lintel beams - Guard Room | 2026-11-17 | 2026-11-22
BSCNCVGUR--12 | RC Parapet for Roof Slab - Guard Room | 2026-11-17 | 2026-11-20
BSCNCVGUR--06 | Backfilling Works - Guard Room | 2026-11-17 | 2026-11-18
BSCNCVSWN--03 | Pipes Laying & Fittings - Sewage Network | 2026-11-17 | 2026-11-25
BSERELGENMV20 | Install MV Cables Steel Support For Basemnet Control Building | 2026-11-17 | 2026-11-22
BSKDGNCRB--01 | Ready for Erection - MVSWG Room |  | 2026-11-16
BSERELGI2G215 | LCC Support Installation - 220 KV GIS Building | 2026-11-16 | 2026-11-24
BSCNARCRB--101 | Plastering for Internal Walls and Ceiling of Control Room For control - Control Building | 2026-11-16 | 2026-11-26
BSERELGI2G202 | Enter Bays & Adjustment Leveling and alignment all GIS 220 KV Bay Components [GIS 220] | 2026-11-16 | 2026-11-22
BSCNARGUT--05 | Installation of Windows & Doors - Guard Towers - north | 2026-11-16 | 2026-11-22
BSCNARGUT--22 | Installation of steel ladder/stair - Guard Towers - West | 2026-11-16 | 2026-11-22
BSCNCVGN1--15 | Backfilling Works - 66 KV Outdoor Equipment- Equipment Foundation | 2026-11-16 | 2026-11-24
BSCNARGI1--10 | Epoxy Paint for SOG - 66 KV GIS Building ( 1 Layer ) | 2026-11-16 | 2026-11-22
BSPRELGENTI10 | Delivery to Site - Tension Insulators 66 KV | 2026-11-15 | 2026-11-29
BSPRELGENTI09 | Delivery to Site - Tension Insulators 220 KV | 2026-11-15 | 2026-11-29
BSCNARFFR--168 | Side Walks for FF Room - 220/66 KV AUX Room | 2026-11-15 | 2026-11-18
BSCNARFFR--58 | Internal Painting Works -AUX Room | 2026-11-15 | 2026-11-18
BSCNCVGEN--17 | RC Foundation for Wire mesh fence - Wire mesh Fence - 175 MVA Area | 2026-11-15 | 2026-11-19
BSCNCVSPT--08 | RC Slab - Septic Tank | 2026-11-15 | 2026-11-18
BSCNCVTRN--475 | Bitumen Isolation - Trenches - Road Crossing - 175MVA Transformers to CB | 2026-11-13 | 2026-11-19
BSCNARFFR--158 | Drainage System for Roofing - AUX Room | 2026-11-13 | 2026-11-13
BSCNARCRB--114 | Painting for External Facade - Control Building | 2026-11-13 | 2026-11-22
BSCNCVTY7--18 | Graveling Works - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-11-13 | 2026-11-13
BSCNCVTY7--09 | Graveling Works - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-11-13 | 2026-11-13
BSCNCVGN2--27 | Graveling Works - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-11-13 | 2026-11-18
BSCNCVGN2--25 | Grouting for top of Pedestals - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-11-13 | 2026-11-19
BSCNCVWSN--06 | Pipes Connection to Guard Room - Water Supply Network | 2026-11-13 | 2026-11-16
BSCNCVCRB--128 | Masonry Works For Control Building - First Floor | 2026-11-12 | 2026-11-19
BSPRELGENAD895 | Delivery to Site - Building service panel | 2026-11-12 | 2026-11-18
BSCNARCRB--88 | Embedding Electric Sleeves Inside Walls of Telecommunication For control - Control Building | 2026-11-12 | 2026-11-16
BSERELGENLV24 | Cables Termination [CTRL to AC-DC] | 2026-11-12 | 2026-11-16
BSCNCVSRP--06 | Crushed Stone 2nd layer 10 cm - Shed Roof - Vehicles | 2026-11-12 | 2026-11-17
BSCNCVGEN--04 | RC Foundation Works - Foundation - Capacitor Bank | 2026-11-12 | 2026-11-18
BSCNCVTRN--625 | Concrete Pouring for Trenches Covers - Trenches - 175MVA Transformers to CB | 2026-11-11 | 2026-11-22
BSERELGI2RW01 | Install Cable Trays & Accessories of LV & Control Cables [GIS 220] | 2026-11-11 | 2026-11-22
BSERELGI2G201 | Prepare & Mark Floor before Installing GIS Bay [GIS 220] | 2026-11-11 | 2026-11-15
BSCNARGI2--11 | Installation of Internal Caged Steel Ladder with Platform - 220 KV GIS Building | 2026-11-11 | 2026-11-11
BSCNARGI1--07 | SOG Screed - 66 KV GIS Building | 2026-11-11 | 2026-11-15
BSERELGENLV23 | Pulling LV & Control Cables [CTRL to AC-DC] | 2026-11-11 | 2026-11-11
BSCNCVTRN--104 | Bitumen Isolation - Duct Bank- 40MVA Transformers | 2026-11-11 | 2026-11-17
BSKDGNGI2--01 | Ready for Erection - 220 KV GIS |  | 2026-11-10
BSCNCVGEN--16 | PC Foundation for Wire mesh fence - Wire mesh Fence - 175 MVA Area | 2026-11-10 | 2026-11-13
BSCNCVSPT--07 | RC Walls - Septic Tank | 2026-11-10 | 2026-11-13
BSCNCVGUR--11 | RC Roof Slab for Guard Room (Including Embedded Conduits) - Guard Room | 2026-11-10 | 2026-11-16
BSCNCVMFN--34 | Columns necks - Fence - West | 2026-11-10 | 2026-11-20
BSCNCVWSN--05 | Pipes Connection to Control Building - Water Supply Network | 2026-11-10 | 2026-11-12
BSCNCVWSN--04 | Pipes Connection to Pump Room - Water Supply Network | 2026-11-10 | 2026-11-12
BSERELTY4SA02 | Installation of Surge Arresters [Trans.40 Area - SA] | 2026-11-10 | 2026-11-10
BSPRELGENMV40 | Delivery to Site - MV Cable Termination | 2026-11-09 | 2026-11-16
BSCNCVCRB--148 | Masonry Works of Telecommunication For control - Control Building | 2026-11-09 | 2026-11-11
BSCNARCRB--100 | Embedding Electric Sleeves Inside Walls For AC/DC Room - Control Building | 2026-11-09 | 2026-11-15
BSCNARCRB--113 | Outdoor Steel Ladder & Handrails Erection - Control Building | 2026-11-09 | 2026-11-12
BSPRMEGENFA04 | Delivery to Site - Fire Alarm System | 2026-11-09 | 2026-11-22
BSCNCVTY7--17 | Decorative Painting - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-11-09 | 2026-11-12
BSCNCVTY7--08 | Decorative Painting - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-11-09 | 2026-11-12
BSCNCVGN1--14 | Bitumen Isolation - 66 KV Outdoor Equipment - Equipment Foundation | 2026-11-09 | 2026-11-15
BSCNARFFR--98 | External Dry mix including Plinth Painting -AUX Room | 2026-11-08 | 2026-11-12
BSCNARFFR--48 | Internal Plastering -AUX Room | 2026-11-08 | 2026-11-13
BSCNARCRB--14 | Epoxy Paint on Floor For Ground Floor SWG - Control Building | 2026-11-08 | 2026-11-16
BSERELFFRFS01 | Installation of Fire Fighting System [FFR - Trans.175] | 2026-11-08 | 2026-11-18
BSCNARGUT--04 | Internal Tiles - Guard Towers - north | 2026-11-08 | 2026-11-15
BSCNCVGN1--27 | Graveling Works - 66 KV Outdoor Equipment - GIB Foundation | 2026-11-08 | 2026-11-12
BSPRMEGENFS46 | Delivery to Site - Fire Extinguishers | 2026-11-07 | 2026-11-20
BSCNARFFR--148 | Tile works for roofing -AUX Room | 2026-11-06 | 2026-11-10
BSCNARCRB--53 | Installing Windows of Battery room - Control Building | 2026-11-06 | 2026-11-10
BSCNARCRB--19 | Plastering for Internal Walls and Ceiling of Control Room - Control Building | 2026-11-06 | 2026-11-22
BSCNARCRB--51 | Anti acid painting Ceiling for Battery Room - Control Building | 2026-11-06 | 2026-11-17
BSCNCVGUR--04 | Masonry works for Backfilling - Guard Room | 2026-11-06 | 2026-11-09
BSCNCVGUT--31 | Watch Cabinet Roof RC Slab - Guard Towers - West | 2026-11-06 | 2026-11-15
BSCNCVWSN--03 | Pipes Connection to FF Room - Water Supply Network | 2026-11-06 | 2026-11-09
BSPRELGENAD835 | FAT - Building service panel | 2026-11-05 | 2026-11-11
BSCNARFFR--138 | Geotextile Laying -AUX Room | 2026-11-05 | 2026-11-05
BSCNMPCRB--203 | Installation Of Wiring Devices | 2026-11-05 | 2026-11-10
BSERELGN2GB01 | Fix & Erect Structural Steel Parts of GIB [Gantry 220 KV - GIB Area] | 2026-11-05 | 2026-11-09
BSCNCVGN2--15 | Backfilling Works - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-11-05 | 2026-11-16
BSCNARGI1--06 | SOG Embedded Plates installing - 66 KV GIS Building | 2026-11-05 | 2026-11-10
BSERELTY4SA01 | Fix & Erect Structural Steel Parts of Surge Arrestor [Trans.40 Area - SA] | 2026-11-05 | 2026-11-09
BSCNCVSRP--05 | Crushed Stone 1st layer 10 cm - Shed Roof - Vehicles | 2026-11-05 | 2026-11-11
BSCNCVSPT--06 | RC Raft - Septic Tank | 2026-11-05 | 2026-11-09
BSCNCVSWN--02 | Sewage Manholes - Sewage Network | 2026-11-05 | 2026-11-16
BSCNCVGEN--03 | PC Foundation Works - Foundation - Capacitor Bank | 2026-11-05 | 2026-11-11
BSCNARFFR--128 | Thermal Insulation Layer - AUX Room | 2026-11-04 | 2026-11-04
BSCNARCRB--131 | Mosaic Tiles For Control Room - Control Building | 2026-11-04 | 2026-11-18
BSCNARGI2--08 | Installation of Roll shutter doors - 220 KV GIS Building | 2026-11-04 | 2026-11-06
BSCNCVGEN--15 | Excavation for Wire mesh fence - Wire mesh Fence - 175 MVA Area | 2026-11-04 | 2026-11-09
BSERELTY7GB01 | Fix & Erect Structural Steel Parts of GIB [Trans.175 Area - GIB ] | 2026-11-04 | 2026-11-20
BSCNCVTY7--16 | Grouting for top of Pedestals - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-11-04 | 2026-11-08
BSCNCVTY7--07 | Grouting for top of Pedestals - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-11-04 | 2026-11-08
BSCNARGI2--10 | Epoxy Paint for SOG - 220 KV GIS Building ( 1 Layer ) | 2026-11-04 | 2026-11-10
BSCNARGI2--09 | Installation of Personnel Door - 220 KV GIS Building | 2026-11-04 | 2026-11-06
BSCNCVGUR--10 | RC Columns - Guard Room | 2026-11-04 | 2026-11-09
BSCNCVGUR--05 | Isolation for Foundation - Guard Room - Guard Room | 2026-11-04 | 2026-11-05
BSPRELGENAD255 | FAT - 48V Battery bank | 2026-11-03 | 2026-11-16
BSPRELGENAD245 | FAT - 220V DC battery bank | 2026-11-03 | 2026-11-16
BSCNCVTRN--865 | Backfilling Works - Trenches - Road Crossing - 66 KV GIS | 2026-11-03 | 2026-11-06
BSCNARFFR--118 | 2 layers of Bituminous membrane insulation including Screed Layer (including Testing) - AUX Room | 2026-11-03 | 2026-11-03
BSCNARFFR--88 | External Plastering Works -AUX Room | 2026-11-03 | 2026-11-06
BSCNMPFFR--28 | Embedded Conduits - AUX Room | 2026-11-03 | 2026-11-06
BSCNARCRB--130 | Thermal Insulation For Control Room - Control Building | 2026-11-03 | 2026-11-03
BSPRCVGENGR18 | Delivery to Site - Lighting arms | 2026-11-03 | 2026-11-07
BSPRELGENAD35 | Delivery to Site - AC & DC Panels | 2026-11-03 | 2026-11-09
BSCNCVGEN--21 | RC Foundation for Wire mesh fence - Wire mesh Fence - 40 MVA Area | 2026-11-03 | 2026-11-09
BSCNCVWSN--02 | Main Inlet Pipes Laying - Water Supply Network | 2026-11-03 | 2026-11-05
BSCNCVGN1--26 | Decorative Painting - 66 KV Outdoor Equipment - GIB Foundation | 2026-11-03 | 2026-11-06
BSCNCVTY4--27 | Graveling Works - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-11-02 | 2026-11-02
BSCNCVGN2--24 | Backfilling Works - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-11-02 | 2026-11-12
BSCNCVSPT--05 | 2 layers of Bituminous membrane insulation & Screed Layer for the floor - Septic Tank | 2026-11-02 | 2026-11-04
BSCNCVTY4--18 | Graveling Works - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-11-02 | 2026-11-02
BSCNCVTY4--09 | Graveling Works - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-11-02 | 2026-11-02
BSERELTY4GB01 | Fix & Erect Structural Steel Parts of GIB [Trans.40 Area - GIB ] | 2026-11-01 | 2026-11-04
BSCNARGUT--03 | Internal Painting - Guard Towers - north | 2026-11-01 | 2026-11-06
BSCNARGUT--02 | Installation of steel ladder/stair - Guard Towers - north | 2026-11-01 | 2026-11-06
BSCNCVCRB--158 | Masonry Works For For AC/DC Room - Control Building | 2026-10-30 | 2026-11-08
BSCNARCRB--142 | Plastering for Internal Walls For Future Room SWG - Control Building | 2026-10-30 | 2026-11-17
BSPRELGENCA24 | Delivery to Site - Cable trays & Accessories (Raceway) Patch 02 | 2026-10-30 | 2026-11-05
BSCNCVTRN--455 | RC Raft & Pipes positioning - Trenchs - Road Crossing - 175MVA Transformers to CB | 2026-10-30 | 2026-11-12
BSCNMPCRB--213 | Installation of Building Service Panels | 2026-10-30 | 2026-11-04
BSCNARCRB--18 | Embedding Electric Sleeves Inside Walls of Control Room - Control Building | 2026-10-30 | 2026-11-05
BSCNARCRB--16 | Installing Windows For Ground Floor SWG - Control Building | 2026-10-30 | 2026-11-03
BSCNARCRB--15 | Installing doors For Ground Floor SWG - Control Building | 2026-10-30 | 2026-11-03
BSCNARCRB--12 | Screed on floor For Ground Floor SWG - Control Building | 2026-10-30 | 2026-11-06
BSCNARCRB--112 | Plastering for External Facade - Control Building | 2026-10-30 | 2026-11-08
BSCNCVTRN--102 | RC Raft & Pipes positioning - Duct Bank- 40MVA Transformers | 2026-10-30 | 2026-11-10
BSCNCVSPT--04 | Masonry Works till top level of RC raft - Septic Tank | 2026-10-30 | 2026-11-01
BSCNCVGUT--30 | Watch Cabinet RC Columns - Guard Towers - West | 2026-10-30 | 2026-11-05
BSCNCVTRN--855 | Bitumen Isolation - Trenches - Road Crossing - 66 KV GIS | 2026-10-29 | 2026-11-02
BSCNARFFR--108 | Light Weight sloped Concrete for roofing - AUX Room | 2026-10-29 | 2026-11-02
BSCNARFFR--38 | Masonry Works -AUX Room | 2026-10-29 | 2026-11-02
BSCNARCRB--67 | Internal painting final coat of Workshop Room - Control Building | 2026-10-29 | 2026-11-02
BSCNARCRB--129 | Apply Protection for Membrane for Roof For Control Room - Control Building | 2026-10-29 | 2026-11-02
BSCNARGI2--07 | SOG Screed - 220 KV GIS Building | 2026-10-29 | 2026-11-03
BSERELTR7T718 | Connection between FF Piping System & FF Room - [TRF.175 - No.02] | 2026-10-29 | 2026-11-06
BSCNCVGN2--14 | Bitumen Isolation - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-29 | 2026-11-04
BSCNCVGEN--20 | PC Foundation for Wire mesh fence - Wire mesh Fence - 40 MVA Area | 2026-10-29 | 2026-11-02
BSCNCVGI1--16 | SOG Embedded Plates Fixing - 66 KV GIS Building | 2026-10-29 | 2026-11-04
BSCNCVSRP--04 | RC Pedestals - Shed Roof - Vehicles | 2026-10-29 | 2026-11-04
BSCNCVGEN--02 | Soil Replacement & Compaction Works - Foundation - Capacitor Bank | 2026-10-29 | 2026-11-04
BSCNCVGI1--15 | RC SOG Works - 66 KV GIS Building | 2026-10-29 | 2026-11-06
BSCNCVTY4--26 | Decorative Painting - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-28 | 2026-11-01
BSPRELGENCP18 | Delivery to Site - Control & Protection Panels | 2026-10-28 | 2026-10-28
BSERELGN1GB01 | Fix & Erect Structural Steel Parts of GIB | 2026-10-28 | 2026-11-01
BSCNCVSPT--03 | PC Foundation - Septic Tank | 2026-10-28 | 2026-10-29
BSCNCVGUR--03 | RC Footings Works - Guard Room | 2026-10-28 | 2026-11-03
BSCNCVGN1--25 | Grouting for top of Pedestals - 66 KV Outdoor Equipment - GIB Foundation | 2026-10-28 | 2026-11-02
BSCNCVTY4--17 | Decorative Painting - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-28 | 2026-11-01
BSCNCVTY4--08 | Decorative Painting - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-28 | 2026-11-01
BSCNMPTR4--03 | Installation of Lighting fixtures - 2*40 MVA Transformers | 2026-10-28 | 2026-11-03
BSPRELGENAD28 | FAT - AC & DC Panels | 2026-10-27 | 2026-11-02
BSCNCVGN2--23 | Bitumen Isolation - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-10-27 | 2026-11-01
BSCNCVTRN--615 | Backfilling Works - 175MVA Transformers to CB | 2026-10-26 | 2026-11-10
BSCNCVGN1--13 | RC Pedestals & Anchors Installation - 66 KV Outdoor Equipment - Equipment Foundation | 2026-10-26 | 2026-11-08
BSCNCVFFR--44 | RC Parapet for Roof Slab -AUX Room | 2026-10-25 | 2026-10-28
BSCNARCRB--66 | Installing Fire Extinguishers of Workshop Room - Control Building | 2026-10-25 | 2026-10-25
BSCNARCRB--65 | Installing Windows of Workshop Room - Control Building | 2026-10-25 | 2026-10-28
BSCNARCRB--64 | Installing doors of Workshop Room - Control Building | 2026-10-25 | 2026-10-28
BSCNARCRB--128 | Water Proofing Membrane For Control Room - Control Building | 2026-10-25 | 2026-10-28
BSPRCVGENGR10 | Delivery to Site - Outdoor steel Steel Structure (SA-DS-CT) | 2026-10-25 | 2026-10-31
BSCNCVTRN--39 | Backfilling Works - Trenches - Road Crossing - 175MVA Transformers to 66 KV GIS | 2026-10-25 | 2026-10-29
BSERELTR7T717 | Installation of Valves, Nozzles, Sprinklers & Accessories - [TRF.175 - No.02] | 2026-10-25 | 2026-10-28
BSERELFFRLS02 | Install Lightening System for the Building [FFR - Trans.175] | 2026-10-25 | 2026-10-25
BSCNMPGI1--03 | Embedded Conduits under SOG Works - 66 KV GIS Building | 2026-10-25 | 2026-10-28
BSCNCVWSN--01 | Excavation works for Main Pipe - Water Supply Network | 2026-10-25 | 2026-11-02
BSCNCVFFR--114 | Internal Backfilling - AUX Room | 2026-10-23 | 2026-10-27
BSCNCVTRN--445 | PC Raft - Trenches - Road Crossing - 175MVA Transformers to CB | 2026-10-23 | 2026-10-29
BSCNARCRB--47 | Screed on floor of Battery room - Control Building | 2026-10-23 | 2026-10-27
BSCNARCRB--127 | Sloped Light Weight Concrete For Control Room - Control Building | 2026-10-23 | 2026-10-23
BSCNARCRB--50 | Anti Acid Ceramic for Walls - Control Building | 2026-10-23 | 2026-11-05
BSCNCVTY4--25 | Grouting for top of Pedestals - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-23 | 2026-10-27
BSCNCVTY7--15 | Backfilling Works - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-23 | 2026-11-03
BSCNCVTY7--06 | Backfilling Works - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-23 | 2026-11-03
BSCNCVGEN--19 | Excavation for Wire mesh fence - Wire mesh Fence - 40 MVA Area | 2026-10-23 | 2026-10-28
BSCNCVTRN--101 | PC Raft - Duct Bank- 40MVA Transformers | 2026-10-23 | 2026-10-29
BSCNCVSPT--02 | Soil Replacement & Compaction - Septic Tank | 2026-10-23 | 2026-10-27
BSCNCVGUR--02 | PC Footings Works - Guard Room | 2026-10-23 | 2026-10-27
BSCNARGUT--01 | Internal Plastering - Guard Towers - north | 2026-10-23 | 2026-10-30
BSCNCVGUT--29 | RC Platform - Guard Towers - West | 2026-10-23 | 2026-10-29
BSCNCVSWN--01 | Excavation works - Sewage Network | 2026-10-23 | 2026-11-04
BSCNCVTY4--16 | Grouting for top of Pedestals - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-23 | 2026-10-27
BSCNCVTY4--07 | Grouting for top of Pedestals - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-23 | 2026-10-27
BSCNARTR4--08 | Gravel Laying - 2*40 MVA Transformers | 2026-10-23 | 2026-10-27
BSCNCVTRN--97 | Backfilling Works - Trenches - Road Crossing - Gantry Area 220 KV | 2026-10-22 | 2026-10-26
BSPRELGENCP17 | FAT - Control & Protection Panels | 2026-10-22 | 2026-10-27
BSCNARGI2--06 | SOG Embedded Plates installing - 220 KV GIS Building | 2026-10-22 | 2026-10-28
BSCNARPUR--18 | Installation of metal cover & Maintenece ladder For Tank - Fire Hydrant | 2026-10-22 | 2026-10-26
BSCNCVSRP--03 | RC Footings - Shed Roof - Vehicles | 2026-10-22 | 2026-10-28
BSCNCVGN1--24 | Backfilling Works - 66 KV Outdoor Equipment - GIB Foundation | 2026-10-22 | 2026-10-27
BSCNCVTY4--35 | Graveling Works - 3*40 MVA Outdoor Equipment & Gantry - NER Foundation | 2026-10-21 | 2026-10-21
BSCNARCRB--61 | Embedded steel for Workshop Room | 2026-10-20 | 2026-10-21
BSCNARCRB--63 | Epoxy Paint on Floor Workshop Room | 2026-10-20 | 2026-10-23
BSERELTR7T716 | Installation of Firefighting Pipes & Fittings - [TRF.175 - No.02] | 2026-10-20 | 2026-10-23
BSERELFFRES02 | Install Secondary Earthing for the Building [FFR - Trans.175] | 2026-10-20 | 2026-10-23
BSCNCVTY4--34 | Decorative Painting - 3*40 MVA Outdoor Equipment & Gantry - NER Foundation | 2026-10-20 | 2026-10-20
BSCNCVGI1--14 | 2 layers of Bituminous membrane including preparation paint & Screed Layer - 66 KV GIS Building | 2026-10-20 | 2026-10-23
BSCNARCRB--162 | Embedding Electric Sleeves Inside Walls For Future Room SWG - Control Building | 2026-10-19 | 2026-10-29
BSCNCVTRN--605 | Bitumen Isolation - 175MVA Transformers to CB | 2026-10-19 | 2026-10-25
BSCNCVFFR--34 | RC Roof Slab for (Including Embedded Conduits) -AUX Room | 2026-10-19 | 2026-10-23
BSCNCVCRB--78 | Masonry Works For Control Building - First Floor | 2026-10-19 | 2026-10-29
BSCNCVCRB--68 | RC Parapet For Control Building - First Floor | 2026-10-19 | 2026-10-22
BSCNARCRB--126 | Pouring Mechanical Equipment Foundations For Control Room - Control Building | 2026-10-19 | 2026-10-22
BSCNCVTY4--24 | Backfilling Works - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-19 | 2026-10-22
BSCNCVTRN--38 | Bitumen Isolation - Trenches - Road Crossing - 175MVA Transformers to 66 KV GIS | 2026-10-19 | 2026-10-23
BSCNCVTY4--15 | Backfilling Works - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-19 | 2026-10-22
BSCNCVTY4--06 | Backfilling Works - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-19 | 2026-10-22
BSCNCVTY4--33 | Grouting for top of Pedestals - 3*40 MVA Outdoor Equipment & Gantry - NER Foundation | 2026-10-19 | 2026-10-19
BSPRCVGENGR09 | FAT - Outdoor steel Steel Structure (SA-DS-CT) | 2026-10-18 | 2026-10-24
BSPRMPGENSS02 | PO Issuance - Security system | 2026-10-18 | 2026-11-16
BSCNCVTY7--14 | Bitumen Isolation - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-18 | 2026-10-22
BSCNCVTY7--05 | Bitumen Isolation - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-18 | 2026-10-22
BSCNCVTY7--27 | Graveling Works - 2*175 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-18 | 2026-10-21
BSCNCVSRP--02 | PC Footings - Shed Roof - Vehicles | 2026-10-18 | 2026-10-21
BSCNCVGN1--23 | Bitumen Isolation - 66 KV Outdoor Equipment - GIB Foundation | 2026-10-18 | 2026-10-21
BSCNCVTY4--32 | Backfilling Works - 3*40 MVA Outdoor Equipment & Gantry - NER Foundation | 2026-10-18 | 2026-10-18
BSCNCVFFR--94 | Masonry Works for Backfilling - AUX Room | 2026-10-16 | 2026-10-22
BSCNARCRB--46 | Plastering for Internal Walls and Ceiling of Battery room - Control Building | 2026-10-16 | 2026-10-22
BSCNARCRB--13 | Internal painting Walls For Ground Floor SWG - Control Building | 2026-10-16 | 2026-10-29
BSCNMPTR4--05 | Installing Fire Alarm- 2*40 MVA Transformers | 2026-10-16 | 2026-10-27
BSCNARPUR--17 | Side Walks - Fire Hydrant | 2026-10-16 | 2026-10-21
BSCNCVMFN--33 | RC Footings & Tie Beams - Fence - West | 2026-10-16 | 2026-11-09
BSCNCVTY4--31 | Bitumen Isolation - 3*40 MVA Outdoor Equipment & Gantry - NER Foundation | 2026-10-16 | 2026-10-16
BSCNMPTR4--02 | Wiring & Terminations - 2*40 MVA Transformers | 2026-10-16 | 2026-10-27
BSCNARGI1--23 | Installation of Caged Ladder and handrails - 66 KV GIS Building | 2026-10-16 | 2026-10-20
BSKDGNPUR--01 | Ready for Erection - Pump Room ( Fire Hydrant ) |  | 2026-10-15
BSCNCVTRN--845 | RC Raft & Pipes positioning - Trenchs - Road Crossing - 66 KV GIS | 2026-10-15 | 2026-10-28
BSCNARCRB--60 | Internal painting for Walls of Workshop Room - Control Building | 2026-10-15 | 2026-10-21
BSCNARCRB--59 | Screed on floor of Workshop Room - Control Building | 2026-10-15 | 2026-10-19
BSCNCVTRN--96 | Bitumen Isolation - Duct banks - Road Crossing - Gantry Area 220 KV | 2026-10-15 | 2026-10-21
BSCNMPGI2--03 | Embedded Conduits under SOG Works - 220 KV GIS Building | 2026-10-15 | 2026-10-16
BSCNCVGI2--16 | SOG Embedded Plates Fixing - 220 KV GIS Building | 2026-10-15 | 2026-10-21
BSCNCVGI2--15 | RC SOG Works - 220 KV GIS Building | 2026-10-15 | 2026-10-21
BSERELTR7T715 | Installation of Oil Treatment Panel with related connections - [TRF.175 - No.02] | 2026-10-15 | 2026-10-19
BSCNCVGN2--22 | RC Pedestals & Plate Fixiation - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-10-15 | 2026-10-26
BSCNCVGUT--28 | Columns & Beams - Guard Towers - West | 2026-10-15 | 2026-10-22
BSCNCVGI1--13 | PC Under SOG & polyethylene sheet under PC - 66 KV GIS Building | 2026-10-15 | 2026-10-19
BSCNCVFFR--104 | Bitumen isolation for Foundation - AUX Room | 2026-10-14 | 2026-10-15
BSCNARCRB--182 | Internal painting Ceiling For Future Room SWG - Control Building | 2026-10-14 | 2026-10-27
BSCNCVFFR--54 | RC columns AUX Room | 2026-10-14 | 2026-10-18
BSCNCVGI2--41 | Isolation for Internal Trench - 66 KV GIS Building | 2026-10-14 | 2026-10-16
BSCNCVTY4--23 | Bitumen Isolation - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-14 | 2026-10-18
BSPRMPGENSS01 | Purchasing Request - Security system | 2026-10-14 | 2026-10-17
BSCNCVGUT--07 | Watch Cabinet Roof RC Slab - Guard Towers - north | 2026-10-14 | 2026-10-22
BSCNCVTY4--14 | Bitumen Isolation - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-14 | 2026-10-18
BSCNCVTY4--05 | Bitumen Isolation - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-14 | 2026-10-18
BSCNCVGI2--14 | 2 layers of Bituminous membrane including preparation paint & Screed Layer - 220 KV GIS Building | 2026-10-13 | 2026-10-14
BSPRCVGENGR17 | Manufacturing - Lighting arms | 2026-10-13 | 2026-11-02
BSCNCVTY7--26 | Decorative Painting - 2*175 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-13 | 2026-10-16
BSCNARMFN--08 | Wiring & Installation of Lighting Fixtures & Distribution Panel - Fence - north | 2026-10-13 | 2026-10-19
BSCNCVSRP--01 | Excavation Works - Shed Roof - Vehicles | 2026-10-12 | 2026-10-16
BSCNCVTRN--100 | Excavation Works - Duct Bank- 40MVA Transformers | 2026-10-12 | 2026-10-22
BSCNARPUR--05 | Door Installation For Pump Room - Fire Hydrant | 2026-10-12 | 2026-10-15
BSCNCVSPT--01 | Excavation & Dewatering - Septic Tank | 2026-10-12 | 2026-10-22
BSCNCVGUR--01 | Excavation Works - Guard Room | 2026-10-12 | 2026-10-22
BSCNCVGN1--22 | RC Pedestals & Plate Fixiation - 66 KV Outdoor Equipment - GIB Foundation | 2026-10-12 | 2026-10-16
BSCNCVTY4--29 | RC Foundation - 3*40 MVA Outdoor Equipment & Gantry - NER Foundation | 2026-10-12 | 2026-10-15
BSCNARTR4--09 | Decorative Painting for Exposed parts in transformer foundation - 2*40 MVA Transformers | 2026-10-12 | 2026-10-15
BSCNARTR4--07 | Steel Grating Works - 2*40 MVA Transformers | 2026-10-12 | 2026-10-22
BSKDGNTR4--01 | Ready for Erection - 40 MVA Transformers |  | 2026-10-11
BSCNCVGI2--13 | PC Under SOG & polyethylene sheet under PC - 220 KV GIS Building | 2026-10-11 | 2026-10-12
BSCNCVTRN--37 | RC Raft & Pipes positioning - Trenchs - Road Crossing - 175MVA Transformers to 66 KV GIS | 2026-10-11 | 2026-10-18
BSCNCVGN2--13 | RC Pedestals & Anchors Installation - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-11 | 2026-10-28
BSCNARPUR--04 | Windows Installation For Pump Room - Fire Hydrant | 2026-10-11 | 2026-10-11
BSCNCVGN1--12 | RC Foundation - 66 KV Outdoor Equipment- Equipment Foundation | 2026-10-11 | 2026-10-25
BSCNCVTRN--835 | PC Raft - Trenches - Road Crossing - 66 KV GIS | 2026-10-09 | 2026-10-14
BSCNARCRB--58 | Plastering for Internal Walls and Ceiling of Workshop Room - Control Building | 2026-10-09 | 2026-10-14
BSCNARCRB--57 | Embedding Electric Sleeves Inside Walls of Workshop Room - Control Building | 2026-10-09 | 2026-10-13
BSCNCVTY4--22 | RC Pedestals & Anchors Installation - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-09 | 2026-10-13
BSERELTR7T706 | Installation of Oil Treatment Panel with related connections - [TRF.175 - No.01] | 2026-10-09 | 2026-10-16
BSCNARPUR--13 | Drainage System for Roofing - Fire Hydrant | 2026-10-09 | 2026-10-09
BSCNARMFN--07 | Painting for Gates - Fence - north | 2026-10-09 | 2026-10-13
BSCNCVGUT--27 | RC Footings & Tie Beams - Guard Towers - West | 2026-10-09 | 2026-10-14
BSCNCVTY4--13 | RC Pedestals & Anchors Installation - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-09 | 2026-10-13
BSCNCVTY4--04 | RC Pedestals & Anchors Installation - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-09 | 2026-10-13
BSPRELGENCP16 | Manufacturing -Control & Protection Panels | 2026-10-08 | 2026-10-21
BSCNCVTY7--25 | Grouting for top of Pedestals - 2*175 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-08 | 2026-10-12
BSKDGNFFR--01 | Ready for Erection - Fire Fighting Room 40 |  | 2026-10-07
BSCNCVGI2--31 | Plastering for Internal Trench - 220 KV GIS Building | 2026-10-07 | 2026-10-09
BSCNCVGI2--12 | Backfilling Works Under SOG - 220 KV GIS Building | 2026-10-07 | 2026-10-09
BSCNARPUR--16 | External Backfilling works - Fire Hydrant | 2026-10-07 | 2026-10-11
BSCNCVGUT--06 | Watch Cabinet RC Columns - Guard Towers - north | 2026-10-07 | 2026-10-13
BSCNCVGI1--12 | Backfilling Works Under SOG - 66 KV GIS Building | 2026-10-07 | 2026-10-14
BSCNCVGI1--11 | RC Side Walls for Internal Trench - 66 KV GIS Building | 2026-10-07 | 2026-10-13
BSPRELGENSA39 | Delivery to Site - Surge Arresters | 2026-10-06 | 2026-10-11
BSPRCVGENGR16 | PO Issuance - Lighting arms | 2026-10-06 | 2026-10-12
BSERELTR7T714 | Cable pulling & Terminations - [TRF.175 - No.02] | 2026-10-06 | 2026-10-14
BSCNCVTY7--13 | RC Pedestals & Anchors Installation - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-06 | 2026-10-16
BSCNCVTY7--04 | RC Pedestals & Anchors Installation - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-06 | 2026-10-16
BSCNCVGN1--21 | RC Foundation - 66 KV Outdoor Equipment - GIB Foundation | 2026-10-06 | 2026-10-11
BSCNCVFFR--84 | RC Foundation Works - AUX Room | 2026-10-05 | 2026-10-13
BSCNCVTY4--21 | RC Foundation - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-05 | 2026-10-08
BSCNCVTRN--36 | PC Raft - Trenches - Road Crossing - 175MVA Transformers to 66 KV GIS | 2026-10-05 | 2026-10-09
BSCNMPTR7--03 | Installation of Lighting fixtures - 2*175 MVA Transformers | 2026-10-05 | 2026-10-13
BSCNARPUR--12 | Tile works for roofing - Fire Hydrant | 2026-10-05 | 2026-10-08
BSCNARPUR--03 | Internal Painting Works For Pump Room - Fire Hydrant | 2026-10-05 | 2026-10-09
BSCNCVTY4--12 | RC Foundation - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-10-05 | 2026-10-08
BSCNCVTY4--03 | RC Foundation - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-10-05 | 2026-10-08
BSCNARTR4--06 | Epoxy Paint for Transformers - 2*40 MVA Transformers | 2026-10-05 | 2026-10-11
BSPRELGENTI08 | FAT - Tension Insulators 66 KV | 2026-10-04 | 2026-11-15
BSPRELGENTI07 | FAT - Tension Insulators 220 KV | 2026-10-04 | 2026-11-15
BSCNARFFR--29 | Epoxy Painting - 66/11 kV Firefighting Room | 2026-10-04 | 2026-10-07
BSCNCVTY7--24 | Backfilling Works - 2*175 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-10-04 | 2026-10-07
BSCNARPUR--11 | Geotextile Laying - Fire Hydrant | 2026-10-04 | 2026-10-04
BSCNARMFN--06 | Installation of upper wire mesh Fence - Fence - north | 2026-10-04 | 2026-10-12
BSCNCVGUT--26 | PC footings - Guard Towers - West | 2026-10-04 | 2026-10-08
BSCNCVMFN--32 | PC footings - Fence - West | 2026-10-04 | 2026-10-15
BSCNARFFR--19 | Door Installation - 66/11 kV Firefighting Room | 2026-10-04 | 2026-10-05
BSCNARFFR--18 | Windows Installation - 66/11 kV Firefighting Room | 2026-10-04 | 2026-10-05
BSCNCVCRB--178 | Masonry Works of Workshop Room - Control Building | 2026-10-02 | 2026-10-08
BSCNARCRB--45 | Embedding Electric Sleeves Inside Walls of Battery room - Control Building | 2026-10-02 | 2026-10-06
BSCNARCRB--49 | Embedding Sanitary Pipes Inside Walls for Eye Wash in Battery Room - Control Building | 2026-10-02 | 2026-10-06
BSCNCVGN2--21 | RC Foundation - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-10-02 | 2026-10-14
BSCNARPUR--10 | Thermal Insulation Layer Floor Roof - Fire Hydrant | 2026-10-02 | 2026-10-02
BSCNARPUR--15 | External Dry mix including Plinth Painting - Fire Hydrant | 2026-10-02 | 2026-10-06
BSCNARMFN--04 | Installation of Main Gate & Secondary Gate - Fence - north | 2026-10-02 | 2026-10-08
BSCNCVTRN--595 | RC Walls & Raceway - Trenches - 175MVA Transformers to CB | 2026-10-01 | 2026-10-18
BSPRELGENCP13 | Delivery to Factory - Control & Protection System | 2026-10-01 | 2026-10-07
BSERELTR7RW02 | Install Cable Trays & Accessories of LV & Control Cables [TRF.175 - No.02] | 2026-10-01 | 2026-10-05
BSERELTR7T713 | Oil Processing - [TRF.175 - No.02] | 2026-10-01 | 2026-10-06
BSCNARPUR--09 | 2 layers of Bituminous membrane insulation including Screed Layer (Including Testing) For Roof - Fire Hydrant | 2026-10-01 | 2026-10-01
BSCNCVFFR--74 | PC Foundation Works - AUX Room | 2026-09-30 | 2026-10-04
BSCNCVCRB--108 | Masonry Works For Future Room SWG - Control Building - Ground Floor | 2026-09-30 | 2026-10-13
BSCNCVTRN--825 | Excavation Works - Trenches - Road Crossing - 66 KV GIS | 2026-09-30 | 2026-10-08
BSCNCVTY4--20 | PC Foundation - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-09-30 | 2026-10-04
BSCNCVGI2--11 | RC Side Walls for Internal Trench - 220 KV GIS Building | 2026-09-30 | 2026-10-06
BSPRELGENG207 | Delivery to Site - 220 KV GIS & GIB | 2026-09-30 | 2026-10-13
BSPRMEGENFA03 | Manufacturing - Fire Alarm System | 2026-09-30 | 2026-11-08
BSPRELGENCB07 | Delivery to Site - Capacitor Banks (9 MVAR) | 2026-09-30 | 2026-10-09
BSPRELGENG107 | Delivery to Site - 66 KV GIS & GIB | 2026-09-30 | 2026-10-13
BSCNCVTRN--35 | Excavation Works - Trenches - Road Crossing - 175MVA Transformers to 66 KV GIS | 2026-09-30 | 2026-10-04
BSERELTR7T705 | Cable pulling & Terminations - [TRF.175 - No.01] | 2026-09-30 | 2026-10-08
BSCNARTR7--07 | Gravel Laying - 2*175 MVA Transformers | 2026-09-30 | 2026-10-04
BSERELTR7T712 | HV & LV Bushing Installation - [TRF.175 - No.02] | 2026-09-30 | 2026-09-30
BSCNMPPUR--01 | Embedded Conduits - Fire Hydrant | 2026-09-30 | 2026-10-04
BSCNCVGUT--05 | RC Platform - Guard Towers - north | 2026-09-30 | 2026-10-06
BSCNCVGN1--11 | PC Foundation - 66 KV Outdoor Equipment - Equipment Foundation | 2026-09-30 | 2026-10-09
BSCNCVGN1--20 | PC Foundation - 66 KV Outdoor Equipment - GIB Foundation | 2026-09-30 | 2026-10-05
BSCNCVTY4--11 | PC Foundation - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-09-30 | 2026-10-04
BSCNCVTY4--02 | PC Foundation - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-09-30 | 2026-10-04
BSCNCVTY4--28 | PC Foundation - 3*40 MVA Outdoor Equipment & Gantry - NER Foundation | 2026-09-30 | 2026-10-11
BSCNARGI1--22 | Side Walks for 66 kV GIS Building - 66 KV GIS Building | 2026-09-30 | 2026-10-15
BSCNCVGI1--10 | RC Base slab for Internal Trench - 66 KV GIS Building | 2026-09-30 | 2026-10-06
BSPRCVGENGR05 | Delivery to Site - Gantry Steel Structure | 2026-09-29 | 2026-10-05
BSPRCVGENGR15 | Purchasing Request - Lighting arms | 2026-09-29 | 2026-10-05
BSCNCVTY7--23 | Bitumen Isolation - 2*175 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-09-29 | 2026-10-02
BSCNARGI2--23 | Drainage System for Roofing - 220 KV GIS Building | 2026-09-29 | 2026-10-02
BSCNARPUR--07 | Epoxy Paint For Tank - Fire Hydrant | 2026-09-29 | 2026-10-04
BSKDGNFFR--02 | Ready for Erection - Fire Fighting Room 175 |  | 2026-09-28
BSCNARCRB--10 | Plastering for Internal Walls For Ground Floor SWG - Control Building | 2026-09-28 | 2026-10-15
BSCNCVTRN--94 | RC Raft & Pipes positioning - Duct banks - Road Crossing - Gantry Area 220 KV | 2026-09-28 | 2026-10-14
BSCNCVGN2--08 | Decorative Painting - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-09-28 | 2026-10-01
BSCNARFFR--17 | Internal Painting Works - 66/11 kV Firefighting Room | 2026-09-28 | 2026-10-02
BSCNARPUR--08 | Light Weight Concrete for roofing - Fire Hydrant | 2026-09-27 | 2026-09-30
BSCNCVGI2--10 | RC Base slab for Internal Trench - 220 KV GIS Building | 2026-09-25 | 2026-09-29
BSERELTR7RW01 | Install Cable Trays & Accessories of LV & Control Cables [TRF.175 - No.01] | 2026-09-25 | 2026-09-29
BSERELTR7T711 | Erection of transformer Accessories (Radiator -conservator-pipes and fans ) - [TRF.175 - No.02] | 2026-09-25 | 2026-09-29
BSERELTR7T704 | Oil Processing - [TRF.175 - No.01] | 2026-09-25 | 2026-09-30
BSCNARPUR--14 | External Plastering Works - Fire Hydrant | 2026-09-25 | 2026-10-01
BSCNARPUR--02 | Internal Plastering For Pump Room - Fire Hydrant | 2026-09-25 | 2026-10-04
BSCNCVGUT--25 | Excavation Works - Guard Towers - West | 2026-09-25 | 2026-10-02
BSCNCVGI1--09 | PC Raft Works for Internal Trench - 66 KV GIS Building | 2026-09-25 | 2026-09-29
BSCNCVTY7--22 | RC Pedestals & Anchors Installation - 2*175 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-09-24 | 2026-09-28
BSERELTR7T703 | HV & LV Bushing Installation - [TRF.175 - No.01] | 2026-09-24 | 2026-09-24
BSCNCVGN2--20 | PC Foundation - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-09-24 | 2026-10-01
BSCNCVMFN--10 | Backfilling Works - Fence - north | 2026-09-24 | 2026-10-01
BSCNARGI1--21 | Dry mix for Facades including Plinth painting - 66 KV GIS Building | 2026-09-24 | 2026-09-29
BSCNARFFR--35 | Epoxy Painting - 220/66 KV Firefighting Room | 2026-09-23 | 2026-09-28
BSCNCVGI2--09 | PC Raft Works for Internal Trench - 220 KV GIS Building | 2026-09-23 | 2026-09-24
BSPRELGENTL06 | Custom Clearance - Complete Telecommunication System With All accessories and Spare Parts | 2026-09-23 | 2026-11-21
BSCNMPTR7--05 | Installing Fire Alarm- 2*175 MVA Transformers | 2026-09-23 | 2026-10-04
BSCNCVTY7--12 | RC Foundation - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-09-23 | 2026-10-05
BSCNCVTY7--03 | RC Foundation - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-09-23 | 2026-10-05
BSCNMPTR7--02 | Wiring & Terminations - 2*175 MVA Transformers | 2026-09-23 | 2026-10-04
BSCNARFFR--05 | Door Installation - 220/66 KV Firefighting Room | 2026-09-23 | 2026-09-24
BSCNARGI2--22 | Installation of Caged Ladder and handrails - 220 KV GIS Building | 2026-09-23 | 2026-09-27
BSCNCVGUT--04 | Columns & Beams - Guard Towers - north | 2026-09-23 | 2026-09-29
BSCNCVTRN--91 | Backfilling Works - Trenches - Road Crossing - 66 KV GIS to CB | 2026-09-22 | 2026-09-27
BSCNCVGN2--12 | RC Foundation - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-09-22 | 2026-10-09
BSCNARMFN--05 | Internal & External Drymix - Fence - north | 2026-09-22 | 2026-10-02
BSCNCVCRB--58 | Concrete Works for Slab For Control Building- First Floor | 2026-09-21 | 2026-10-18
BSCNCVTRN--93 | PC Raft - Duct banks - Road Crossing - Gantry Area 220 KV | 2026-09-21 | 2026-09-27
BSPRCVGENGR04 | FAT - Gantry Steel Structure | 2026-09-21 | 2026-09-28
BSCNCVGN2--09 | Graveling Works - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-09-21 | 2026-09-25
BSCNCVGN2--07 | Grouting for top of Pedestals - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-09-21 | 2026-09-27
BSCNARFFR--16 | Internal Plastering - 66/11 kV Firefighting Room | 2026-09-21 | 2026-09-27
BSCNARTR4--04 | Fixation of Rails - 2*40 MVA Transformers | 2026-09-21 | 2026-10-04
BSCNCVGI1--08 | Backfilling Works till bottom level of internal trench & External - 66 KV GIS Building | 2026-09-21 | 2026-09-24
BSCNCVTRN--585 | RC Raft - Trenches - 175MVA Transformers to CB | 2026-09-20 | 2026-09-30
BSCNCVGI2--08 | Backfilling Works till bottom level of internal trench & External - 220 KV GIS Building | 2026-09-20 | 2026-09-22
BSCNCVTY7--21 | RC Foundation - 2*175 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-09-20 | 2026-09-23
BSERELTR7T702 | Erection of transformer Accessories (Radiator -conservator-pipes and fans ) - [TRF.175 - No.01] | 2026-09-20 | 2026-09-23
BSCNARGI2--17 | Tile works for roofing & Joints filling - 220 KV GIS Building | 2026-09-20 | 2026-09-28
BSCNARPUR--06 | Surface preparation & curing and Apply Water Test for Tank - Fire Hydrant | 2026-09-20 | 2026-09-28
BSCNARPUR--01 | Masonry Works For Pump Room - Fire Hydrant | 2026-09-20 | 2026-09-24
BSCNCVPUR--10 | RC Parapet for Roof Slab - Fire Hydrant | 2026-09-20 | 2026-09-25
BSCNARGI1--20 | External Platform for Personnel Doors - 66 KV GIS Building | 2026-09-20 | 2026-09-23
BSCNCVCRB--168 | Masonry Works of Battery room - Control Building | 2026-09-18 | 2026-10-01
BSCNARCRB--11 | Internal painting Ceiling For Ground Floor SWG - Control Building | 2026-09-18 | 2026-10-01
BSCNARCRB--09 | Embedding Electric Sleeves Inside Walls For Ground Floor SWG - Control Building | 2026-09-18 | 2026-09-27
BSPRMPGENTD02 | PO Issuance - Telephone & Data System | 2026-09-18 | 2026-11-16
BSCNARTR7--08 | Decorative Painting for Exposed parts in transformer foundation - 2*175 MVA Transformers | 2026-09-18 | 2026-09-22
BSCNARTR7--06 | Steel Greeting Works - 2*175 MVA Transformers | 2026-09-18 | 2026-09-29
BSERELTR7T710 | Positioning - [TRF.175 - No.02] | 2026-09-18 | 2026-09-18
BSERELTR7T701 | Positioning - [TRF.175 - No.01] | 2026-09-18 | 2026-09-18
BSCNCVFFR--09 | RC SOG & Upstand Concrete Foundation for Equipment - 220/66 KV Firefighting Room | 2026-09-18 | 2026-09-22
BSCNARGI2--16 | Geotextile Laying - 220 KV GIS Building | 2026-09-18 | 2026-09-18
BSCNMPGI2--11 | Installation of OH Crane - 220 KV GIS Building | 2026-09-18 | 2026-09-23
BSERELCRBLS01 | Install Lightening System for the Building [CTRL] | 2026-09-18 | 2026-09-27
BSCNMPFFR--11 | Embedded Conduits - 66/11 kV Firefighting Room | 2026-09-18 | 2026-09-20
BSKDGNTR7--01 | Ready for Erection - 175 MVA Transformers |  | 2026-09-17
BSCNARCRB--08 | Installing Fire Extinguishers For Basement floor - Control Building | 2026-09-17 | 2026-09-17
BSCNARFFR--14 | Side Walks for FF Room - 220/66 KV Firefighting Room | 2026-09-17 | 2026-09-21
BSCNARGI2--15 | Thermal Insulation Layer - 220 KV GIS Building | 2026-09-17 | 2026-09-17
BSCNCVGUT--03 | RC Footings & Tie Beams - Guard Towers - north | 2026-09-17 | 2026-09-22
BSCNCVMFN--07 | Bitumen isolation - Fence - north | 2026-09-17 | 2026-09-23
BSCNARFFR--28 | Side Walks for FF Room - 66/11 kV Firefighting Room | 2026-09-17 | 2026-09-21
BSCNCVGI2--06 | Masonry works Under SOG - 220 KV GIS Building | 2026-09-16 | 2026-09-18
BSPRELGENTL05 | Shipping - Complete Telecommunication System With All accessories and Spare Parts | 2026-09-16 | 2026-09-22
BSPRELGENSA33 | Custom Clearance - Surge Arresters | 2026-09-16 | 2026-10-05
BSPRMEGENFA02 | PO Issuance - Fire Alarm System | 2026-09-16 | 2026-09-29
BSCNCVTRN--90 | Bitumen Isolation - Trenches - Road Crossing - 66 KV GIS to CB | 2026-09-16 | 2026-09-21
BSCNCVFFR--08 | 2 layer of bituminous membrane & Screed Layer - 220/66 KV Firefighting Room | 2026-09-16 | 2026-09-17
BSCNARFFR--13 | Drainage System for Roofing - 66/11 kV Firefighting Room | 2026-09-16 | 2026-09-16
BSCNARMFN--01 | Embedded conduits for Lighting system - Fence - north | 2026-09-16 | 2026-09-24
BSCNARMFN--03 | Internal & External Plastering - Fence - north | 2026-09-16 | 2026-10-02
BSCNARMFN--02 | Masonry Works till bottom of top beam - Fence - north | 2026-09-16 | 2026-09-24
BSCNCVMFN--09 | RC Top beams - Fence - north | 2026-09-16 | 2026-09-23
BSCNCVMFN--08 | RC Columns - Fence - north | 2026-09-16 | 2026-09-23
BSCNCVMFN--06 | RC middle Beams - Fence - north | 2026-09-16 | 2026-09-23
BSCNARFFR--27 | Drainage System for Roofing - 66/11 kV Firefighting Room | 2026-09-16 | 2026-09-16
BSCNMPGI1--11 | Installation of OH Crane - 66 KV GIS Building | 2026-09-16 | 2026-09-22
BSCNARGI1--09 | Installation of Personnel Door, Roll shutter doors - 66 KV GIS Building | 2026-09-16 | 2026-09-27
BSCNCVGI1--06 | Masonry works Under SOG - 66 KV GIS Building | 2026-09-16 | 2026-09-20
BSCNCVTRN--575 | PC Raft - Trenches - 175MVA Transformers to CB | 2026-09-15 | 2026-09-18
BSPRELGENOH04 | Delivery to Site - OH Conductors | 2026-09-15 | 2026-09-20
BSPRELGENCA03 | Manufacturing - Cable trays & Accessories (Raceway) Patch 02 | 2026-09-15 | 2026-10-29
BSCNCVTY7--11 | PC Foundation - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-09-15 | 2026-09-22
BSCNCVTY7--02 | PC Foundation - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-09-15 | 2026-09-22
BSCNCVTY7--20 | PC Foundation - 2*175 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-09-15 | 2026-09-18
BSCNCVGN2--19 | Excavation Works - 220 KV Outdoor Equipment & Gantry - GIB Foundation | 2026-09-15 | 2026-09-23
BSCNARGI2--21 | Side Walks for 220 KV GIS Building - 220 KV GIS Building | 2026-09-15 | 2026-09-22
BSCNCVMFN--05 | Masonry Works till bottom of middle beam - Fence - north | 2026-09-15 | 2026-09-23
BSCNCVFFR--07 | PC for SOG - 220/66 KV Firefighting Room | 2026-09-14 | 2026-09-15
BSCNARFFR--04 | Windows Installation - 220/66 KV Firefighting Room | 2026-09-14 | 2026-09-15
BSCNCVFFR--64 | Excavation Works - AUX Room | 2026-09-13 | 2026-09-29
BSCNARGI2--20 | External Platform for Personnel Doors- 220 KV GIS Building | 2026-09-13 | 2026-09-18
BSCNCVGUT--02 | PC footings - Guard Towers - north | 2026-09-13 | 2026-09-16
BSCNCVMFN--04 | Columns necks - Fence - north | 2026-09-13 | 2026-09-23
BSCNCVMFN--03 | RC Footings & Tie Beams - Fence - north | 2026-09-13 | 2026-09-23
BSCNCVMFN--02 | PC footings - Fence - north | 2026-09-13 | 2026-09-23
BSCNCVMFN--31 | Excavation Works - Fence - West | 2026-09-13 | 2026-10-02
BSCNCVGEN--01 | Excavation Works - Foundation - Capacitor Bank | 2026-09-13 | 2026-09-23
BSCNCVFFR--21 | RC SOG & Upstand Concrete Foundation for Equipment - 66/11 kV Firefighting Room | 2026-09-13 | 2026-09-17
BSCNARCRB--06 | Epoxy Paint on Floor Basement floor - Control Building | 2026-09-11 | 2026-09-16
BSCNARGI2--14 | test of moisture insulation - 220 KV GIS Building | 2026-09-11 | 2026-09-16
BSCNCVTRN--92 | Excavation Works - Trenches - Road Crossing - Gantry Area 220 KV | 2026-09-11 | 2026-09-20
BSCNARTR7--04 | Epoxy Paint for Transformers - 2*175 MVA Transformers | 2026-09-11 | 2026-09-17
BSCNARFFR--10 | Tile works for roofing - 220/66 KV Firefighting Room | 2026-09-11 | 2026-09-15
BSCNCVGN2--06 | Backfilling Works - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-09-11 | 2026-09-20
BSCNCVGN2--11 | PC Foundation - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-09-11 | 2026-09-21
BSCNARGI2--05 | Installation of Windows - 220 KV GIS Building | 2026-09-11 | 2026-09-15
BSCNARFFR--24 | Tile works for roofing - 66/11 kV Firefighting Room | 2026-09-11 | 2026-09-15
BSPRELGENT705 | Delivery to Site - Three phase transformer 175 MVA with all accessories. | 2026-09-10 | 2026-09-17
BSCNARFFR--09 | Geotextile Laying - 220/66 KV Firefighting Room | 2026-09-10 | 2026-09-10
BSCNCVFFR--20 | 2 layer of bituminous membrane & Screed Layer - 66/11 kV Firefighting Room | 2026-09-10 | 2026-09-11
BSCNARFFR--23 | Geotextile Laying - 66/11 kV Firefighting Room | 2026-09-10 | 2026-09-10
BSCNARGI1--05 | Installation of Windows - 66 KV GIS Building | 2026-09-10 | 2026-09-15
BSPRELGENTL04 | FAT - Complete Telecommunication System With All accessories and Spare Parts | 2026-09-09 | 2026-09-15
BSPRELGENG206 | Custom Clearance - 220 KV GIS & GIB | 2026-09-09 | 2026-09-29
BSPRELGENG106 | Custom Clearance - 66 KV GIS & GIB | 2026-09-09 | 2026-09-29
BSCNARFFR--08 | Thermal Insulation Layer - 66/11 kV Firefighting Room | 2026-09-09 | 2026-09-09
BSCNARFFR--03 | Internal Painting Works - 220/66 KV Firefighting Room | 2026-09-09 | 2026-09-13
BSERELCRBES02 | Install Secondary Earthing for the Building [CTRL - Bat R] | 2026-09-09 | 2026-09-09
BSERELCRBES03 | Install Secondary Earthing for the Building [CTRL - AC/DC R] | 2026-09-09 | 2026-09-13
BSERELCRBES04 | Install Secondary Earthing for the Building [CTRL - Tele R] | 2026-09-09 | 2026-09-09
BSERELCRBES05 | Install Secondary Earthing for the Building [CTRL - R] | 2026-09-09 | 2026-09-17
BSCNARFFR--22 | Thermal Insulation Layer - 66/11 kV Firefighting Room | 2026-09-09 | 2026-09-09
BSPRELGENDS19 | Delivery to Site - Disconnector Switches | 2026-09-08 | 2026-09-14
BSPRELGENLT07 | Delivery to Site - Wave Trap "Line Trap" | 2026-09-08 | 2026-09-14
BSPRELGENVT21 | Delivery to Site - Voltage Transformer (CVT,VT) | 2026-09-08 | 2026-09-14
BSPRELGENCT19 | Delivery to Site - Current Transformers | 2026-09-08 | 2026-09-14
BSPRMPGENTD01 | Purchasing Request - Telephone & Data System | 2026-09-08 | 2026-09-17
BSCNCVTRN--89 | RC Raft & Pipes positioning - Trenchs - Road Crossing - 66 KV GIS to CB | 2026-09-08 | 2026-09-15
BSCNARFFR--07 | 2 layers of Bituminous membrane insulation including Screed Layer (including Testing) - 66/11 kV Firefighting Room | 2026-09-08 | 2026-09-08
BSCNARGI2--04 | Internal Painting For Walls - 220 KV GIS Building | 2026-09-08 | 2026-09-15
BSCNARGI2--03 | Internal Painting For Ceiling Roof Slab - 220 KV GIS Building | 2026-09-08 | 2026-09-14
BSCNARGI2--19 | Dry mix for Facades including Plinth painting - 220 KV GIS Building | 2026-09-08 | 2026-09-14
BSCNARGI2--18 | External Plastering Works - 220 KV GIS Building | 2026-09-08 | 2026-09-18
BSCNARGI1--04 | Internal Painting For Walls - 66 KV GIS Building | 2026-09-08 | 2026-09-15
BSCNARGI1--03 | Internal Painting For Ceiling Roof Slab - 66 KV GIS Building | 2026-09-08 | 2026-09-14
BSCNARFFR--21 | 2 layers of Bituminous membrane insulation including Screed Layer (including Testing) - 66/11 kV Firefighting Room | 2026-09-08 | 2026-09-08
BSCNARFFR--26 | External Dry mix including Plinth Painting - 66/11 kV Firefighting Room | 2026-09-08 | 2026-09-13
BSCNARGI1--18 | External Plastering Works - 66 KV GIS Building | 2026-09-08 | 2026-09-18
BSPRELGENCB06 | Custom Clearance - Capacitor Banks | 2026-09-07 | 2026-09-29
BSPRELGENLS08 | Delivery to Site - Lightning Cables | 2026-09-07 | 2026-09-07
BSPRELGENLS07 | Delivery to Site - Lightning Materials | 2026-09-07 | 2026-09-07
BSCNARFFR--12 | External Dry mix including Plinth Painting - 220/66 KV Firefighting Room | 2026-09-07 | 2026-09-11
BSCNARGI2--13 | 2 layers of Bituminous membrane insulation including Screed Layer (Including Testing) - 220 KV GIS Building | 2026-09-07 | 2026-09-10
BSCNCVFFR--19 | PC for SOG - 66/11 kV Firefighting Room | 2026-09-07 | 2026-09-09
BSCNARTR4--01 | Surface preparation & Decorative Painting for Firewalls - 2*40 MVA Transformers | 2026-09-07 | 2026-09-20
BSCNARCRB--03 | Screed on floor For Basement floor - Control Building | 2026-09-06 | 2026-09-10
BSCNCVFFR--06 | Internal Backfilling - 220/66 KV Firefighting Room | 2026-09-06 | 2026-09-08
BSCNCVGN2--05 | Bitumen Isolation - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-09-06 | 2026-09-10
BSPRELGENES22 | Delivery to Site - Earthing Risers Material | 2026-09-05 | 2026-09-08
BSCNCVCRB--98 | Masonry Works For SWG - Control Building - Ground Floor | 2026-09-04 | 2026-09-17
BSCNCVCRB--48 | Columns Works For Control Building - First Floor | 2026-09-04 | 2026-09-20
BSPRELGENSE13 | Delivery to Site - Cable Sealing End "HV" | 2026-09-04 | 2026-09-10
BSPRELGENES24 | Delivery to Site - Secondary Earthing Material | 2026-09-04 | 2026-09-07
BSPRELGENES23 | Delivery to Site - Earthing Risers Cables | 2026-09-04 | 2026-09-07
BSPRELGENES21 | Delivery to Site - Secondary Earthing Cables | 2026-09-04 | 2026-09-07
BSCNARFFR--02 | Internal Plastering - 220/66 KV Firefighting Room | 2026-09-04 | 2026-09-08
BSCNCVGUT--01 | Excavation Works - Guard Towers - north | 2026-09-04 | 2026-09-11
BSCNARTR4--02 | Membrane insulation for Basin Walls & Masonry Works for Membrane Protection - 2*40 MVA Transformers | 2026-09-04 | 2026-09-08
BSPRELGENCP10 | Custom Clearance - Control & Protection System | 2026-09-03 | 2026-09-30
BSCNCVFFR--05 | Bitumen isolation for Foundation - 220/66 KV Firefighting Room | 2026-09-03 | 2026-09-04
BSCNARFFR--06 | Light Weight sloped Concrete for roofing - 66/11 kV Firefighting Room | 2026-09-03 | 2026-09-07
BSCNCVPUR--09 | RC Roof Slab - Fire Hydrant | 2026-09-03 | 2026-09-18
BSCNCVFFR--18 | Internal Backfilling - 66/11 kV Firefighting Room | 2026-09-03 | 2026-09-06
BSCNARFFR--20 | Light Weight Concrete for roofing - 66/11 kV Firefighting Room | 2026-09-03 | 2026-09-07
BSCNARFFR--25 | External Plastering Works - 66/11 kV Firefighting Room | 2026-09-03 | 2026-09-07
BSPRELGENSA27 | Shipping - Surge Arresters | 2026-09-02 | 2026-09-15
BSPRMEGENFA01 | Purchasing Request - Fire Alarm System | 2026-09-02 | 2026-09-15
BSCNCVTRN--88 | PC Raft - Trenches - Road Crossing - 66 KV GIS to CB | 2026-09-02 | 2026-09-07
BSCNARFFR--11 | External Plastering Works - 220/66 KV Firefighting Room | 2026-09-02 | 2026-09-06
BSCNMPFFR--03 | Embedded Conduits - 220/66 KV Firefighting Room | 2026-09-02 | 2026-09-03
BSCNARGI2--12 | Light Weight Concrete for roofing - 220 KV GIS Building | 2026-09-02 | 2026-09-06
BSCNARGI1--17 | Tile works for roofing & Joints filling - 66 KV GIS Building | 2026-09-02 | 2026-09-08
BSCNCVFFR--17 | Bitumen isolation for Foundation - 66/11 kV Firefighting Room | 2026-09-01 | 2026-09-02
BSCNARGI1--16 | Geotextile Laying - 66 KV GIS Building | 2026-09-01 | 2026-09-01
BSCNARTR7--18 | Fixation of Rails for catch basin - 2*175 MVA Transformers | 2026-08-31 | 2026-09-10
BSPRELGENAD29 | Delivery to Site - 11 KV /0.4KV (500 KVA) Aux. Transformer | 2026-08-30 | 2026-09-05
BSCNCVFFR--04 | Masonry Works for Backfilling - 220/66 KV Firefighting Room | 2026-08-30 | 2026-09-02
BSCNCVFFR--12 | RC Parapet for Roof Slab - 220/66 KV Firefighting Room | 2026-08-30 | 2026-09-02
BSCNARFFR--01 | Masonry Works - 220/66 KV Firefighting Room | 2026-08-30 | 2026-09-01
BSCNCVFFR--16 | Masonry Works for Backfilling - 66/11 kV Firefighting Room | 2026-08-30 | 2026-08-31
BSCNCVFFR--24 | RC Parapet for Roof Slab - 66/11 kV Firefighting Room | 2026-08-30 | 2026-09-02
BSCNARFFR--15 | Masonry Works - 66/11 kV Firefighting Room | 2026-08-30 | 2026-09-02
BSCNCVTRN--87 | Excavation Works - Trenches - Road Crossing - 66 KV GIS to CB | 2026-08-28 | 2026-09-01
BSCNCVCRB--15 | RC Concrete Works for SOG- Basement Slab For Control Building | 2026-08-27 | 2026-09-04
BSCNARGI2--02 | Internal Plastering Works - 220 KV GIS Building | 2026-08-27 | 2026-09-07
BSCNARGI1--19 | Drainage System for Roofing - 66 KV GIS Building | 2026-08-27 | 2026-08-31
BSCNARGI1--15 | Thermal Insulation Layer - 66 KV GIS Building | 2026-08-27 | 2026-08-27
BSCNARGI1--02 | Internal Plastering Works - 66 KV GIS Building | 2026-08-27 | 2026-09-07
BSPRELGENMV23 | Delivery to Site - MV Cables | 2026-08-26 | 2026-09-02
BSPRELGENHV05 | Delivery to Site - HV Cables | 2026-08-26 | 2026-09-02
BSPRELGENCA4 | PO Issuance - Cable trays & Accessories (Raceway) Patch 02 | 2026-08-26 | 2026-09-14
BSCNCVOP7--02 | Lay & Compact Outer Backfilling Layers around Building [OP - TRF.175] | 2026-08-26 | 2026-08-30
BSCNARTR4--03 | Slopped Concrete inside the transformers basins - 2*40 MVA Transformers | 2026-08-26 | 2026-09-03
BSPRELGENT715 | Custom Clearance - Three phase transformer 175 MVA with all accessories. | 2026-08-25 | 2026-09-09
BSCNCVCRB--14 | Apply Protection for Membrane For Control Building | 2026-08-25 | 2026-08-26
BSPRMEGENFS43 | Delivery to Site - 40 MVA Transformers fire fighghting system | 2026-08-25 | 2026-08-25
BSPRMEGENFS44 | Delivery to Site - 175 MVA Transformers fire fighghting system | 2026-08-25 | 2026-08-25
BSCNMPGI1--02 | Embedded Conduits for walls Works - 66 KV GIS Building | 2026-08-25 | 2026-08-26
BSPRCVGENGR58 | Delivery to Site - LCC Support | 2026-08-24 | 2026-08-27
BSPRMEGENFS41 | FAT - 40 MVA Transformers fire fighghting Water Tank | 2026-08-24 | 2026-08-24
BSCNMPGI2--02 | Embedded Conduits for walls Works - 220 KV GIS Building | 2026-08-24 | 2026-08-26
BSPRMEGENFS42 | FAT - 175 MVA Transformers fire fighghting Water Tank | 2026-08-24 | 2026-08-24
BSPRCVGENGR14 | Delivery to Site - Panels Frame | 2026-08-24 | 2026-08-27
BSCNCVOP4--02 | Lay & Compact Outer Backfilling Layers around Building [OP - TRF.40] | 2026-08-24 | 2026-08-27
BSPRELGENAD22 | FAT - 11 KV /0.4KV (500 KVA) Aux. Transformer | 2026-08-23 | 2026-08-29
BSCNARTR7--09 | manuvery slab and Fixation of Rails - 2*175 MVA Transformers | 2026-08-23 | 2026-09-11
BSCNCVMFN--01 | Excavation Works - Fence - north | 2026-08-23 | 2026-09-11
BSCNARGI1--13 | 2 layers of Bituminous membrane insulation including Screed Layer (Including Testing) - 66 KV GIS Building | 2026-08-23 | 2026-08-26
A3540 | RECC- I/O LIST - Approval | 2026-08-21 | 2026-09-07
BSENMEGENTD05 | Material approval - Telephone & Data System | 2026-08-21 | 2026-09-07
BSCNCVPUR--07 | Walls Joints - Fire Hydrant | 2026-08-21 | 2026-08-25
BSCNCVPUR--08 | RC columns & Walls - Fire Hydrant | 2026-08-21 | 2026-09-02
BSCNCVCRB--13 | Membrane Isolation for SOG- Basement Slab For Control Building | 2026-08-20 | 2026-08-24
BSPRELGENMV53 | FAT - MV Cables | 2026-08-19 | 2026-08-26
BSPRELGENHV04 | FAT - HV Cables | 2026-08-19 | 2026-08-26
BSPRELGENMV25 | Delivery to Site - Cable Steel Supports | 2026-08-19 | 2026-09-02
BSPRELGENSA21 | FAT - Surge Arresters | 2026-08-19 | 2026-09-01
BSPRELGENCA04 | Delivery to Site - Cable trays & Accessories (Raceway) Patch 01 | 2026-08-19 | 2026-08-25
BSCNMPOP7--01 | Install & Test of Oil Pipes [OP - TRF.175] | 2026-08-19 | 2026-08-25
BSCNCVWAT--07 | Backfilling Works - 220/66 RC Tank | 2026-08-19 | 2026-08-19
BSCNCVGN2--04 | RC Pedestals & Anchors Installation - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-08-19 | 2026-09-04
BSCNCVGN2--03 | RC Foundation - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-08-19 | 2026-09-03
BSPRELGENAD635 | Delivery to Site - 48V Battery Charger | 2026-08-18 | 2026-08-27
BSPRELGENAD625 | Delivery to Site - 220V DC battery Charger | 2026-08-18 | 2026-08-27
BSPRELGENDS16 | Custom Clearance - Disconnector Switches | 2026-08-18 | 2026-09-07
BSPRELGENLT06 | Custom Clearance - Wave Trap "Line Trap" | 2026-08-18 | 2026-09-07
BSPRELGENVT18 | Custom Clearance - Voltage Transformer (CVT,VT) | 2026-08-18 | 2026-09-07
BSPRELGENCT16 | Custom Clearance - Current Transformers | 2026-08-18 | 2026-09-07
BSPRELGENLS06 | Manufacturing - Lightning Cables | 2026-08-18 | 2026-09-06
BSPRELGENLS05 | Manufacturing - Lightning Materials | 2026-08-18 | 2026-09-06
BSCNARTR7--05 | Backfilling works - 2*175 MVA Transformers | 2026-08-18 | 2026-08-21
BSCNARGI1--12 | Light Weight Concrete for roofing - 66 KV GIS Building | 2026-08-18 | 2026-08-21
BSENMEGENFA05 | Material approval - Fire Alarm System | 2026-08-17 | 2026-09-01
BSCNMPOP4--01 | Install & Test of Oil Pipes [OP - TRF.40] | 2026-08-17 | 2026-08-23
BSCNCVCRB--12 | PC for SOG- Basement Slab For Control Building | 2026-08-16 | 2026-08-19
BSPRELGENOH03 | Manufacturing - OH Conductors | 2026-08-16 | 2026-09-14
A3530 | NECC- I/O LIST - Approval | 2026-08-14 | 2026-08-31
A1130 | RECC- I/O LIST - Drawing Submittal | 2026-08-14 | 2026-08-20
BSPRELGENSE11 | Custom Clearance - Cable Sealing End "HV" | 2026-08-14 | 2026-09-03
BSCNARTR7--03 | Slopped Concrete inside the transformers basins - 2*175 MVA Transformers | 2026-08-14 | 2026-08-23
BSCNARTR7--02 | Membrane insulation for Basin Walls & Masonry Works for Membrane Protection(outer till 0 level) - 2*175 MVA Transformers | 2026-08-14 | 2026-08-17
BSCNARTR7--01 | Surface preparation & Decorative Painting for Firewalls - 2*175 MVA Transformers | 2026-08-14 | 2026-08-30
BSPRELGENCP09 | Shipping - Control & Protection System | 2026-08-13 | 2026-09-02
BSCNCVWAT--06 | Bitumen isolation for Foundation - 220/66 RC Tank | 2026-08-13 | 2026-08-18
BSCNCVWAT--05 | Installation of Steel Tank - 220/66 RC Tank | 2026-08-13 | 2026-08-19
BSCNCVFFR--11 | RC Roof Slab for FF Room (Including Embedded Conduits) - 220/66 KV Firefighting Room | 2026-08-13 | 2026-08-28
BSCNAROP7--05 | Apply Epoxy Painting for Internal Walls [OP - TRF.175] | 2026-08-12 | 2026-08-18
BSCNCVPUR--06 | RC Foundation - Fire Hydrant | 2026-08-12 | 2026-08-20
BSCNCVGI1--23 | RC Parapet for Roof Slab - 66 KV GIS Building | 2026-08-12 | 2026-08-17
BSCNARGI1--01 | Masonry works & lintel beams - 66 KV GIS Building | 2026-08-12 | 2026-08-24
BSPRELGENAD575 | FAT - 48V Battery Charger | 2026-08-11 | 2026-08-17
BSPRELGENAD565 | FAT - 220V DC battery Charger | 2026-08-11 | 2026-08-17
A4810 | SEPTIC TANK CALCULATION REPORT - Approval | 2026-08-11 | 2026-08-26
A4800 | SEPTIC TANK STRUCTURAL DRAWINGS - Drawing Approval | 2026-08-11 | 2026-08-26
BSPRELGENLS04 | PO Issuance - Lightning Cables | 2026-08-11 | 2026-08-17
BSPRELGENLS03 | PO Issuance - Lightning Materials | 2026-08-11 | 2026-08-17
BSCNCVFFR--23 | RC Roof Slab for FF Room (Including Embedded Conduits) - 66/11 kV Firefighting Room | 2026-08-11 | 2026-08-28
BSCNCVGN2--02 | PC Foundation - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-08-10 | 2026-08-18
BSCNCVGI2--26 | RC Parapet for Roof Slab - 220 KV GIS Building | 2026-08-10 | 2026-08-14
BSCNARGI2--01 | Masonry works & lintel beams - 220 KV GIS Building | 2026-08-10 | 2026-08-23
BSPRMPGENGR12 | Delivery to Site - WIRING DEVICES | 2026-08-09 | 2026-08-15
BSCNCVWAT--04 | RC Pedestals and anchored bolt installation - 220/66 RC Tank | 2026-08-09 | 2026-08-12
BSPRELGENAD775 | Manufacturing - Building service panel | 2026-08-07 | 2026-11-04
BSPRELGENLS02 | Purchasing Request - Lightning Cables | 2026-08-07 | 2026-08-10
BSPRELGENLS01 | Purchasing Request - Lightning Materials | 2026-08-07 | 2026-08-10
A3510 | Alarm Annunciation SIGNAL LIST - Approval | 2026-08-06 | 2026-08-24
A1120 | NECC- I/O LIST - Drawing Submittal | 2026-08-06 | 2026-08-13
BSCNCVCRB--18 | Concrete Works for Slab For Control Building | 2026-08-06 | 2026-09-03
BSCNAROP7--04 | Apply Membrane Protection for slab [OP - TRF.175] | 2026-08-06 | 2026-08-11
BSCNCVPUR--05 | 2 layers of Bituminous membrane insulation & Screed Layer - Fire Hydrant | 2026-08-06 | 2026-08-11
BSPRELGENTI06 | Manufacturing - Tension Insulators 66 KV | 2026-08-05 | 2026-10-04
BSPRELGENTI05 | Manufacturing - Tension Insulators 220 KV | 2026-08-05 | 2026-10-04
A5740 | GUARD ROOM HVAC CALCULATION - Approval | 2026-08-04 | 2026-08-20
A5730 | GUARD ROOM DRAINAGE SYSTEM PLAN & DETAILS - Drawing Approval | 2026-08-04 | 2026-08-20
A5720 | GUARD ROOM WATER SUPPLY SYSTEM PLAN & DETAILS - Drawing Approval | 2026-08-04 | 2026-08-20
A5710 | GUARD ROOM HVAC SYSTEM LAYOUT & DETAILS - Drawing Approval | 2026-08-04 | 2026-08-20
A5300 | GUARD ROOM PANEL SCHEDULES - Drawing Approval | 2026-08-04 | 2026-08-20
A5290 | GUARD ROOM POWER SOCKET SYSTEM PLAN - Drawing Approval | 2026-08-04 | 2026-08-20
A5280 | GUARD ROOM NORMAL & EMERGENCY LIGHTING SYSTEM FLOOR PLAN - Drawing Approval | 2026-08-04 | 2026-08-20
A5270 | GUARD ROOM LIGHTING LUX - Drawing Approval | 2026-08-04 | 2026-08-20
A5050 | GUARD ROOM DATA & TELEPHONE SYSTEM LAYOUT & DETAILS - Drawing Approval | 2026-08-04 | 2026-08-20
A5040 | GUARD ROOM FIRE ALARM SYSTEM PLAN AND DETAILS - Drawing Approval | 2026-08-04 | 2026-08-20
A4530 | GUARD ROOM STRUCTURAL PLANS & SECTIONS - Drawing Approval | 2026-08-04 | 2026-08-20
A4520 | GUARD ROOM STRUCTURAL DESIGN CALCULATIONS - Approval | 2026-08-04 | 2026-08-20
A2430 | SEPTIC TANK CALCULATION REPORT - Submittal | 2026-08-04 | 2026-08-10
A2420 | SEPTIC TANK STRUCTURAL DRAWINGS - Drawing Submittal | 2026-08-04 | 2026-08-10
BSENMEGENTD04 | Material submittal - Telephone & Data System | 2026-08-04 | 2026-08-20
BSCNAROP4--04 | Masonry Protection Works for Walls [OP - TRF.40] | 2026-08-04 | 2026-08-09
BSCNAROP4--03 | Apply Membrane Protection for slab [OP - TRF.40] | 2026-08-04 | 2026-08-09
BSCNMPTR4--04 | Oil Drainage System Works in Transformers Foundation ( Manholes & Pipes to oil pits ) - 2*40 MVA Transformers | 2026-08-04 | 2026-08-16
BSCNCVTR4--09 | RC Firewalls 2nd Cast - 2*40 MVA Transformers | 2026-08-04 | 2026-08-25
BSCNARCRB--07 | Installing doors For Basement floor - Control Building | 2026-08-03 | 2026-08-06
BSCNCVCRB--11 | Backfilling below SOG- Basement Slab For Control Building | 2026-08-03 | 2026-08-14
BSCNCVFFR--10 | RC columns for FF Room - 220/66 KV Firefighting Room | 2026-08-03 | 2026-08-12
BSCNCVFFR--22 | RC columns for FF Room - 66/11 kV Firefighting Room | 2026-08-03 | 2026-08-10
BSCNAROP7--03 | Apply Membrane Waterproofing Sheets [OP - TRF.175] | 2026-08-02 | 2026-08-05
BSCNCVPUR--04 | Negative shuttering -Masonry Works till top level of RC raft - Fire Hydrant | 2026-08-02 | 2026-08-05
BSPRELGENSG05 | Delivery to Site - 11 KV MVSWGR ( S/S ) | 2026-08-01 | 2026-08-07
A6040 | Finish Engineering |  | 2026-07-31
A1100 | Alarm Annunciation SIGNAL LIST - Drawing Submittal | 2026-07-30 | 2026-08-05
BSPRELGENCP07 | FAT - Control & Protection System | 2026-07-30 | 2026-08-12
BSENELGENCP11 | SAS I/O SIGNAL LIST - Approval | 2026-07-30 | 2026-08-17
BSCNAROP7--02 | Apply Water Test for Tank [OP - TRF.175] | 2026-07-30 | 2026-07-31
BSCNAROP4--05 | Apply Epoxy Painting for Internal Walls [OP - TRF.40] | 2026-07-30 | 2026-08-05
BSCNAROP4--02 | Apply Membrane Waterproofing Sheets [OP - TRF.40] | 2026-07-30 | 2026-08-03
A3340 | GUARD ROOM HVAC CALCULATION - Submittal | 2026-07-29 | 2026-08-03
A3330 | GUARD ROOM DRAINAGE SYSTEM PLAN & DETAILS - Drawing Submittal | 2026-07-29 | 2026-08-03
A3320 | GUARD ROOM WATER SUPPLY SYSTEM PLAN & DETAILS - Drawing Submittal | 2026-07-29 | 2026-08-03
A3310 | GUARD ROOM HVAC SYSTEM LAYOUT & DETAILS - Drawing Submittal | 2026-07-29 | 2026-08-03
A2920 | GUARD ROOM PANEL SCHEDULES - Drawing Submittal | 2026-07-29 | 2026-08-03
A2910 | GUARD ROOM POWER SOCKET SYSTEM PLAN - Drawing Submittal | 2026-07-29 | 2026-08-03
A2900 | GUARD ROOM NORMAL & EMERGENCY LIGHTING SYSTEM FLOOR PLAN - Drawing Submittal | 2026-07-29 | 2026-08-03
A2890 | GUARD ROOM LIGHTING LUX - Drawing Submittal | 2026-07-29 | 2026-08-03
A2630 | GUARD ROOM DATA & TELEPHONE SYSTEM LAYOUT & DETAILS - Drawing Submittal | 2026-07-29 | 2026-08-03
A2620 | GUARD ROOM FIRE ALARM SYSTEM PLAN AND DETAILS - Drawing Submittal | 2026-07-29 | 2026-08-03
A2150 | GUARD ROOM STRUCTURAL PLANS & SECTIONS - Drawing Submittal | 2026-07-29 | 2026-08-03
A2140 | GUARD ROOM STRUCTURAL DESIGN CALCULATIONS - Submittal | 2026-07-29 | 2026-08-03
BSENMEGENFA04 | Material submittal - Fire Alarm System | 2026-07-29 | 2026-08-14
BSPRELGENNR05 | Delivery to Site - Single phase Earthing resistor,20 Ohm | 2026-07-29 | 2026-08-04
BSCNCVWAT--03 | RC Foundation Works - 220/66 RC Tank | 2026-07-29 | 2026-08-06
BSCNCVPUR--03 | PC Foundation - Fire Hydrant | 2026-07-29 | 2026-07-31
BSPRMEGENCR28 | Delivery to Site - OH Crane, Min 5 Ton ( GIS 66 ) | 2026-07-28 | 2026-08-03
BSPRMEGENCR27 | Delivery to Site - Monorail Crane 3 Ton | 2026-07-28 | 2026-08-03
BSPRMEGENCR26 | Delivery to Site - OH Crane, Min 5 Ton ( GIS 220 ) | 2026-07-28 | 2026-08-03
BSCNCVFFR--03 | RC Foundation Works - 220/66 KV Firefighting Room | 2026-07-27 | 2026-08-02
BSPRELGENG205 | Shipping - 220 KV GIS & GIB | 2026-07-26 | 2026-09-08
BSPRELGENG105 | Shipping - 66 KV GIS & GIB | 2026-07-26 | 2026-09-08
BSCNCVTR7--11 | RC Firewalls 4th Cast - 2*175 MVA Transformers | 2026-07-26 | 2026-08-04
BSCNMPGI1--01 | Embedded Conduits for ceiling Works - 66 KV GIS Building | 2026-07-26 | 2026-07-26
BSCNCVGI1--20 | RC Roof Slab and beams - 66 KV GIS Building | 2026-07-26 | 2026-08-11
BSPRMPGENLF28 | Delivery to Site - LIGHTING FIXTURES Outdoor | 2026-07-25 | 2026-07-31
BSPRELGENSG04 | FAT - 11 KV MVSWGR ( S/S ) | 2026-07-25 | 2026-07-31
BSPRMEGENFS40 | Manufacturing - Fire Extinguishers | 2026-07-25 | 2026-11-06
BSCNAROP7--01 | surface preparation and curing | 2026-07-24 | 2026-07-29
BSPRELGENCB05 | Shipping - Capacitor Banks | 2026-07-24 | 2026-09-06
BSCNCVWAT--02 | PC Foundation Works - 220/66 RC Tank | 2026-07-24 | 2026-07-28
BSCNCVFFR--02 | PC Foundation Works - 220/66 KV Firefighting Room | 2026-07-24 | 2026-07-26
BSCNCVFFR--15 | RC Foundation Works - 66/11 kV Firefighting Room | 2026-07-24 | 2026-08-02
BSCNARCRB--05 | Internal painting Walls For Basement floor - Control Building | 2026-07-22 | 2026-08-02
BSPRELGENNR04 | FAT - Single phase Earthing resistor,20 Ohm | 2026-07-22 | 2026-07-28
BSENELGENGR14 | SUBSTATION LIGHTNING LAYOUT - Drawing Approval | 2026-07-22 | 2026-08-06
BSENELGENCP02 | SAS I/O SIGNAL LIST - Drawing Submittal | 2026-07-22 | 2026-07-29
BSCNAROP4--01 | Apply Water Test for Tank [OP - TRF.40] | 2026-07-22 | 2026-07-29
BSCNCVTRN--86 | RC Covers laying - Trenches - 66 KV GIS to CB | 2026-07-21 | 2026-07-27
BSCNCVFFR--14 | PC Foundation Works - 66/11 kV Firefighting Room | 2026-07-21 | 2026-07-23
BSPRELGENCA14 | Manufacturing - Cable trays & Accessories (Raceway) Patch 01 | 2026-07-20 | 2026-08-18
BSCNCVOP7--08 | Oil pit Neck [OP - TRF.175] | 2026-07-20 | 2026-07-23
BSCNCVGI2--25 | RC Roof Slab and beams - 220 KV GIS Building | 2026-07-19 | 2026-08-09
BSCNMPGI2--01 | Embedded Conduits Ceiling Works - 220 KV GIS Building | 2026-07-19 | 2026-07-22
BSCNCVGI1--24 | Bracing Beams 3rd cast at Roof Slab- 66 KV GIS Building | 2026-07-17 | 2026-07-24
BSPRMEGENFS39 | Manufacturing - Fire hydrant system | 2026-07-17 | 2026-12-14
BSENELGENGR48 | SUBSTATION LIGHTNING CALCULATIONS - Approval | 2026-07-16 | 2026-07-31
A6100 | AUXILIARY TRANSFORMER ROOM STRUCTURAL DESIGN CALCULATIONS - Approval | 2026-07-15 | 2026-07-30
A6090 | AUXILIARY TRANSFORMER ROOM STRUCTURAL PLANS & SECTIONS - Drawing Approval | 2026-07-15 | 2026-07-30
BSCNCVCRB--06 | External Backfilling For Control Building | 2026-07-15 | 2026-07-28
BSPRELGENSE09 | Shipping -Cable Sealing End "HV" | 2026-07-15 | 2026-08-13
BSCNCVTR7--10 | RC Firewalls 3 rd Cast - 2*175 MVA Transformers | 2026-07-15 | 2026-07-24
BSCNCVOP4--08 | Oil pit Neck [OP - TRF.40] | 2026-07-15 | 2026-07-21
BSPRELGENT725 | Shipping - Three phase transformer 175 MVA with all accessories. | 2026-07-14 | 2026-08-24
BSCNCVCRB--17 | Columns Works For Control Building | 2026-07-14 | 2026-08-05
BSCNMPTR4--01 | Embedded Conduits for Lighting Fixtures - 2*40 MVA Transformers | 2026-07-14 | 2026-07-24
BSCNCVTR4--08 | RC Firewalls 1st Cast - 2*40 MVA Transformers | 2026-07-14 | 2026-08-03
A6070 | AUXILIARY TRANSFORMER ROOM STRUCTURAL PLANS & SECTIONS - Drawing Submittal | 2026-07-13 | 2026-07-14
A6060 | AUXILIARY TRANSFORMER ROOM STRUCTURAL DESIGN CALCULATIONS - Submittal | 2026-07-13 | 2026-07-14
A3980 | GUARD ROOM ARCHITECTURAL DRAWINGS DETAILS AND SCHEDULES - Drawing Approval | 2026-07-13 | 2026-07-28
A3970 | GUARD ROOM ARCHITECTURAL DRAWINGS ELEVATION - Drawing Approval | 2026-07-13 | 2026-07-28
A3960 | GUARD ROOM ARCHITECTURAL DRAWINGS SECTIONS - Drawing Approval | 2026-07-13 | 2026-07-28
A3950 | GUARD ROOM ARCHITECTURAL DRAWINGS PLANS - Drawing Approval | 2026-07-13 | 2026-07-28
BSPRMEGENHC14 | Delivery to Site - Fans & Ventilation System | 2026-07-13 | 2026-07-24
BSENELGENGR05 | SUBSTATION LIGHTNING LAYOUT - Drawing Submittal | 2026-07-13 | 2026-07-21
BSCNCVOP7--07 | RC Slab [OP - TRF.175] | 2026-07-13 | 2026-07-19
BSCNCVGI2--22 | Bracing Beams 3rd Cast - 220 KV GIS Building | 2026-07-12 | 2026-07-17
BSCNARCRB--04 | Internal painting Ceiling For Basement floor - Control Building | 2026-07-10 | 2026-07-21
BSCNCVCRB--10 | Apply Membrane Protection for RC Walls till basement slab for Control Building | 2026-07-10 | 2026-07-14
BSCNARCRB--02 | Plastering for Internal Walls For Basement floor - Control Building | 2026-07-10 | 2026-07-21
BSPRELGENG204 | FAT - 220 KV GIS & GIB | 2026-07-10 | 2026-07-25
BSPRELGENCB04 | FAT - Capacitor Banks | 2026-07-10 | 2026-07-23
BSPRELGENG104 | FAT - 66 KV GIS & GIB | 2026-07-10 | 2026-07-25
BSPRCVGENGR08 | Manufacturing - Outdoor steel Steel Structure (SA-DS-CT) | 2026-07-10 | 2026-10-17
BSPRMPGENGR11 | Manufacturing - WIRING DEVICES | 2026-07-10 | 2026-08-08
BSPRELGENOH02 | PO Issuance - OH Conductors | 2026-07-10 | 2026-07-16
BSCNCVOP4--07 | RC Slab [OP - TRF.40] | 2026-07-10 | 2026-07-14
BSCNCVTR4--07 | wall opening - 2*40 MVA Transformers | 2026-07-09 | 2026-07-13
BSENMPGENGR26 | Material approval - wiring devices | 2026-07-09 | 2026-07-24
BSPRELGENAD715 | PO Issuance - Building service panel | 2026-07-08 | 2026-08-06
BSCNCVTRN--85 | Concrete Pouring for Trenches Covers - Trenches - 66 KV GIS to CB | 2026-07-08 | 2026-07-20
BSCNCVOP7--06 | RC Walls [OP - TRF.175] | 2026-07-08 | 2026-07-12
BSCNCVGI1--22 | Columns 3rd Cast - 66 KV GIS Building | 2026-07-08 | 2026-07-16
A1570 | GUARD ROOM ARCHITECTURAL DRAWINGS DETAILS AND SCHEDULES - Drawing Submittal | 2026-07-07 | 2026-07-10
A1560 | GUARD ROOM ARCHITECTURAL DRAWINGS ELEVATION - Drawing Submittal | 2026-07-07 | 2026-07-10
A1550 | GUARD ROOM ARCHITECTURAL DRAWINGS SECTIONS - Drawing Submittal | 2026-07-07 | 2026-07-10
A1540 | GUARD ROOM ARCHITECTURAL DRAWINGS PLANS - Drawing Submittal | 2026-07-07 | 2026-07-10
BSENELGENGR28 | SUBSTATION LIGHTNING CALCULATIONS - Submittal | 2026-07-07 | 2026-07-15
BSPRELGENSE07 | FAT - Cable Sealing End "HV" | 2026-07-07 | 2026-07-14
BSPRELGENES16 | Manufacturing - Earthing Risers Material | 2026-07-07 | 2026-09-04
BSPRELGENTI04 | PO Issuance - Tension Insulators 66 KV | 2026-07-06 | 2026-08-05
BSPRELGENTI03 | PO Issuance - Tension Insulators 220 KV | 2026-07-06 | 2026-08-05
BSCNARCRB--01 | Embedding Electric Sleeves Inside Walls For Basement floor - Control Building | 2026-07-06 | 2026-07-09
BSPRELGENOH08 | Delivery to Site - OH Clamps | 2026-07-06 | 2026-07-12
BSPRELGENMV22 | Delivery to Site - MV Cables Cleats | 2026-07-06 | 2026-07-12
BSPRCVGENGR03 | Manufacturing - Gantry Steel Structure | 2026-07-06 | 2026-09-20
BSPRELGENES18 | Manufacturing - Secondary Earthing Material | 2026-07-06 | 2026-09-03
BSPRELGENES17 | Manufacturing - Earthing Risers Cables | 2026-07-06 | 2026-09-03
BSPRELGENES15 | Manufacturing - Secondary Earthing Cables | 2026-07-06 | 2026-09-03
BSPRELGENOH01 | Purchasing Request - OH Conductors | 2026-07-06 | 2026-07-09
BSCNCVOP4--06 | RC Walls [OP - TRF.40] | 2026-07-06 | 2026-07-09
BSPRMPGENLF18 | Manufacturing - LIGHTING FIXTURES Outdoor | 2026-07-05 | 2026-07-24
BSCNCVTR7--09 | RC Firewalls 2nd Cast - 2*175 MVA Transformers | 2026-07-05 | 2026-07-14
BSCNMPTR7--04 | Oil Drainage System Works in Transformers Foundation ( Manholes & Pipes to oil pits ) - 2*175 MVA Transformers | 2026-07-05 | 2026-07-15
BSPRELGENDS13 | Shipping - Disconnector Switches | 2026-07-04 | 2026-08-17
BSPRELGENLT05 | Shipping - Wave Trap "Line Trap" | 2026-07-04 | 2026-08-17
BSPRELGENVT15 | Shipping - Voltage Transformer (CVT,VT) | 2026-07-04 | 2026-08-17
BSPRELGENCT13 | Shipping - Current Transformers | 2026-07-04 | 2026-08-17
BSPRELGENLV07 | Delivery to Site - LV/ Control Cables TERMINATIONS & ACCESSORIES | 2026-07-04 | 2026-07-10
BSPRELGENLV11 | Delivery to Site - LV CABLES | 2026-07-04 | 2026-07-10
BSPRELGENLV13 | Delivery to Site - Control Cables | 2026-07-04 | 2026-07-10
BSPRMPGENLF08 | Delivery to Site - LIGHTING FIXTURES Indoor | 2026-07-04 | 2026-07-10
BSCNCVTRN--07 | Concrete Pouring for Trenches Covers - Trenches - Gantry yard 220 KV to 220 KV GIS | 2026-07-03 | 2026-07-14
BSPRELGENTI02 | Purchasing Request - Tension Insulators 66 KV | 2026-07-02 | 2026-07-06
BSPRELGENTI01 | Purchasing Request - Tension Insulators 220 KV | 2026-07-02 | 2026-07-06
BSCNCVGI2--21 | Columns 3rd Cast - 220 KV GIS Building | 2026-07-02 | 2026-07-10
BSPRELGENAD655 | Purchasing Request - Building service panel | 2026-07-01 | 2026-07-07
A4560 | GUARD TOWER STRUCTURAL PLANS & SECTIONS - Drawing Approval | 2026-07-01 | 2026-07-16
A4550 | GUARD TOWER STRUCTURAL CALCULATIONS - Approval | 2026-07-01 | 2026-07-16
BSCNCVOP7--05 | RC Foundations [OP - TRF.175] | 2026-07-01 | 2026-07-07
BSCNCVOP4--05 | RC Foundations [OP - TRF.40] | 2026-07-01 | 2026-07-05
BSCNCVGI1--21 | Bracing Beams 2nd Cast at upper level & Corbel - 66 KV GIS Building | 2026-07-01 | 2026-07-07
A4320 | BOUNDARY WALL STRUCTURAL DESIGN CALCULATIONS - Approval | 2026-06-30 | 2026-07-15
A4310 | BOUNDARY WALL STRUCTURAL LAYOUT AND DETAILS - Drawing Approval | 2026-06-30 | 2026-07-15
BSPRELGENT704 | FAT - Three phase transformer 175 MVA with all accessories. | 2026-06-30 | 2026-07-13
BSPRELGENCA02 | PO Issuance - Cable trays & Accessories (Raceway) Patch 01 | 2026-06-30 | 2026-07-19
BSCNCVTRN--84 | Backfilling Works - 66 KV GIS to CB | 2026-06-30 | 2026-07-07
BSPRMEGENHC16 | Delivery to Site - Air Conditioner & Air Curtain | 2026-06-29 | 2026-07-10
BSCNCVOP7--03 | Negative shuttering - Masonry Works for Foundation [OP - TRF.175] | 2026-06-29 | 2026-06-30
BSPRMPGENGR10 | PO Issuance - WIRING DEVICES | 2026-06-26 | 2026-07-09
BSPRELGENLV10 | FAT - LV CABLES | 2026-06-25 | 2026-07-03
BSPRELGENLV12 | FAT - Control Cables | 2026-06-25 | 2026-07-03
BSCNCVOP7--04 | PC Foundation [OP - TRF.175] | 2026-06-25 | 2026-06-28
BSCNCVOP4--10 | Apply Membrane Protection [OP - TRF.40] | 2026-06-25 | 2026-06-30
A6190 | AUX ROOM ARCHITECTURAL DRAWINGS DETAILS AND SCHEDULES - Drawing Approval | 2026-06-24 | 2026-07-10
A6180 | AUX ROOM ARCHITECTURAL DRAWINGS ELEVATION - Drawing Approval | 2026-06-24 | 2026-07-10
A6170 | AUX ROOM ARCHITECTURAL DRAWINGS SECTIONS - Drawing Approval | 2026-06-24 | 2026-07-10
A6160 | AUX ROOM ARCHITECTURAL DRAWINGS PLANS - Drawing Approval | 2026-06-24 | 2026-07-10
BSPRELGENDS10 | FAT - Disconnector Switches | 2026-06-24 | 2026-07-03
BSPRELGENLT04 | FAT - Wave Trap "Line Trap" | 2026-06-24 | 2026-07-03
BSPRELGENVT12 | FAT - Voltage Transformer (CVT,VT) | 2026-06-24 | 2026-07-03
BSPRELGENCT10 | FAT - Current Transformers | 2026-06-24 | 2026-07-03
BSCNCVGI2--20 | Bracing Beams at 2nd Cast - 220 KV GIS Building | 2026-06-24 | 2026-07-01
BSCNCVOP4--09 | Apply Membrane Waterproofing Sheets for RC [OP - TRF.40] | 2026-06-24 | 2026-06-24
BSCNCVTRN--06 | Backfilling Works - Gantry yard 220 KV to 220 KV GIS | 2026-06-23 | 2026-07-02
BSCNMPTR7--01 | Embedded Conduits for Lighting Fixtures - 2*175 MVA Transformers | 2026-06-23 | 2026-07-05
BSCNCVTR7--08 | RC Firewalls 1st Cast - 2*175 MVA Transformers | 2026-06-23 | 2026-07-03
BSCNCVOP4--04 | Negative shuttering - Masonry Works for Foundation [OP - TRF.40] | 2026-06-23 | 2026-06-23
BSPRELGENMV36 | Manufacturing - MV Cable Termination | 2026-06-22 | 2026-11-09
A6150 | AUX ROOM ARCHITECTURAL DRAWINGS DETAILS AND SCHEDULES - Drawing Submittal | 2026-06-22 | 2026-06-23
A6140 | AUX ROOM ARCHITECTURAL DRAWINGS ELEVATION - Drawing Submittal | 2026-06-22 | 2026-06-23
A6130 | AUX ROOM ARCHITECTURAL DRAWINGS SECTIONS - Drawing Submittal | 2026-06-22 | 2026-06-23
A6120 | AUX ROOM ARCHITECTURAL DRAWINGS PLANS - Drawing Submittal | 2026-06-22 | 2026-06-23
A3850 | BOUNDARY WALL ARCHITECTURAL ELEVATION - Drawing Approval | 2026-06-22 | 2026-07-08
A3840 | BOUNDARY WALL ARCHITECTURAL SCHEDULES & TYP. DETAILS - Drawing Approval | 2026-06-22 | 2026-07-08
A3830 | BOUNDARY WALL ARCHITECTURAL PLAN - Drawing Approval | 2026-06-22 | 2026-07-08
A1900 | BOUNDARY WALL STRUCTURAL DESIGN CALCULATIONS - Submittal | 2026-06-22 | 2026-06-29
A1890 | BOUNDARY WALL STRUCTURAL LAYOUT AND DETAILS - Drawing Submittal | 2026-06-22 | 2026-06-29
BSPRMPGENGR04 | Delivery to Site - ELECTRICAL WIRES | 2026-06-22 | 2026-06-22
BSPRMPGENGR09 | Purchasing Request - WIRING DEVICES | 2026-06-22 | 2026-06-25
BSENMPGENGR22 | Material submittal - wiring devices | 2026-06-22 | 2026-07-08
BSCNCVTRN--83 | Bitumen Isolation - 66 KV GIS to CB | 2026-06-22 | 2026-06-29
BSCNCVOP4--03 | PC Foundation [OP - TRF.40] | 2026-06-22 | 2026-06-22
BSCNCVCRB--88 | Masonry Works For For Basement floor - Control Building | 2026-06-21 | 2026-07-05
BSCNCVCRB--09 | Apply Membrane sheets for RC Walls till basement slab for Control Building | 2026-06-21 | 2026-06-28
BSCNCVCRB--16 | Concrete Works for Basement Slab- Basement Slab For Control Building | 2026-06-21 | 2026-07-09
BSPRMPGENGR03 | Manufacturing - ELECTRICAL WIRES | 2026-06-21 | 2026-06-21
BSCNCVGI1--19 | Columns 2nd Cast - 66 KV GIS Building | 2026-06-21 | 2026-06-30
BSPRCVGENGR07 | PO Issuance - Outdoor steel Steel Structure (SA-DS-CT) | 2026-06-20 | 2026-07-09
A3990 | GUARD TOWER ARCHITECTURAL PLANS & SECTIONS - Drawing Approval | 2026-06-19 | 2026-07-07
A2180 | GUARD TOWER STRUCTURAL PLANS & SECTIONS - Drawing Submittal | 2026-06-19 | 2026-06-30
A2170 | GUARD TOWER STRUCTURAL CALCULATIONS - Submittal | 2026-06-19 | 2026-06-30
BSCNCVTR4--06 | RC works for Basin Walls, Piers & Firewalls till Top level of basin walls & Embedded Plates- 2*40 MVA Transformers | 2026-06-19 | 2026-07-08
BSCNCVTR7--07 | wall opening - 2*175 MVA Transformers | 2026-06-18 | 2026-06-22
BSPRMEGENFS35 | PO Issuance - Fire hydrant system | 2026-06-17 | 2026-07-16
BSPRCVGENGR02 | PO Issuance - Gantry Steel Structure | 2026-06-17 | 2026-07-05
BSPRMPGENGR02 | PO Issuance - ELECTRICAL WIRES | 2026-06-17 | 2026-06-20
BSCNCVTRN--555 | Backfilling Works - Trenches - Road Crossing - 175MVA Transformers to CB | 2026-06-16 | 2026-06-21
BSCNCVTRN--05 | Bitumen Isolation - Gantry yard 220 KV to 220 KV GIS | 2026-06-16 | 2026-06-22
BSPRCVGENGR06 | Purchasing Request - Outdoor steel Steel Structure (SA-DS-CT) | 2026-06-16 | 2026-06-19
A1580 | GUARD TOWER ARCHITECTURAL PLANS & SECTIONS - Drawing Submittal | 2026-06-15 | 2026-06-18
A1440 | BOUNDARY WALL ARCHITECTURAL ELEVATION - Drawing Submittal | 2026-06-15 | 2026-06-19
A1430 | BOUNDARY WALL ARCHITECTURAL SCHEDULES & TYP. DETAILS - Drawing Submittal | 2026-06-15 | 2026-06-19
A1420 | BOUNDARY WALL ARCHITECTURAL PLAN - Drawing Submittal | 2026-06-15 | 2026-06-19
BSCNCVGI2--19 | Columns 2nd Cast - 220 KV GIS Building | 2026-06-15 | 2026-06-23
BSPRMPGENLF07 | Manufacturing - LIGHTING FIXTURES Indoor | 2026-06-14 | 2026-07-03
BSCNCVGI1--18 | Bracing Beams 1st Cast - 66 KV GIS Building | 2026-06-14 | 2026-06-19
BSPRMEGENHC11 | Manufacturing - Fans & Ventilation System | 2026-06-13 | 2026-07-12
BSPRMEGENFS29 | Purchasing Request - Fire hydrant system | 2026-06-13 | 2026-06-16
BSPRMPGENGR01 | Purchasing Request - ELECTRICAL WIRES | 2026-06-13 | 2026-06-16
BSCNCVTRN--545 | Bitumen Isolation - Trenches - Road Crossing - 175MVA Transformers to CB | 2026-06-10 | 2026-06-15
BSPRMEGENFS36 | PO Issuance - Fire Extinguishers | 2026-06-10 | 2026-07-24
BSPRELGENCA01 | Purchasing Request - Cable trays & Accessories (Raceway) | 2026-06-10 | 2026-06-29
BSCNCVTRN--82 | RC Walls & Raceway - Trenches - 66 KV GIS to CB | 2026-06-10 | 2026-06-21
BSPRCVGENGR48 | Manufacturing - LCC Support | 2026-06-08 | 2026-08-23
BSPRCVGENGR13 | Manufacturing - Panels Frame | 2026-06-08 | 2026-08-23
BSCNCVGI2--18 | Bracing Beams 1st Cast - 220 KV GIS Building | 2026-06-08 | 2026-06-14
BSCNCVCRB--07 | Column till Basement Slab for Control Building | 2026-06-07 | 2026-06-19
BSCNCVWAT--14 | Backfilling Works - 66/11 RC Tank | 2026-06-07 | 2026-06-07
BSPRELGENOH07 | Manufacturing - OH Clamps | 2026-06-06 | 2026-07-05
BSPRELGENMV17 | Manufacturing - MV Cables Cleats | 2026-06-06 | 2026-07-05
BSPRMEGENFS32 | Purchasing Request - Fire Extinguishers | 2026-06-06 | 2026-06-09
BSCNCVTRN--13 | Backfilling Works - Trenches - Road Crossing - Gantry yard 220 KV to 220 KV GIS | 2026-06-05 | 2026-06-10
BSPRMPGENLF8 | PO Issuance - LIGHTING FIXTURES Outdoor | 2026-06-04 | 2026-06-13
BSCNCVTRN--04 | RC Walls & Raceway - Trenches - Gantry yard 220 KV to 220 KV GIS | 2026-06-04 | 2026-06-15
BSPRMPGENLF06 | PO Issuance - LIGHTING FIXTURES Indoor | 2026-06-04 | 2026-06-13
BSCNCVGI1--17 | Columns 1st Cast - 66 KV GIS Building | 2026-06-04 | 2026-06-12
BSPRMEGENHC10 | PO Issuance - Air Conditioner & Air Curtain | 2026-06-03 | 2026-06-22
BSCNCVTRN--535 | RC Raft & Pipes positioning - Trenchs - Road Crossing - 175MVA Transformers to CB | 2026-06-02 | 2026-06-09
BSPRELGENES10 | PO Issuance - Earthing Risers Material | 2026-06-02 | 2026-06-06
BSCNCVTR7--06 | RC works for Basin Walls, Piers & Firewalls till Top level of basin walls & Embedded Plates- 2*175 MVA Transformers | 2026-06-02 | 2026-06-17
BSPRELGENES12 | PO Issuance - Secondary Earthing Material | 2026-06-01 | 2026-06-05
BSPRELGENES11 | PO Issuance - Earthing Risers Cables | 2026-06-01 | 2026-06-05
BSPRELGENES09 | PO Issuance - Secondary Earthing Cables | 2026-06-01 | 2026-06-05
BSCNCVWAT--13 | Bitumen isolation for Foundation - 66/11 RC Tank | 2026-06-01 | 2026-06-05
BSCNCVWAT--12 | Installation of Steel Tank - 66/11 RC Tank | 2026-06-01 | 2026-06-17
BSCNCVOP4--01 | Excavate to the Foundation Level [OP - TRF.40] | 2026-06-01 | 2026-06-21
BSPRELGENMV16 | Manufacturing - MV Cables | 2026-05-31 | 2026-08-19
BSPRELGENHV03 | Manufacturing - HV Cables | 2026-05-31 | 2026-08-19
BSPRELGENMV18 | Manufacturing - Cable Steel Supports | 2026-05-31 | 2026-08-19
BSCNCVCRB--05 | Insulation of Foundations For Control Building | 2026-05-31 | 2026-06-03
BSCNCVCRB--08 | RC Walls till Basement Slab for Control Building | 2026-05-31 | 2026-06-19
BSCNCVTRN--12 | Bitumen Isolation - Duct banks - Road Crossing - Gantry yard 220 KV to 220 KV GIS | 2026-05-31 | 2026-06-04
BSCNCVWAT--11 | RC Pedestals and anchored bolt installation - 66/11 RC Tank | 2026-05-31 | 2026-05-31
BSPRMEGENHC13 | Manufacturing - Air Conditioner & Air Curtain | 2026-05-30 | 2026-06-28
BSPRELGENAD20 | Manufacturing - AC & DC Panels | 2026-05-30 | 2026-10-26
BSPRMEGENHC07 | Purchasing Request - Air Conditioner & Air Curtain | 2026-05-30 | 2026-06-02
BSENMEGENCA2 | Material approval- Outdoor Steel Structure | 2026-05-29 | 2026-06-15
BSENMEGENCA1 | Material approval - Gantry Steel | 2026-05-29 | 2026-06-15
BSCNCVGI2--07 | Isolation for Foundation - 220 KV GIS Building | 2026-05-29 | 2026-06-02
BSPRCVGENGR01 | Purchasing Request - Gantry Steel Structure | 2026-05-29 | 2026-06-16
BSCNCVTRN--81 | RC Raft - Trenches - 66 KV GIS to CB | 2026-05-29 | 2026-06-09
BSCNCVGI2--17 | Columns 1st Cast - 220 KV GIS Building | 2026-05-29 | 2026-06-07
BSCNCVTR4--05 | RC Raft for Transformers & Firewalls - 2*40 MVA Transformers | 2026-05-29 | 2026-06-18
BSPRMPGENLF05 | Purchasing Request - LIGHTING FIXTURES Indoor | 2026-05-28 | 2026-06-03
BSENMEGENFS07 | Material approval - Fire hydrant system | 2026-05-28 | 2026-06-12
BSENMPGENGR24 | Material approval - Lighting fixtures & electrical wires | 2026-05-28 | 2026-06-12
BSCNCVTRN--525 | PC Raft - Trenches - Road Crossing - 175MVA Transformers to CB | 2026-05-27 | 2026-06-01
BSENELGENPB02 | BUILDING SERVICE PANELS BASE DESIGN AND WIRING SCHEMATICS | 2026-05-26 | 2026-06-08
BSPRMEGENFS37 | Manufacturing - 40 MVA Transformers fire fighghting system | 2026-05-26 | 2026-08-23
BSPRMEGENFS38 | Manufacturing - 175 MVA Transformers fire fighghting system | 2026-05-26 | 2026-08-23
BSCNCVWAT--10 | RC Foundation Works - 66/11 RC Tank | 2026-05-26 | 2026-05-29
BSENELGENCA02 | Material approval - Cable trays & Accessories | 2026-05-25 | 2026-06-09
BSCNCVGI1--05 | Bracing Beams at lower level - 66 KV GIS Building | 2026-05-25 | 2026-06-03
BSCNCVPUR--02 | Soil Replacement & Compaction - Fire Hydrant | 2026-05-25 | 2026-05-28
BSCNCVWAT--09 | PC Foundation Works - 66/11 RC Tank | 2026-05-25 | 2026-05-25
BSCNCVTR4--04 | 2 layers of Bituminous membrane & Screed layer - 2*40 MVA Transformers | 2026-05-25 | 2026-05-28
BSCNCVGI1--07 | Isolation for Foundation - 66 KV GIS Building | 2026-05-25 | 2026-05-26
BSCNCVTRN--03 | RC Raft - Trenches - Gantry yard 220 KV to 220 KV GIS | 2026-05-24 | 2026-06-03
BSPRMEGENHC09 | PO Issuance - Fans & Ventilation System | 2026-05-24 | 2026-06-12
BSPRELGENMV33 | PO Issuance - MV Cable Termination | 2026-05-23 | 2026-06-22
A4930 | OUTDOOR EQUIPMENT FOUNDATION DESIGN CALCULATIONS - Approval | 2026-05-21 | 2026-06-09
A4920 | Outdoor Equipment Foundation Layout And Details - Drawing Approval | 2026-05-21 | 2026-06-09
A5110 | OUTDOOR CCTV SYSTEM PLAN - Drawing Approval | 2026-05-21 | 2026-06-08
BSCNCVTRN--515 | Excavation Works - Trenches - Road Crossing - 175MVA Transformers to CB | 2026-05-21 | 2026-05-26
BSCNCVTRN--11 | RC Raft & Pipes positioning - Duct banks - Road Crossing - Gantry yard 220 KV to 220 KV GIS | 2026-05-21 | 2026-05-29
BSCNCVTRN--80 | PC Raft - Trenches - 66 KV GIS to CB | 2026-05-21 | 2026-05-28
BSPRMEGENHC06 | Purchasing Request - Fans & Ventilation System | 2026-05-20 | 2026-05-23
BSENMEGENFS08 | Material approval - FIRE EXTINGUISHERS | 2026-05-20 | 2026-06-05
BSPRELGENMV28 | Purchasing Request - MV Cable Termination | 2026-05-19 | 2026-05-23
BSCNCVWAT--01 | Excavation Works - 220/66 RC Tank | 2026-05-19 | 2026-06-02
BSCNCVFFR--01 | Excavation Works - 220/66 KV Firefighting Room | 2026-05-19 | 2026-06-03
BSENELGI1G107 | 66KV BUILDING EQUIPMENT EARTHING LAYOUT & DETAILS - Drawing Approval | 2026-05-18 | 2026-06-03
BSCNCVTR4--03 | Negative shattering - Masonry works for RC Raft - 2*40 MVA Transformers | 2026-05-18 | 2026-05-24
BSCNCVGI2--05 | Bracing Beams at lower level - 220 KV GIS Building | 2026-05-17 | 2026-05-28
BSPRELGENES06 | Purchasing Request - Secondary Earthing Material | 2026-05-16 | 2026-05-21
BSPRELGENES05 | Purchasing Request - Earthing Risers Cables | 2026-05-16 | 2026-05-21
BSPRELGENES04 | Purchasing Request - Earthing Risers Material | 2026-05-16 | 2026-05-21
BSPRELGENES03 | Purchasing Request - Secondary Earthing Cables | 2026-05-16 | 2026-05-21
BSENELGENAD12 | AC AND DC SYSTEM PANEL BOARDS WIRING SCHEMATICS MATERIAL APPROVAL | 2026-05-15 | 2026-05-29
BSCNCVTRN--10 | PC Raft - Duct banks - Road Crossing - Gantry yard 220 KV to 220 KV GIS | 2026-05-15 | 2026-05-20
BSCNCVTRN--02 | PC Raft - Trenches - Gantry yard 220 KV to 220 KV GIS | 2026-05-15 | 2026-05-21
BSENELGENGR16 | GROUNDING SYSTEM RISERS - Drawing Approval | 2026-05-14 | 2026-06-01
BSENMEGENHC04 | Material approval - Air Conditioner & Air Curtain | 2026-05-13 | 2026-05-29
BSCNCVGI1--04 | Columns Neck- 66 KV GIS Building | 2026-05-13 | 2026-05-24
A1010 | OUTDOOR EQUIPMENT FOUNDATION DESIGN CALCULATIONS - Submittal | 2026-05-12 | 2026-05-21
A1000 | Outdoor Equipment Foundation Layout And Details - Drawing Submittal | 2026-05-12 | 2026-05-21
BSCNCVTRN--565 | Excavation Works - Trenches - 175MVA Transformers to CB | 2026-05-12 | 2026-05-20
BSENELGI2G210 | 220 KV Gantry Area Equipment Layout And Sections - Drawing Approval | 2026-05-12 | 2026-05-28
BSENELGI1G102 | 66KV BUILDING EQUIPMENT EARTHING LAYOUT & DETAILS - Drawing Submittal | 2026-05-12 | 2026-05-15
BSCNCVTRN--79 | Excavation Works - Trenches - 66 KV GIS to CB | 2026-05-12 | 2026-05-20
BSCNCVPUR--01 | Excavation Works - Fire Hydrant | 2026-05-12 | 2026-05-24
BSENELGENPB01 | BUILDING SERVICE PANELS BASE DESIGN AND WIRING SCHEMATICS | 2026-05-11 | 2026-05-25
BSENMEGENFS03 | Material submittal - Fire hydrant system | 2026-05-11 | 2026-05-27
BSENMPGENGR20 | Material submittal - Lighting fixtures & electrical wires | 2026-05-11 | 2026-05-27
BSCNCVWAT--08 | Excavation Works - 66/11 RC Tank | 2026-05-10 | 2026-05-24
BSCNCVFFR--13 | Excavation Works - 66/11 kV Firefighting Room | 2026-05-10 | 2026-05-20
BSCNCVTR4--02 | PC Raft & Polyethylene sheet laying - 2*40 MVA Transformers | 2026-05-10 | 2026-05-17
BSPRCVGENGR38 | PO Issuance - LCC Support | 2026-05-09 | 2026-06-07
BSPRCVGENGR12 | PO Issuance - Panels Frame | 2026-05-09 | 2026-06-07
BSPRELGENOH06 | PO Issuance - OH Clamps | 2026-05-09 | 2026-05-15
BSPRELGENMV11 | PO Issuance - MV Cables Cleats | 2026-05-09 | 2026-05-15
BSCNCVTR7--05 | RC Raft for Transformers & Firewalls - 2*175 MVA Transformers | 2026-05-08 | 2026-06-01
BSPRELGENAD195 | Manufacturing - 48V Battery bank | 2026-05-07 | 2026-11-02
BSPRELGENAD185 | Manufacturing - 220V DC battery bank | 2026-05-07 | 2026-11-02
BSENELGI2G205 | 220kV GANTRY EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Submittal | 2026-05-06 | 2026-05-11
BSENELGENOH03 | Material approval - OH Conductors | 2026-05-06 | 2026-05-21
BSENELGENCA01 | Material submittal - Cable trays & Accessories | 2026-05-06 | 2026-05-21
A5100 | OUTDOOR LIGHT CURRENT SYSTEM LAYOUT DATA & TELEPHONE SYSTEM PLAN - Drawing Approval | 2026-05-05 | 2026-05-20
A4910 | SHED ROOF FOR VEHICLES CALCULATION REPORT - Approval | 2026-05-05 | 2026-05-20
A4900 | SHED ROOF FOR VEHICLES STRUCTURAL SECTIONS & DETAILS - Drawing Approval | 2026-05-05 | 2026-05-20
A4890 | SHED ROOF FOR VEHICLES STRUCTURAL DRAWINGS FOUNDATION PLAN - Drawing Approval | 2026-05-05 | 2026-05-20
A4880 | SHED ROOF FOR CAPACITOR BANK STEEL STRUCTURAL CALCULATION - Approval | 2026-05-05 | 2026-05-20
A4870 | SHED ROOF FOR CAPACITOR BANK STEEL STRUCTURAL CALCULATION - Approval | 2026-05-05 | 2026-05-20
BSCNCVGI2--04 | Columns Neck- 220 KV GIS Building | 2026-05-05 | 2026-05-15
BSENELGENGR08 | GROUNDING SYSTEM RISERS - Drawing Submittal | 2026-05-05 | 2026-05-13
BSENMEGENHC03 | Material approval - Fans & Ventilation System | 2026-05-04 | 2026-05-19
BSENMEGENFS04 | Material submittal - FIRE EXTINGUISHERS | 2026-05-04 | 2026-05-19
BSCNCVTR7--04 | 2 layers of Bituminous membrane & Protection layer - 2*175 MVA Transformers | 2026-05-04 | 2026-05-07
BSPRELGENNR03 | Manufacturing - Single phase Earthing resistor,20 Ohm | 2026-05-03 | 2026-07-21
BSCNCVOP7--01 | Excavate to the Foundation Level [OP - TRF.175] | 2026-05-03 | 2026-05-31
BSENELGENTK02 | Material approval - MV termination | 2026-04-30 | 2026-05-19
BSCNCVCRB--04 | RC Foundation Works for Control Building | 2026-04-30 | 2026-05-29
BSENELGENAD11 | AC AND DC SYSTEM PANEL BOARDS WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-04-30 | 2026-05-14
BSPRELGENAD515 | Manufacturing - 48V Battery Charger | 2026-04-28 | 2026-08-10
BSPRELGENAD505 | Manufacturing - 220V DC battery Charger | 2026-04-28 | 2026-08-10
A4860 | SHED ROOF FOR CAPACITOR BANK CALCULATION REPORT - Approval | 2026-04-28 | 2026-05-14
A4850 | SHED ROOF FOR CAPACITOR BANK STRUCTURAL SECTIONS & DETAILS - Drawing Approval | 2026-04-28 | 2026-05-14
A4840 | SHED ROOF FOR CAPACITOR BANK STRUCTURAL DRAWINGS FOUNDATION PLAN - Drawing Approval | 2026-04-28 | 2026-05-14
A4640 | OUTDOOR DUCTS AND TRENCHES DESIGN CALCULATIONS - Approval | 2026-04-28 | 2026-05-14
A4630 | OUTDOOR DUCTS AND TRENCHES STRUCTURAL DRAWINGS - Approval | 2026-04-28 | 2026-05-14
A4600 | 40 MVA OIL PIT STRUCTURAL DESIGN CALCULATIONS - Approval | 2026-04-28 | 2026-05-14
A4570 | 40MVA OIL PIT STRUCTURAL LAYOUT & DETAILS - Drawing Approval | 2026-04-28 | 2026-05-14
A2530 | SHED ROOF FOR VEHICLES CALCULATION REPORT - Submittal | 2026-04-28 | 2026-05-04
A2520 | SHED ROOF FOR VEHICLES STRUCTURAL SECTIONS & DETAILS - Drawing Submittal | 2026-04-28 | 2026-05-04
A2510 | SHED ROOF FOR VEHICLES STRUCTURAL DRAWINGS FOUNDATION PLAN - Drawing Submittal | 2026-04-28 | 2026-05-04
A5680 | FIRE HYDRANT ROOM HVAC SYSTEM CALCULATIONS - Approval | 2026-04-27 | 2026-05-13
A5670 | FIRE HYDRANT ROOM HVAC SYSTEM LAYOUT & DETAILS - Drawing Approval | 2026-04-27 | 2026-05-13
BSCNCVTR7--03 | Negative shattering - Masonry works for RC Raft - 2*175 MVA Transformers | 2026-04-27 | 2026-05-03
BSPRMEGENFS34 | PO Issuance - 175 MVA Transformers fire fighghting system | 2026-04-26 | 2026-05-25
BSPRMEGENFS33 | PO Issuance - 40 MVA Transformers fire fighghting system | 2026-04-26 | 2026-05-25
BSPRELGENLV08 | Manufacturing - LV CABLES | 2026-04-26 | 2026-06-24
BSPRELGENLV09 | Manufacturing - Control Cables | 2026-04-26 | 2026-06-24
BSCNCVGI1--03 | RC Footings Works - 66 KV GIS Building | 2026-04-26 | 2026-05-12
BSPRCVGENGR28 | Purchasing Request - LCC Support | 2026-04-25 | 2026-05-08
BSPRCVGENGR11 | Purchasing Request - Panels Frame | 2026-04-25 | 2026-05-08
BSPRELGENMV07 | PO Issuance - MV Cables | 2026-04-24 | 2026-05-01
BSPRELGENHV02 | PO Issuance - HV Cables | 2026-04-24 | 2026-05-01
BSPRELGENMV12 | PO Issuance - Cable Steel Supports | 2026-04-24 | 2026-05-01
BSCNCVCRB--03 | Apply Membrane sheets for PC Footing under RC foundation including screed - Control Building | 2026-04-24 | 2026-04-29
BSENELGENLS02 | Material approval - Lightning/shielding System | 2026-04-24 | 2026-05-12
BSENMEGENHC02 | Material submittal - Air Conditioner & Air Curtain | 2026-04-24 | 2026-05-12
A5700 | SUBSTATION FIRE HYDRANT DESIGN CALCULATION - Approval | 2026-04-23 | 2026-05-11
A5690 | SUBSTATION FIRE HYDRANT PLAN & SECTION - Drawing Approval | 2026-04-23 | 2026-05-11
A4590 | 175MVA OIL PIT STRUCTURAL DESIGN CALCULATIONS - Approval | 2026-04-23 | 2026-05-11
BSPRELGENAD455 | PO Issuance - 48V Battery Charger | 2026-04-22 | 2026-04-27
BSPRELGENAD445 | PO Issuance - 220V DC battery Charger | 2026-04-22 | 2026-04-27
A5890 | ROADS TYPICAL CROSS SECTIONS. - Drawing Approval | 2026-04-22 | 2026-05-08
A5880 | ROADS SETTING PLAN & TABLES. - Drawing Approval | 2026-04-22 | 2026-05-08
A5870 | ROADS PROFILES. - Drawing Approval | 2026-04-22 | 2026-05-08
A5860 | ROADS SIGNS & MARKING LAYOUT & DETAILS. - Drawing Approval | 2026-04-22 | 2026-05-08
A5850 | ROADS GRADING LAYOUT. - Drawing Approval | 2026-04-22 | 2026-05-08
A5840 | ROADS GENERAL LAYOUT. - Drawing Approval | 2026-04-22 | 2026-05-08
A5830 | ROADS STRUCTURAL DESIGN CALCULATIONS. - Approval | 2026-04-22 | 2026-05-08
A5660 | FIRE HYDRANT ROOM MECHANICAL EQUIPMENT ARRANGEMENT - Drawing Approval | 2026-04-22 | 2026-05-08
A5460 | FIRE HYDRANT ROOM PANEL SCHEDULES - Drawing Approval | 2026-04-22 | 2026-05-08
A5450 | FIRE HYDRANT ROOM POWER SYSTEM PLAN - Drawing Approval | 2026-04-22 | 2026-05-08
A5440 | FIRE HYDRANT ROOM NORMAL & EMERGENCY LIGHTING SYSTEM FLOOR PLAN - Drawing Approval | 2026-04-22 | 2026-05-08
A5430 | FIRE HYDRANT ROOM LIGHTING LUX CALCULATION - Approval | 2026-04-22 | 2026-05-08
A5120 | 220KV GIS BUILDING LIGHTING LUX CALCULATION - Approval | 2026-04-22 | 2026-05-08
A5080 | FIRE HYDRANT ROOM FIRE ALARM SYSTEM PLAN AND DETAILS - Drawing Approval | 2026-04-22 | 2026-05-08
A4470 | FIRE HYDRANT ROOM STRUCTURAL CALCULATION - Approval | 2026-04-22 | 2026-05-08
A4460 | FIRE HYDRANT ROOM STRUCTURAL PLANS & SECTIONS - Drawing Approval | 2026-04-22 | 2026-05-08
A2480 | SHED ROOF FOR CAPACITOR BANK CALCULATION REPORT - Submittal | 2026-04-22 | 2026-04-27
A2470 | SHED ROOF FOR CAPACITOR BANK STRUCTURAL SECTIONS & DETAILS - Drawing Submittal | 2026-04-22 | 2026-04-27
A2460 | SHED ROOF FOR CAPACITOR BANK STRUCTURAL DRAWINGS FOUNDATION PLAN - Drawing Submittal | 2026-04-22 | 2026-04-27
A2220 | 40 MVA OIL PIT STRUCTURAL DESIGN CALCULATIONS - Submittal | 2026-04-22 | 2026-04-27
A2190 | 40MVA OIL PIT STRUCTURAL LAYOUT & DETAILS - Drawing Submittal | 2026-04-22 | 2026-04-27
BSPRMEGENFS31 | Purchasing Request - 40 MVA Transformers fire fighghting system | 2026-04-22 | 2026-04-25
BSENMPGI2GR12 | 220KV GIS BUILDING PANEL SCHEDULES - Drawing Approval | 2026-04-22 | 2026-05-08
BSENMPGI2GR09 | 220KV GIS BUILDING POWER SOCKET SYSTEM LAYOUT - Drawing Approval | 2026-04-22 | 2026-05-08
BSENMPGI2GR11 | 220KV GIS BUILDING LIGHTING SYSTEM LAYOUT - Drawing Approval | 2026-04-22 | 2026-05-08
BSPRMEGENFS30 | Purchasing Request - 175 MVA Transformers fire fighghting system | 2026-04-22 | 2026-04-25
BSPRELGENNR02 | PO Issuance - Single phase Earthing resistor,20 Ohm | 2026-04-21 | 2026-05-02
BSCNCVGN2--01 | Excavation Works - 220 KV Outdoor Equipment & Gantry - Gantry Foundation | 2026-04-21 | 2026-05-05
BSCNCVGN2--10 | Excavation Works - 220 KV Outdoor Equipment & Gantry - Equipment Foundation | 2026-04-21 | 2026-05-12
BSCNCVTR4--01 | Excavation Works - 2*40 MVA Transformers | 2026-04-21 | 2026-05-08
BSCNCVGI1--02 | PC Footings Works - 66 KV GIS Building | 2026-04-21 | 2026-04-24
A4620 | OUTDOOR EQUIPMENT STEEL STRUCTURE SUPPORTS SECTIONS & DETAILS - Drawing Approval | 2026-04-20 | 2026-05-06
A4610 | OUTDOOR EQUIPMENT STEEL STRUCTURE CALCULATION REPORT - Approval | 2026-04-20 | 2026-05-06
BSCNCVTR7--02 | PC Raft & Polyethylene sheet laying - 2*175 MVA Transformers | 2026-04-19 | 2026-04-26
BSPRELGENAD395 | Purchasing Request - 48V Battery Charger | 2026-04-16 | 2026-04-21
BSPRELGENAD385 | Purchasing Request - 220V DC battery Charger | 2026-04-16 | 2026-04-21
BSPRELGENAD135 | PO Issuance - 48V Battery bank | 2026-04-16 | 2026-05-06
BSPRELGENAD125 | PO Issuance - 220V DC battery bank | 2026-04-16 | 2026-05-06
A2260 | OUTDOOR DUCTS AND TRENCHES DESIGN CALCULATIONS - Submittal | 2026-04-16 | 2026-04-27
A2250 | OUTDOOR DUCTS AND TRENCHES STRUCTURAL DRAWINGS - Drawing Submittal | 2026-04-16 | 2026-04-27
A2210 | 175MVA OIL PIT STRUCTURAL DESIGN CALCULATIONS - Submittal | 2026-04-16 | 2026-04-22
BSCNCVTRN--435 | Excavation Works - Trenches - Road Crossing - 175MVA Transformers to CB | 2026-04-16 | 2026-04-26
BSCNCVGI2--03 | RC Footings Works - 220 KV GIS Building | 2026-04-16 | 2026-05-04
BSENMPGENTD03 | DATA&TELEPHONE SYSTEM RISER PLAN - Drawing Approval | 2026-04-16 | 2026-05-05
BSENMPGENSS03 | FIRE ALARM SYSTEM RISER PLAN - Drawing Approval | 2026-04-16 | 2026-05-05
BSPRELGENAD13 | PO Issuance - AC & DC Panels | 2026-04-16 | 2026-04-29
BSENELGENOH01 | Material submittal - OH Conductors | 2026-04-16 | 2026-05-05
BSENELGENGR11 | Overhead Conductor Calculation Report - Approval | 2026-04-16 | 2026-05-05
BSENELGENGR17 | SUBSTATION OVERALL CABLE ROUTING LAYOUT - Drawing Approval | 2026-04-16 | 2026-05-05
BSCNCVTY7--10 | Excavation Works - 2*175 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-04-16 | 2026-05-08
BSCNCVTY7--01 | Excavation Works - 2*175 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-04-16 | 2026-04-23
BSCNCVTY7--19 | Excavation Works - 2*175 MVA Outdoor Equipment & Gantry - Cables Sealing End Foundation | 2026-04-16 | 2026-05-08
A5800 | OVERALL POTABLE WATER SUPPLY NETWORK CALCULATION - Approval | 2026-04-15 | 2026-05-04
A5770 | OUTDOOR POTABLE WATER NETWORK - Drawing Approval | 2026-04-15 | 2026-05-04
A5420 | OUTDOOR POWER SOCKET LAYOUT & GUARD TOWER PLAN - Drawing Approval | 2026-04-15 | 2026-05-04
A5410 | OUTDOOR LIGHTING SYSTEM LAYOUT - Drawing Approval | 2026-04-15 | 2026-05-04
A5400 | OUTDOOR LIGHTING LUX CALCULATION - Approval | 2026-04-15 | 2026-05-04
A5390 | OUTDOOR PANEL SCHEDULE - Drawing Approval | 2026-04-15 | 2026-05-04
A5090 | OUTDOOR LIGHT CURRENT SYSTEM LAYOUT FIRE ALARM SYSTEM PLAN - Drawing Approval | 2026-04-15 | 2026-05-04
A3300 | SUBSTATION FIRE HYDRANT DESIGN CALCULATION - Submittal | 2026-04-15 | 2026-04-22
A3290 | SUBSTATION FIRE HYDRANT PLAN & SECTION - Drawing Submittal | 2026-04-15 | 2026-04-22
A3280 | FIRE HYDRANT ROOM HVAC SYSTEM CALCULATIONS - Submittal | 2026-04-15 | 2026-04-24
A3270 | FIRE HYDRANT ROOM HVAC SYSTEM LAYOUT & DETAILS - Drawing Submittal | 2026-04-15 | 2026-04-24
A3260 | FIRE HYDRANT ROOM MECHANICAL EQUIPMENT ARRANGEMENT - Drawing Submittal | 2026-04-15 | 2026-04-21
A3000 | FIRE HYDRANT ROOM PANEL SCHEDULES - Drawing Submittal | 2026-04-15 | 2026-04-21
A2990 | FIRE HYDRANT ROOM POWER SYSTEM PLAN - Drawing Submittal | 2026-04-15 | 2026-04-21
A2980 | FIRE HYDRANT ROOM NORMAL & EMERGENCY LIGHTING SYSTEM FLOOR PLAN - Drawing Submittal | 2026-04-15 | 2026-04-21
A2970 | FIRE HYDRANT ROOM LIGHTING LUX CALCULATION - Submittal | 2026-04-15 | 2026-04-21
A2660 | FIRE HYDRANT ROOM FIRE ALARM SYSTEM PLAN AND DETAILS - Drawing Submittal | 2026-04-15 | 2026-04-21
A2080 | FIRE HYDRANT ROOM STRUCTURAL CALCULATION - Submittal | 2026-04-15 | 2026-04-21
A2070 | FIRE HYDRANT ROOM STRUCTURAL PLANS & SECTIONS - Drawing Submittal | 2026-04-15 | 2026-04-21
BSPRELGENOH05 | Purchasing Request - OH Clamps | 2026-04-15 | 2026-04-18
BSPRELGENMV05 | Purchasing Request - MV Cables Cleats | 2026-04-15 | 2026-04-18
A5790 | OVERALL FIRE EXTINGUISHER DISTRIBUTION - Drawing Approval | 2026-04-14 | 2026-04-30
A5780 | OUTDOOR SEWAGE NETWORK - Drawing Approval | 2026-04-14 | 2026-04-30
A5760 | 40 MVA Power TRF OIL PIT DRAINAGE NETWORK - Drawing Approval | 2026-04-14 | 2026-04-30
A5750 | 175 MVA Power TRF OIL PIT DRAINAGE NETWORK - Drawing Approval | 2026-04-14 | 2026-04-30
A4670 | WIRE MESH FENCE STRUCTURAL DESIGN CALCULATIONS - Approval | 2026-04-14 | 2026-04-30
A4660 | WIRE MESH FENCE STRUCTURAL LAYOUT & DETAILS - Drawing Approval | 2026-04-14 | 2026-04-30
A4580 | 175MVA OIL PIT STRUCTURAL LAYOUT & DETAILS - Drawing Approval | 2026-04-14 | 2026-04-30
BSPRMEGENCR25 | Manufacturing - OH Crane, Min 5 Ton (( GIS 66 ) | 2026-04-14 | 2026-07-27
BSPRMEGENCR24 | Manufacturing - Monorail Crane 3 Ton | 2026-04-14 | 2026-07-27
BSPRMEGENCR23 | Manufacturing - OH Crane, Min 5 Ton ( GIS 220 ) | 2026-04-14 | 2026-07-27
BSENMEGENHC01 | Material submittal - Fans & Ventilation System | 2026-04-14 | 2026-04-30
BSPRELGENMV01 | Purchasing Request -MV Cables | 2026-04-13 | 2026-04-17
BSPRELGENHV01 | Purchasing Request - HV Cables | 2026-04-13 | 2026-04-17
BSPRELGENMV06 | Purchasing Request - Cable Steel Supports | 2026-04-13 | 2026-04-17
BSENELGENTK01 | Material submittal - MV termination | 2026-04-13 | 2026-04-30
A3720 | SCS Panels Base Design - Drawing Approval | 2026-04-13 | 2026-04-29
BSCNCVCRB--02 | PC Foundation for Control Building | 2026-04-12 | 2026-04-23
BSCNCVGI2--02 | PC Footings Works - 220 KV GIS Building | 2026-04-12 | 2026-04-15
BSPRELGENNR01 | Purchasing Request - Single phase Earthing resistor,20 Ohm | 2026-04-11 | 2026-04-20
A2700 | 220KV GIS BUILDING LIGHTING LUX CALCULATION - Submittal | 2026-04-10 | 2026-04-21
BSENMPGI2GR04 | 220KV GIS BUILDING PANEL SCHEDULES - Drawing Submittal | 2026-04-10 | 2026-04-21
BSENMPGI2GR03 | 220KV GIS BUILDING POWER SOCKET SYSTEM LAYOUT - Drawing Submittal | 2026-04-10 | 2026-04-21
BSENMPGI2GR02 | 220KV GIS BUILDING LIGHTING SYSTEM LAYOUT - Drawing Submittal | 2026-04-10 | 2026-04-21
BSENELGENGR07 | Overhead Conductor Calculation Report - Submittal | 2026-04-10 | 2026-04-15
BSENELGENCP39 | 66 CONTROL & PROTECTION WIRING SCHEMATICS MATERIAL APPROVAL | 2026-04-09 | 2026-04-23
A3490 | ROADS TYPICAL CROSS SECTIONS. - Drawing Submittal | 2026-04-08 | 2026-04-21
A3480 | ROADS SETTING PLAN & TABLES. - Drawing Submittal | 2026-04-08 | 2026-04-21
A3470 | ROADS PROFILES. - Drawing Submittal | 2026-04-08 | 2026-04-21
A3460 | ROADS SIGNS & MARKING LAYOUT & DETAILS. - Drawing Submittal | 2026-04-08 | 2026-04-21
A3440 | ROADS GENERAL LAYOUT. - Drawing Submittal | 2026-04-08 | 2026-04-21
A3430 | ROADS STRUCTURAL DESIGN CALCULATIONS. - Drawing Submittal | 2026-04-08 | 2026-04-21
A3400 | OVERALL POTABLE WATER SUPPLY NETWORK CALCULATION - Submittal | 2026-04-08 | 2026-04-14
A3390 | OVERALL FIRE EXTINGUISHER DISTRIBUTION - Drawing Submittal | 2026-04-08 | 2026-04-13
A3380 | OUTDOOR SEWAGE NETWORK - Drawing Submittal | 2026-04-08 | 2026-04-13
A3370 | OUTDOOR POTABLE WATER NETWORK - Drawing Submittal | 2026-04-08 | 2026-04-14
A3360 | 40 MVA Power TRF OIL PIT DRAINAGE NETWORK - Drawing Submittal | 2026-04-08 | 2026-04-13
A3350 | 175 MVA Power TRF OIL PIT DRAINAGE NETWORK - Drawing Submittal | 2026-04-08 | 2026-04-13
A3040 | OUTDOOR POWER SOCKET LAYOUT & GUARD TOWER PLAN - Drawing Submittal | 2026-04-08 | 2026-04-14
A3030 | OUTDOOR LIGHTING SYSTEM LAYOUT - Drawing Submittal | 2026-04-08 | 2026-04-14
A3020 | OUTDOOR LIGHTING LUX CALCULATION - Submittal | 2026-04-08 | 2026-04-14
A3010 | OUTDOOR PANEL SCHEDULE - Drawing Submittal | 2026-04-08 | 2026-04-14
A2690 | OUTDOOR CCTV SYSTEM PLAN - Drawing Submittal | 2026-04-08 | 2026-04-14
A2680 | OUTDOOR LIGHT CURRENT SYSTEM LAYOUT DATA & TELEPHONE SYSTEM PLAN - Drawing Submittal | 2026-04-08 | 2026-04-14
A2670 | OUTDOOR LIGHT CURRENT SYSTEM LAYOUT FIRE ALARM SYSTEM PLAN - Drawing Submittal | 2026-04-08 | 2026-04-14
A2290 | WIRE MESH FENCE STRUCTURAL DESIGN CALCULATIONS - Submittal | 2026-04-08 | 2026-04-13
A2280 | WIRE MESH FENCE STRUCTURAL LAYOUT & DETAILS - Drawing Submittal | 2026-04-08 | 2026-04-13
A2240 | OUTDOOR EQUIPMENT STEEL STRUCTURE SUPPORTS SECTIONS & DETAILS - Drawing Submittal | 2026-04-08 | 2026-04-16
A2230 | OUTDOOR EQUIPMENT STEEL STRUCTURE CALCULATION REPORT - Submittal | 2026-04-08 | 2026-04-16
A2200 | 175MVA OIL PIT STRUCTURAL LAYOUT & DETAILS - Drawing Submittal | 2026-04-08 | 2026-04-13
BSENMEGENCA3 | Material approval- Panel Frames | 2026-04-08 | 2026-04-24
BSENMPGENTD01 | DATA&TELEPHONE SYSTEM RISER PLAN - Drawing Submittal | 2026-04-08 | 2026-04-15
BSENMPGENSS01 | FIRE ALARM SYSTEM RISER PLAN - Drawing Submittal | 2026-04-08 | 2026-04-15
BSENELGENES04 | Material approval - Secondary Earthing System | 2026-04-08 | 2026-04-24
BSENELGENGR09 | SUBSTATION OVERALL CABLE ROUTING LAYOUT - Drawing Submittal | 2026-04-08 | 2026-04-15
BSERELGENES1 | Install Primary Earthing for Control Building | 2026-04-07 | 2026-04-10
A5580 | 66KV GIS BUILDING HVAC CALCULATION - Approval | 2026-04-07 | 2026-04-23
A5570 | 66KV GIS BUILDING HVAC SYSTEM LAYOUT & SECTIONS - Drawing Approval | 2026-04-07 | 2026-04-23
A5160 | 66KV GIS BUILDING LIGHTING LUX - Drawing Approval | 2026-04-07 | 2026-04-23
BSENMPGI1FA02 | 66KV GIS BUILDING FIRE ALARM SYSTEM LAYOUT - Drawing Approval | 2026-04-07 | 2026-04-23
BSENMPGI1TD07 | 66KV GIS BUILDING TELEPHONE SYSTEM LAYOUT - Drawing Approval | 2026-04-07 | 2026-04-23
BSENELGENLS01 | Material submittal - Lightning/Shielding System | 2026-04-07 | 2026-04-23
BSENMPGI1GR12 | 66KV GIS BUILDING PANEL SCHEDULES - Drawing Approval | 2026-04-07 | 2026-04-23
BSENMPGI1GR11 | 66KV GIS BUILDING POWER SOCKET SYSTEM LAYOUT - Drawing Approval | 2026-04-07 | 2026-04-23
BSENMPGI1GR10 | 66KV GIS BUILDING LIGHTING SYSTEM LAYOUT - Drawing Approval | 2026-04-07 | 2026-04-23
BSERELGENES01 | Install Primary Earthing for 220 KV GIS Building | 2026-04-07 | 2026-04-10
A1310 | SCS Panels Base Design - Drawing Submittal | 2026-04-06 | 2026-04-10
BSENMEGENFS05 | Material approval - Transformers fire fighghting system 40 MVA | 2026-04-03 | 2026-04-21
BSENMEGENFS06 | Material approval - Transformers fire fighghting system 175 MVA | 2026-04-03 | 2026-04-21
BSPRELGENAD75 | Purchasing Request - 48V Battery bank | 2026-04-02 | 2026-04-15
BSPRELGENAD65 | Purchasing Request - 220V DC battery bank | 2026-04-02 | 2026-04-15
A4790 | 40MVA PRESSURIZED WATER TANK CALCULATION - Approval | 2026-04-02 | 2026-04-20
A4780 | 40MVA PRESSURIZED WATER TANK STRUCTURAL DRAWINGS - Drawing Approval | 2026-04-02 | 2026-04-20
A4770 | 175MVA PRESSURIZED WATER TANK CALCULATION - Approval | 2026-04-02 | 2026-04-20
A4760 | 175MVA PRESSURIZED WATER TANK STRUCTURAL DRAWINGS - Drawing Approval | 2026-04-02 | 2026-04-20
BSPRELGENAD06 | Purchasing Request - AC & DC Panels | 2026-04-02 | 2026-04-15
BSCNCVGN1--10 | Excavation Works - 66 KV Outdoor Equipment - Equipment Foundation | 2026-04-02 | 2026-04-14
BSCNCVGN1--19 | Excavation Works - 66 KV Outdoor Equipment - GIB Foundation | 2026-04-02 | 2026-04-10
BSCNCVGI1--01 | Excavation Works - 66 KV GIS Building | 2026-04-02 | 2026-04-20
A5650 | FIRE FIGHTING ROOM #2 HVAC CALCULATION - Approval | 2026-04-01 | 2026-04-16
A5640 | FIRE FIGHTING ROOM #2 HVAC SYSTEM LAYOUT & DETAILS - Drawing Approval | 2026-04-01 | 2026-04-16
A5630 | FIRE FIGHTING ROOM #1 HVAC CALCULATION - Approval | 2026-04-01 | 2026-04-16
A5620 | FIRE FIGHTING ROOM #1 HVAC SYSTEM LAYOUT & DETAILS - Drawing Approval | 2026-04-01 | 2026-04-16
A4750 | 40MVA TRANSFORMER AREA CALCULATION - Approval | 2026-04-01 | 2026-04-16
A4720 | 40MVA TRANSFORMER AREA STRUCTURAL DRAWINGS - FOUNDATION PLAN , LAYOUT & DETAILS - Drawing Approval | 2026-04-01 | 2026-04-16
A4710 | 175MVA TRANSFORMER AREA CALCULATION - Approval | 2026-04-01 | 2026-04-16
A4680 | 175MVA TRANSFORMERS AREA STRUCTURAL DRAWINGS FOUNDATION PLAN , LAYOUT & DETAILS - Drawing Approval | 2026-04-01 | 2026-04-16
BSPRMEGENCR20 | PO Issuance - OH Crane, Min 5 Ton (( GIS 66 ) | 2026-03-31 | 2026-04-13
BSPRMEGENCR22 | PO Issuance - Monorail Crane 3 Ton | 2026-03-31 | 2026-04-13
BSPRMEGENCR21 | PO Issuance - OH Crane, Min 5 Ton ( GIS 220 ) | 2026-03-31 | 2026-04-13
BSPRELGENSE05 | Manufacturing - Cable Sealing End "HV" | 2026-03-29 | 2026-07-06
BSPRELGENLV04 | PO Issuance - LV CABLES | 2026-03-27 | 2026-04-25
BSPRELGENLV05 | PO Issuance - Control Cables | 2026-03-27 | 2026-04-25
BSPRELGENAD15 | Manufacturing - 11 KV /0.4KV (500 KVA) Aux. Transformer | 2026-03-26 | 2026-08-22
A4480 | 220KV GIB STRUCTURAL DRAWINGS - FOUNDATION PLAN & DETAILS - Drawing Approval | 2026-03-24 | 2026-04-15
BSPRMEGENCR19 | Purchasing Request - OH Crane, Min 5 Ton (( GIS 66 ) | 2026-03-24 | 2026-03-30
BSPRMEGENCR18 | Purchasing Request - Monorail Crane 3 Ton | 2026-03-24 | 2026-03-30
BSPRMEGENCR17 | Purchasing Request - OH Crane, Min 5 Ton ( GIS 220 ) | 2026-03-24 | 2026-03-30
BSENELGENAD08 | Material approval - Battery Charger | 2026-03-24 | 2026-04-15
A3940 | FIRE HYDRANT ROOM ARCHITECTURAL GENERAL DETAILS & SCHEDULES - Drawing Approval | 2026-03-23 | 2026-04-14
A3930 | FIRE HYDRANT ROOM ARCHITECTURAL SECTIONS & ELEVATION - Drawing Approval | 2026-03-23 | 2026-04-14
A3920 | FIRE HYDRANT ROOM ARCHITECTURAL PLANS - Drawing Approval | 2026-03-23 | 2026-04-14
BSENELGENOH04 | Material approval - OH Clamps | 2026-03-23 | 2026-04-14
BSCNCVTR7--01 | Excavation Works - 2*175 MVA Transformers | 2026-03-22 | 2026-04-15
BSENELGENTI02 | Material approval - Insulators | 2026-03-20 | 2026-04-14
A5560 | 220 KV GIS BUILDING HVAC SYSTEM DESIGN CALCULATION - Approval | 2026-03-20 | 2026-04-13
A5550 | 220KV GIS BUILDING HVAC SYSTEM LAYOUT & SECTION - Drawing Approval | 2026-03-20 | 2026-04-13
A5380 | FIRE FIGHTING ROOM #2 PANEL SCHEDULES - Drawing Approval | 2026-03-20 | 2026-04-13
A5370 | FIRE FIGHTING ROOM #2 POWER SOCKET SYSTEM PLAN - Drawing Approval | 2026-03-20 | 2026-04-13
A5360 | FIRE FIGHTING ROOM #2 NORMAL & EMERGENCY LIGHTING SYSTEM FLOOR PLAN - Drawing Approval | 2026-03-20 | 2026-04-13
A5350 | FIRE FIGHTING ROOM #2 LIGHTING LUX CALCULATION - Approval | 2026-03-20 | 2026-04-13
A5340 | FIRE FIGHTING ROOM #1 PANEL SCHEDULES - Drawing Approval | 2026-03-20 | 2026-04-13
A5330 | FIRE FIGHTING ROOM #1 POWER SOCKET SYSTEM PLAN - Drawing Approval | 2026-03-20 | 2026-04-13
A5320 | FIRE FIGHTING ROOM #1 NORMAL & EMERGENCY LIGHTING SYSTEM FLOOR PLAN - Drawing Approval | 2026-03-20 | 2026-04-13
A5310 | FIRE FIGHTING ROOM #1 LIGHTING LUX CALCULATION - Approval | 2026-03-20 | 2026-04-13
A5070 | FIRE FIGHTING ROOM #2 FIRE ALARM SYSTEM PLAN AND DETAILS - Drawing Approval | 2026-03-20 | 2026-04-13
A5060 | FIRE FIGHTING ROOM #1 FIRE ALARM SYSTEM PLAN AND DETAILS - Drawing Approval | 2026-03-20 | 2026-04-13
A4450 | FIRE FIGHTING ROOM #1 STRUCTURAL CALCULATIONS - Approval | 2026-03-20 | 2026-04-13
A4440 | FIRE FIGHTING ROOM #1 STRUCTURAL PLANS & SECTIONS - Drawing Approval | 2026-03-20 | 2026-04-13
A4430 | FIRE FIGHTING ROOM #1 STRUCTURAL CALCULATIONS - Approval | 2026-03-20 | 2026-04-13
A4420 | FIRE FIGHTING ROOM #1 STRUCTURAL PLANS & SECTIONS - Drawing Approval | 2026-03-20 | 2026-04-13
A3180 | 66KV GIS BUILDING HVAC CALCULATION - Submittal | 2026-03-20 | 2026-04-06
A3170 | 66KV GIS BUILDING HVAC SYSTEM LAYOUT & SECTIONS - Drawing Submittal | 2026-03-20 | 2026-04-06
A2740 | 66KV GIS BUILDING LIGHTING LUX - Drawing Submittal | 2026-03-20 | 2026-04-06
A2410 | 40MVA PRESSURIZED WATER TANK CALCULATION - Submittal | 2026-03-20 | 2026-04-01
A2400 | 40MVA PRESSURIZED WATER TANK STRUCTURAL DRAWINGS - Drawing Submittal | 2026-03-20 | 2026-04-01
A2390 | 175MVA PRESSURIZED WATER TANK CALCULATION - Submittal | 2026-03-20 | 2026-04-01
A2380 | 175MVA PRESSURIZED WATER TANK STRUCTURAL DRAWINGS - Drawing Submittal | 2026-03-20 | 2026-04-01
BSENMEGENCS01 | Material submittal - Gantry Steel | 2026-03-20 | 2026-04-13
BSENMPGI1TD01 | 66KV GIS BUILDING TELEPHONE SYSTEM LAYOUT - Drawing Submittal | 2026-03-20 | 2026-04-06
BSENMPGI1FA01 | 66KV GIS BUILDING FIRE ALARM SYSTEM LAYOUT - Drawing Submittal | 2026-03-20 | 2026-04-06
BSENMPGI2FA02 | 220KV GIS BUILDING FIRE ALARM SYSTEM LAYOUT - Drawing Approval | 2026-03-20 | 2026-04-13
BSENMPGI2TD07 | 220KV GIS BUILDING DATA & TELEPHONE SYSTEM LAYOUT - Drawing Approval | 2026-03-20 | 2026-04-13
BSENMEGENFS01 | Material submittal - Transformers fire fighghting system 40 MVA | 2026-03-20 | 2026-04-02
BSENELTR7T704 | 175 MVA TRANSFORMERS AREA WALL OPENING AND SECTIONS - Drawing Approval | 2026-03-20 | 2026-04-13
BSENMEGENFS02 | Material submittal - Transformers fire fighghting system 175 MVA | 2026-03-20 | 2026-04-02
BSENELGI1G109 | 66KV BUILDING WALL OPENING & FLOOR CUTOUT PLAN & SECTIONS - Drawing Approval | 2026-03-20 | 2026-04-13
BSENMPGI1GR04 | 66KV GIS BUILDING PANEL SCHEDULES - Drawing Submittal | 2026-03-20 | 2026-04-06
BSENMPGI1GR03 | 66KV GIS BUILDING POWER SOCKET SYSTEM LAYOUT - Drawing Submittal | 2026-03-20 | 2026-04-06
BSENMPGI1GR02 | 66KV GIS BUILDING LIGHTING SYSTEM LAYOUT - Drawing Submittal | 2026-03-20 | 2026-04-06
BSENELGENHV02 | Material approval - HV & MV Cable | 2026-03-19 | 2026-04-13
BSENELGENCP29 | 66 CONTROL & PROTECTION WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-03-19 | 2026-04-08
BSENELGENNR02 | Material approval - Neutral Point Equipment (NER) | 2026-03-19 | 2026-04-10
BSENELGENCP18 | Supplier Document Approval - C&P Panels Base Design | 2026-03-19 | 2026-04-08
BSENELGENCP17 | 220 CONTROL & PROTECTION WIRING SCHEMATICS MATERIAL APPROVAL | 2026-03-19 | 2026-04-08
BSENELGENCP15 | Supplier Document Submittal - C&P Panels Base Design | 2026-03-19 | 2026-04-08
BSENELGENCP14 | 220 CONTROL & PROTECTION WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-03-19 | 2026-04-08
A4170 | 220KV GIS S.O.G EMBEDDED PLATES LAYOUT PLAN - Drawing Approval | 2026-03-18 | 2026-04-09
A4160 | 220KV GIS BUILDING STRUCTURAL DRAWINGS TYPICAL DETAILS - Drawing Approval | 2026-03-18 | 2026-04-09
A4150 | 220KV GIS BUILDING STRUCTURAL DRAWINGS FRAME DETAILS - Drawing Approval | 2026-03-18 | 2026-04-09
A4140 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - ROOF PLAN - Drawing Approval | 2026-03-18 | 2026-04-09
A4130 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - CARNE BEAMS - Drawing Approval | 2026-03-18 | 2026-04-09
A4120 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - TIE BEAMS - Drawing Approval | 2026-03-18 | 2026-04-09
A4110 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - GROUND FLOOR - SECTIONS & DETAILS - Drawing Approval | 2026-03-18 | 2026-04-09
A4100 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - GROUND FLOOR PLAN - Drawing Approval | 2026-03-18 | 2026-04-09
A4090 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - FOUNDATION PLAN - Drawing Approval | 2026-03-18 | 2026-04-09
A4080 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - COLUMNS AND AXES - Drawing Approval | 2026-03-18 | 2026-04-09
A4070 | 220KV GIS BUILDING STRUCTURAL CALCULATION REPORT - Approval | 2026-03-18 | 2026-04-09
A2100 | 220KV GIB STRUCTURAL DRAWINGS - FOUNDATION PLAN & DETAILS - Drawing Submittal | 2026-03-18 | 2026-03-23
BSENMEGENCS02 | Material submittal - Outdoor Steel Structure | 2026-03-17 | 2026-04-08
BSPRELGENSE04 | PO Issuance - Cable Sealing End "HV" | 2026-03-17 | 2026-03-28
BSPRELGENSA09 | Manufacturing - Surge Arresters | 2026-03-17 | 2026-08-18
BSPRELGENLV01 | Purchasing Request - LV CABLES | 2026-03-17 | 2026-03-26
BSPRELGENLV02 | Purchasing Request - Control Cables | 2026-03-17 | 2026-03-26
A3250 | FIRE FIGHTING ROOM #2 HVAC CALCULATION - Submittal | 2026-03-16 | 2026-03-24
A3240 | FIRE FIGHTING ROOM #2 HVAC SYSTEM LAYOUT & DETAILS - Drawing Submittal | 2026-03-16 | 2026-03-24
A3230 | FIRE FIGHTING ROOM #1 HVAC CALCULATION - Submittal | 2026-03-16 | 2026-03-24
A3220 | FIRE FIGHTING ROOM #1 HVAC SYSTEM LAYOUT & DETAILS - Drawing Submittal | 2026-03-16 | 2026-03-24
A2960 | FIRE FIGHTING ROOM #2 PANEL SCHEDULES - Drawing Submittal | 2026-03-16 | 2026-03-19
A2950 | FIRE FIGHTING ROOM #2 POWER SOCKET SYSTEM PLAN - Drawing Submittal | 2026-03-16 | 2026-03-19
A2940 | FIRE FIGHTING ROOM #2 NORMAL & EMERGENCY LIGHTING SYSTEM FLOOR PLAN - Drawing Submittal | 2026-03-16 | 2026-03-19
A2930 | FIRE FIGHTING ROOM #2 LIGHTING LUX CALCULATION - Submittal | 2026-03-16 | 2026-03-19
A2880 | FIRE FIGHTING ROOM #1 PANEL SCHEDULES - Drawing Submittal | 2026-03-16 | 2026-03-19
A2870 | FIRE FIGHTING ROOM #1 POWER SOCKET SYSTEM PLAN - Drawing Submittal | 2026-03-16 | 2026-03-19
A2860 | FIRE FIGHTING ROOM #1 NORMAL & EMERGENCY LIGHTING SYSTEM FLOOR PLAN - Drawing Submittal | 2026-03-16 | 2026-03-19
A2850 | FIRE FIGHTING ROOM #1 LIGHTING LUX CALCULATION - Submittal | 2026-03-16 | 2026-03-19
A2650 | FIRE FIGHTING ROOM #2 FIRE ALARM SYSTEM PLAN AND DETAILS - Drawing Submittal | 2026-03-16 | 2026-03-19
A2640 | FIRE FIGHTING ROOM #1 FIRE ALARM SYSTEM PLAN AND DETAILS - Drawing Submittal | 2026-03-16 | 2026-03-19
A2060 | FIRE FIGHTING ROOM #1 STRUCTURAL CALCULATIONS - Submittal | 2026-03-16 | 2026-03-19
A2050 | FIRE FIGHTING ROOM #1 STRUCTURAL PLANS & SECTIONS - Drawing Submittal | 2026-03-16 | 2026-03-19
A2010 | FIRE FIGHTING ROOM #1 STRUCTURAL CALCULATIONS - Submittal | 2026-03-16 | 2026-03-19
A2000 | FIRE FIGHTING ROOM #1 STRUCTURAL PLANS & SECTIONS - Drawing Submittal | 2026-03-16 | 2026-03-19
A1530 | FIRE HYDRANT ROOM ARCHITECTURAL GENERAL DETAILS & SCHEDULES - Drawing Submittal | 2026-03-16 | 2026-03-20
A1520 | FIRE HYDRANT ROOM ARCHITECTURAL SECTIONS & ELEVATION - Drawing Submittal | 2026-03-16 | 2026-03-20
A1510 | FIRE HYDRANT ROOM ARCHITECTURAL PLANS - Drawing Submittal | 2026-03-16 | 2026-03-20
BSENMEGENCS03 | Material submittal - Panel Frames | 2026-03-16 | 2026-04-07
BSENELTR7T702 | 175 MVA TRANSFORMERS AREA WALL OPENING AND SECTIONS - Drawing Submittal | 2026-03-16 | 2026-03-19
BSENELGENES02 | Material submittal - Secondary Earthing System | 2026-03-16 | 2026-04-07
BSENELGENGR10 | GENERAL LAYOUT - Drawing Approval | 2026-03-16 | 2026-04-07
BSPRELGENCP48 | Manufacturing - Transformers 40 | 2026-03-15 | 2026-12-22
BSPRELGENAD08 | PO Issuance - 11 KV /0.4KV (500 KVA) Aux. Transformer | 2026-03-14 | 2026-03-25
BSENELGENGR12 | SUBSTATION MAIN GRID LAYOUT & DETAILS - Drawing Approval | 2026-03-13 | 2026-04-06
BSPRELGENCP15 | PO Issuance -Control & Protection Panels | 2026-03-12 | 2026-03-18
BSPRELGENCP05 | Manufacturing - Control & Protection System | 2026-03-12 | 2026-07-29
BSPRELGENCB03 | Manufacturing - Capacitor Banks | 2026-03-12 | 2026-07-09
BSENELGI1G104 | 66KV BUILDING WALL OPENING & FLOOR CUTOUT PLAN & SECTIONS - Drawing Submittal | 2026-03-12 | 2026-03-19
BSENELGI1G108 | 66KV GIS BUILDING CABLE ROUTING LAYOUT, SECTIONS - Drawing Approval | 2026-03-12 | 2026-04-03
A3160 | 220 KV GIS BUILDING HVAC SYSTEM DESIGN CALCULATION - Submittal | 2026-03-11 | 2026-03-19
A3150 | 220KV GIS BUILDING HVAC SYSTEM LAYOUT & SECTION - Drawing Submittal | 2026-03-11 | 2026-03-19
A2370 | 40MVA TRANSFORMER AREA CALCULATION - Submittal | 2026-03-11 | 2026-03-24
A2340 | 40MVA TRANSFORMER AREA STRUCTURAL DRAWINGS - FOUNDATION PLAN , LAYOUT & DETAILS - Drawing Submittal | 2026-03-11 | 2026-03-24
A2330 | 175MVA TRANSFORMER AREA CALCULATION - Submittal | 2026-03-11 | 2026-03-24
A2300 | 175MVA TRANSFORMERS AREA STRUCTURAL DRAWINGS FOUNDATION PLAN , LAYOUT & DETAILS - Drawing Submittal | 2026-03-11 | 2026-03-24
A1750 | 220KV GIS S.O.G EMBEDDED PLATES LAYOUT PLAN - Drawing Submittal | 2026-03-11 | 2026-03-17
A1740 | 220KV GIS BUILDING STRUCTURAL DRAWINGS TYPICAL DETAILS - Drawing Submittal | 2026-03-11 | 2026-03-17
A1730 | 220KV GIS BUILDING STRUCTURAL DRAWINGS FRAME DETAILS - Drawing Submittal | 2026-03-11 | 2026-03-17
A1720 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - ROOF PLAN - Drawing Submittal | 2026-03-11 | 2026-03-17
A1710 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - CARNE BEAMS - Drawing Submittal | 2026-03-11 | 2026-03-17
A1700 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - TIE BEAMS - Drawing Submittal | 2026-03-11 | 2026-03-17
A1690 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - GROUND FLOOR - SECTIONS & DETAILS - Drawing Submittal | 2026-03-11 | 2026-03-17
A1680 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - GROUND FLOOR PLAN - Drawing Submittal | 2026-03-11 | 2026-03-17
A1670 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - FOUNDATION PLAN - Drawing Submittal | 2026-03-11 | 2026-03-17
A1660 | 220KV GIS BUILDING STRUCTURAL DRAWINGS - COLUMNS AND AXES - Drawing Submittal | 2026-03-11 | 2026-03-17
A1650 | 220KV GIS BUILDING STRUCTURAL CALCULATION REPORT - Submittal | 2026-03-11 | 2026-03-17
BSENMPGI2TD01 | 220KV GIS BUILDING DATA & TELEPHONE SYSTEM LAYOUT - Drawing Submittal | 2026-03-11 | 2026-03-19
BSENMPGI2FA01 | 220KV GIS BUILDING FIRE ALARM SYSTEM LAYOUT - Drawing Submittal | 2026-03-11 | 2026-03-19
BSENELTR7T703 | 175 MVA TRANSFORMERS AREA EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Approval | 2026-03-11 | 2026-04-02
BSPRELGENSG03 | Manufacturing - 11 KV MVSWGR ( S/S ) | 2026-03-11 | 2026-07-24
BSPRELGENES20 | Delivery to Site - Main Grounding Materials | 2026-03-10 | 2026-03-13
BSPRELGENES19 | Delivery to Site - Main Grounding Cables | 2026-03-10 | 2026-03-13
BSPRELGENAD01 | Purchasing Request - 11 KV /0.4KV (500 KVA) Aux. Transformer | 2026-03-10 | 2026-03-13
BSENELGENAD07 | Material approval - DC Batteries | 2026-03-10 | 2026-04-01
BSENELGENAD09 | Material approval - AC & DC Panels | 2026-03-10 | 2026-04-01
BSENELGENAD06 | Material approval - 11 KV /0.4KV (300 KVA) Aux. Transformer | 2026-03-10 | 2026-04-01
BSENELCRBGR08 | CONTROL BUILDING WALL OPENING & FLOOR CUTOUT - Drawing Approval | 2026-03-10 | 2026-04-01
BSENELGENGR15 | GROUNDING SYSTEM CALCULATION REPORT - Approval | 2026-03-10 | 2026-04-01
BSENELCRBGR06 | CONTROL BUILDING EQUIPMENT EARTHING LAYOUT - Drawing Approval | 2026-03-10 | 2026-04-01
A4510 | 66KV GIB STRUCTURAL DESIGN CALCULATION - Approval | 2026-03-09 | 2026-03-24
A4500 | 66KV GIB STRUCTURAL DRAWINGS - FOUNDATION PLAN & DETAILS - Drawing Approval | 2026-03-09 | 2026-03-24
BSENMEGENCR04 | Material approval - Monorail Crane 3 Ton | 2026-03-06 | 2026-03-23
BSENMEGENCR03 | Material approval - OH Crane, Min 5 Ton | 2026-03-06 | 2026-03-23
BSENELGENAD03 | Material submittal - battery Charger | 2026-03-06 | 2026-03-23
BSCNCVTRN--09 | Excavation Works - Trenches - Road Crossing - Gantry yard 220 KV to 220 KV GIS | 2026-03-05 | 2026-03-11
BSENELTR7T701 | 175 MVA TRANSFORMERS AREA EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Submittal | 2026-03-05 | 2026-03-10
BSENELGENOH02 | Material submittal - OH Clamps | 2026-03-05 | 2026-03-20
BSENELGENGR01 | GENERAL LAYOUT - Drawing Submittal | 2026-03-05 | 2026-03-13
BSENELGENTI01 | Material submittal - Insulators | 2026-03-04 | 2026-03-20
A5610 | CONTROL BUILDING HVAC CALCULATION - Approval | 2026-03-04 | 2026-03-19
A5590 | CONTROL BUILDING HVAC SYSTEM PLANS AND SECTIONS - Drawing Approval | 2026-03-04 | 2026-03-19
A5260 | CONTROL BUILDING PANEL SCHEDULE - Drawing Approval | 2026-03-04 | 2026-03-19
A5250 | CONTROL BUILDING POWER SOCKET SYSTEM GROUND FLOOR - Drawing Approval | 2026-03-04 | 2026-03-19
A5240 | CONTROL BUILDING POWER SOCKET SYSTEM BASEMENT FLOOR - Drawing Approval | 2026-03-04 | 2026-03-19
A5230 | CONTROL BUILDING LIGHTING SYSTEM FIRST FLOOR - Drawing Approval | 2026-03-04 | 2026-03-19
A5220 | CONTROL BUILDING LIGHTING SYSTEM GROUND FLOOR - Drawing Approval | 2026-03-04 | 2026-03-19
A5210 | CONTROL BUILDING LIGHTING SYSTEM BASEMENT FLOOR - Drawing Approval | 2026-03-04 | 2026-03-19
A5200 | CONTROL BUILDING LIGHTING LUX CALCULATION - Approval | 2026-03-04 | 2026-03-19
A5030 | CONTROL BUILDING FIRE ALARM SYSTEM LAYOUT - Drawing Approval | 2026-03-04 | 2026-03-19
A5020 | CONTROL BUILDING TELEPHONE SYSTEM LAYOUT - Drawing Approval | 2026-03-04 | 2026-03-19
A4060 | 220kV GANTRY FOUNDATION CALCULATION REPORT - Approval | 2026-03-04 | 2026-03-19
A4050 | 220kV GANTRY STRUCTURAL DRAWINGS - FOUNDATION PLAN & SECTIONS - Drawing Approval | 2026-03-04 | 2026-03-19
A4040 | 220kV GANTRY STEEL STRUCTURE CALCULATION - Approval | 2026-03-04 | 2026-03-19
A4030 | 220kV GANTRY STEEL STRUCTURAL DRAWINGS - Drawing Approval | 2026-03-04 | 2026-03-19
BSENARGI2GR131 | 66KV GIS BUILDING ARCHITECTURAL DRAWINGS - ELEVATION Plan - Drawing Approval | 2026-03-04 | 2026-03-19
BSENARGI2GR121 | 66KV GIS BUILDING ARCHITECTURAL DRAWINGS - Roof Floor Plan - Drawing Approval | 2026-03-04 | 2026-03-19
BSENARGI2GR111 | 66KV GIS BUILDING ARCHITECTURAL DRAWINGS - SECTIONS & FINISHING SCHEDUELS - Drawing Approval | 2026-03-04 | 2026-03-19
BSENARGI1GR1 | 66KV GIS BUILDING ARCHITECTURAL DRAWINGS - Ground Floor Plan - Drawing Approval | 2026-03-04 | 2026-03-19
BSENELCRBGR04 | CONTROL BUILDING WALL OPENING & FLOOR CUTOUT - Drawing Submittal | 2026-03-04 | 2026-03-09
BSENELCRBGR07 | CONTROL BUILDING CABLE ROUTING LAYOUT, SECTIONS - Drawing Approval | 2026-03-04 | 2026-03-19
BSENELGI1G103 | 66KV GIS BUILDING CABLE ROUTING LAYOUT, SECTIONS - Drawing Submittal | 2026-03-04 | 2026-03-11
BSENELCRBGR02 | CONTROL BUILDING EQUIPMENT EARTHING LAYOUT - Drawing Submittal | 2026-03-04 | 2026-03-09
BSENELGENHV01 | Material submittal - HV & MV Cable | 2026-03-03 | 2026-03-19
BSENELGENGR30 | Earthing resistively Measurement Report - Drawing Approval | 2026-03-03 | 2026-03-18
BSPRELGENCP03 | PO Issuance -Control & Protection System | 2026-03-03 | 2026-03-11
BSENELGI2G208 | 220KV BUILDING WALL OPENING & FLOOR CUTOUT PLAN, SECTIONS & FILLING RATIO - Drawing Approval | 2026-03-03 | 2026-03-18
BSENELGENNR01 | Material submittal - Neutral Point Equipment ( NER) | 2026-03-03 | 2026-03-18
BSENELGENGR06 | GROUNDING SYSTEM CALCULATION REPORT - Submittal | 2026-03-03 | 2026-03-09
BSENELGENGR03 | SUBSTATION MAIN GRID LAYOUT & DETAILS - Drawing Submittal | 2026-03-03 | 2026-03-12
A5600 | CONTROL BUILDING POTABLE WATER SUPPLY LAYOUT - Drawing Approval | 2026-03-02 | 2026-03-17
A4290 | 66KV GIS S.O.G EMBEDDED PLATES LAYOUT PLAN - Drawing Approval | 2026-03-02 | 2026-03-17
A4270 | 66KV GIS BUILDING STRUCTURAL DRAWINGS FRAME DETAILS - Drawing Approval | 2026-03-02 | 2026-03-17
A4260 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - ROOF PLAN - Drawing Approval | 2026-03-02 | 2026-03-17
A4250 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - CARNE BEAMS - Drawing Approval | 2026-03-02 | 2026-03-17
A4240 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - TIE BEAMS - Drawing Approval | 2026-03-02 | 2026-03-17
A4230 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - GROUND FLOOR - SECTIONS & DETAILS - Drawing Approval | 2026-03-02 | 2026-03-17
A4220 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - GROUND FLOOR PLAN - Drawing Approval | 2026-03-02 | 2026-03-17
A4210 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - FOUNDATION PLAN - Drawing Approval | 2026-03-02 | 2026-03-17
A4200 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - COLUMNS AND AXES - Drawing Approval | 2026-03-02 | 2026-03-17
A4190 | 66KV GIS BUILDING STRUCTURAL CALCULATION REPORT - Approval | 2026-03-02 | 2026-03-17
A2120 | 66KV GIB STRUCTURAL DRAWINGS - FOUNDATION PLAN - Drawing Submittal | 2026-03-02 | 2026-03-06
BSCNCVCRB--01 | Excavation Works - Control Building | 2026-03-02 | 2026-03-24
BSPRELGENDS07 | Manufacturing - Disconnector Switches | 2026-02-28 | 2026-06-23
BSPRELGENLT03 | Manufacturing - Wave Trap "Line Trap" | 2026-02-28 | 2026-06-23
BSPRELGENVT09 | Manufacturing - Voltage Transformer (CVT,VT) | 2026-02-28 | 2026-06-23
BSPRELGENCT07 | Manufacturing - Current Transformers | 2026-02-28 | 2026-06-23
BSENELGI2G245 | 220KV GIS BUILDING CABLE ROUTING LAYOUT, SECTIONS - Drawing Approval | 2026-02-26 | 2026-03-16
BSENELGENSE02 | Material approval - 66KV Cable Sealing End | 2026-02-26 | 2026-03-16
BSENELGENSA02 | Material approval - Surge Arresters | 2026-02-26 | 2026-03-16
BSENELGENLV03 | Material approval - LV CABLES | 2026-02-26 | 2026-03-16
BSENELGENLV04 | Material approval - Control Cables | 2026-02-26 | 2026-03-16
A3910 | FIRE FIGHTING ROOM 2 ARCHITECTURAL PLANS & SECTIONS - Drawing Approval | 2026-02-25 | 2026-03-13
A3880 | FIRE FIGHTING ROOM 1 ARCHITECTURAL PLANS & SECTIONS - Drawing Approval | 2026-02-25 | 2026-03-13
BSCNCVTY4--19 | Excavation Works - 3*40 MVA Outdoor Equipment & Gantry -Cables Sealing End Foundation | 2026-02-25 | 2026-03-09
BSCNCVTRN--01 | Excavation Works - Trenches - Gantry yard 220 KV to 220 KV GIS | 2026-02-25 | 2026-03-04
BSCNCVGI2--01 | Excavation Works - 220 KV GIS Building | 2026-02-25 | 2026-03-20
BSPRELGENTL03 | Manufacturing - Complete Telecommunication System With All accessories and Spare Parts | 2026-02-25 | 2026-09-08
BSENELCRBGR03 | CONTROL BUILDING CABLE ROUTING LAYOUT, SECTIONS - Drawing Submittal | 2026-02-25 | 2026-03-03
BSENELCRBGR05 | CONTROL BUILDING EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Approval | 2026-02-25 | 2026-03-13
BSCNCVTY4--10 | Excavation Works - 3*40 MVA Outdoor Equipment & Gantry - GIB Foundation | 2026-02-25 | 2026-03-09
BSCNCVTY4--01 | Excavation Works - 3*40 MVA Outdoor Equipment & Gantry - Equipment Foundation | 2026-02-25 | 2026-03-09
BSENELGENGR29 | Earthing resistively Measurement Report - Submittal | 2026-02-23 | 2026-03-02
BSENELGENGR02 | Soil resistively point locations - Drawing Submittal | 2026-02-23 | 2026-02-24
BSPRELGENES14 | Manufacturing - Main Grounding Materials | 2026-02-23 | 2026-03-09
BSPRELGENES13 | Manufacturing - Main Grounding Cables | 2026-02-23 | 2026-03-09
BSENARGI2GR91 | 220KV GIS BUILDING ARCHITECTURAL DRAWINGS - ELEVATION Plan - Drawing Approval | 2026-02-20 | 2026-03-10
BSENARGI2GR81 | 220KV GIS BUILDING ARCHITECTURAL DRAWINGS - Roof Floor Plan - Drawing Approval | 2026-02-20 | 2026-03-10
BSENARGI2GR71 | 220KV GIS BUILDING ARCHITECTURAL DRAWINGS - SECTIONS & FINISHING SCHEDUELS - Drawing Approval | 2026-02-20 | 2026-03-10
BSENARGI2GR101 | 220KV GIS BUILDING ARCHITECTURAL DRAWINGS - Ground Floor Plan - Drawing Approval | 2026-02-20 | 2026-03-10
A3210 | CONTROL BUILDING HVAC CALCULATION - Submittal | 2026-02-20 | 2026-03-03
A3200 | CONTROL BUILDING POTABLE WATER SUPPLY LAYOUT - Drawing Submittal | 2026-02-20 | 2026-02-26
A3190 | CONTROL BUILDING HVAC SYSTEM PLANS AND SECTIONS - Drawing Submittal | 2026-02-20 | 2026-03-03
A2840 | CONTROL BUILDING PANEL SCHEDULE - Drawing Submittal | 2026-02-20 | 2026-03-03
A2830 | CONTROL BUILDING POWER SOCKET SYSTEM GROUND FLOOR - Drawing Submittal | 2026-02-20 | 2026-03-03
A2820 | CONTROL BUILDING POWER SOCKET SYSTEM BASEMENT FLOOR - Drawing Submittal | 2026-02-20 | 2026-03-03
A2810 | CONTROL BUILDING LIGHTING SYSTEM FIRST FLOOR - Drawing Submittal | 2026-02-20 | 2026-03-03
A2800 | CONTROL BUILDING LIGHTING SYSTEM GROUND FLOOR - Drawing Submittal | 2026-02-20 | 2026-03-03
A2790 | CONTROL BUILDING LIGHTING SYSTEM BASEMENT FLOOR - Drawing Submittal | 2026-02-20 | 2026-03-03
A2780 | CONTROL BUILDING LIGHTING LUX CALCULATION - Submittal | 2026-02-20 | 2026-03-03
A2610 | CONTROL BUILDING FIRE ALARM SYSTEM LAYOUT - Drawing Submittal | 2026-02-20 | 2026-03-03
A2600 | CONTROL BUILDING TELEPHONE SYSTEM LAYOUT - Drawing Submittal | 2026-02-20 | 2026-03-03
A1870 | 66KV GIS S.O.G EMBEDDED PLATES LAYOUT PLAN - Drawing Submittal | 2026-02-20 | 2026-02-26
A1850 | 66KV GIS BUILDING STRUCTURAL DRAWINGS FRAME DETAILS - Drawing Submittal | 2026-02-20 | 2026-02-26
A1840 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - ROOF PLAN - Drawing Submittal | 2026-02-20 | 2026-02-26
A1830 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - CARNE BEAMS - Drawing Submittal | 2026-02-20 | 2026-02-26
A1820 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - TIE BEAMS - Drawing Submittal | 2026-02-20 | 2026-02-26
A1810 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - GROUND FLOOR - SECTIONS & DETAILS - Drawing Submittal | 2026-02-20 | 2026-02-26
A1800 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - GROUND FLOOR PLAN - Drawing Submittal | 2026-02-20 | 2026-02-26
A1790 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - FOUNDATION PLAN - Drawing Submittal | 2026-02-20 | 2026-02-26
A1780 | 66KV GIS BUILDING STRUCTURAL DRAWINGS - COLUMNS AND AXES - Drawing Submittal | 2026-02-20 | 2026-02-26
A1770 | 66KV GIS BUILDING STRUCTURAL CALCULATION REPORT - Submittal | 2026-02-20 | 2026-02-26
A1640 | 220kV GANTRY FOUNDATION CALCULATION REPORT - Submittal | 2026-02-20 | 2026-03-03
A1630 | 220kV GANTRY STRUCTURAL DRAWINGS - FOUNDATION PLAN & SECTIONS - Drawing Submittal | 2026-02-20 | 2026-03-03
A1620 | 220kV GANTRY STEEL STRUCTURE CALCULATION - Submittal | 2026-02-20 | 2026-03-03
A1610 | 220kV GANTRY STEEL STRUCTURAL DRAWINGS - Drawing Submittal | 2026-02-20 | 2026-03-03
BSENARGI2GR61 | 66KV GIS BUILDING ARCHITECTURAL DRAWINGS - ELEVATION Plan - Drawing Submittal | 2026-02-20 | 2026-03-03
BSENARGI2GR51 | 66KV GIS BUILDING ARCHITECTURAL DRAWINGS - Roof Floor Plan - Drawing Submittal | 2026-02-20 | 2026-03-03
BSENARGI2GR41 | 66KV GIS BUILDING ARCHITECTURAL DRAWINGS - SECTIONS & FINISHING SCHEDUELS - Drawing Submittal | 2026-02-20 | 2026-03-03
BSENELGI2G225 | 220KV GIS BUILDING CABLE ROUTING LAYOUT, SECTIONS - Drawing Submittal | 2026-02-20 | 2026-02-25
BSENELGI2G203 | 220 kV GIS WALL OPENING LAYOUT AND SECTIONS - Drawing Submittal | 2026-02-20 | 2026-03-02
BSENELTR7T706 | 175MVA TRANSFORMER WIRING SCHEMATICS MATERIAL APPROVAL | 2026-02-20 | 2026-03-06
BSENARGI1GR01 | 66KV GIS BUILDING ARCHITECTURAL DRAWINGS - Ground Floor Plan - Drawing Submittal | 2026-02-20 | 2026-03-03
A3670 | SCS Material Approval | 2026-02-19 | 2026-03-09
BSPRELGENLT02 | PO Issuance - Wave Trap "Line Trap" | 2026-02-19 | 2026-02-27
BSENELGENCP13 | Material approval - Control & Protection Systems | 2026-02-19 | 2026-03-09
BSENELGENAD02 | Material submittal -DC batteries | 2026-02-19 | 2026-03-09
BSENELGENAD04 | Material submittal - AC & DC Panels | 2026-02-19 | 2026-03-09
BSENELGENAD01 | Material submittal - AUXILIARY TRANSFORMER | 2026-02-19 | 2026-03-09
BSENELCRBGR01 | CONTROL BUILDING EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Submittal | 2026-02-19 | 2026-02-24
A1500 | FIRE FIGHTING ROOM 2 ARCHITECTURAL PLANS & SECTIONS - Drawing Submittal | 2026-02-18 | 2026-02-24
A1470 | FIRE FIGHTING ROOM 1 ARCHITECTURAL PLANS & SECTIONS - Drawing Submittal | 2026-02-18 | 2026-02-24
BSENELTR4T403 | 40MVA TRANSFORMERS AREA EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Approval | 2026-02-18 | 2026-03-06
BSENELTR4T404 | 40MVA TRANSFORMERS AREA WALL OPENING AND SECTIONS - Drawing Approval | 2026-02-18 | 2026-03-06
BSPRELGENES08 | PO Issuance - Main Grounding Materials | 2026-02-17 | 2026-02-22
BSPRELGENES07 | PO Issuance - Main Grounding Cables | 2026-02-17 | 2026-02-22
BSENMEGENCR02 | Material submittal - Monorail Crane 3 Ton | 2026-02-17 | 2026-03-05
BSENMEGENCR01 | Material submittal - OH Crane, Min 5 Ton | 2026-02-17 | 2026-03-05
BSENELGENCP19 | SCS WIRING SCHEMATICS MATERIAL APPROVAL | 2026-02-17 | 2026-03-03
BSPRELGENDS04 | PO Issuance - Disconnector Switches | 2026-02-14 | 2026-02-27
BSPRELGENVT06 | PO Issuance - Voltage Transformer (CVT,VT) | 2026-02-14 | 2026-02-27
BSPRELGENCT04 | PO Issuance - Current Transformers | 2026-02-14 | 2026-02-27
BSENELGENVT02 | Material approval -Three phase transformer 40 MVA with all accessories. | 2026-02-11 | 2026-03-02
BSENELTR4T401 | 40MVA TRANSFORMERS AREA EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Submittal | 2026-02-11 | 2026-02-17
BSENELTR4T402 | 40MVA TRANSFORMERS AREA WALL OPENING AND SECTIONS - Drawing Submittal | 2026-02-11 | 2026-02-17
BSENARGI2GR31 | 220KV GIS BUILDING ARCHITECTURAL DRAWINGS - ELEVATION Plan - Drawing Submittal | 2026-02-10 | 2026-02-19
BSENARGI2GR21 | 220KV GIS BUILDING ARCHITECTURAL DRAWINGS - Roof Floor Plan - Drawing Submittal | 2026-02-10 | 2026-02-19
BSENARGI2GR11 | 220KV GIS BUILDING ARCHITECTURAL DRAWINGS - SECTIONS & FINISHING SCHEDUELS - Drawing Submittal | 2026-02-10 | 2026-02-19
BSPRELGENT703 | Manufacturing -Three phase transformer 175 MVA with all accessories. | 2026-02-10 | 2026-06-29
BSPRELGENDS01 | Purchasing Request - Disconnector Switches | 2026-02-10 | 2026-02-13
BSPRELGENLT01 | Purchasing Request Wave Trap "Line Trap" | 2026-02-10 | 2026-02-18
BSPRELGENVT03 | Purchasing Request - Voltage Transformer (CVT,VT) | 2026-02-10 | 2026-02-13
BSPRELGENCT01 | Purchasing Request - Current Transformers | 2026-02-10 | 2026-02-13
BSENELTR7T705 | 175MVA TRANSFORMER WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-02-10 | 2026-02-19
BSENARGI2GR01 | 220KV GIS BUILDING ARCHITECTURAL DRAWINGS - Ground Floor Plan - Drawing Submittal | 2026-02-10 | 2026-02-19
BSPRELGENG203 | Manufacturing - 220 KV GIS & GIB | 2026-02-10 | 2026-07-09
BSPRELGENG103 | Manufacturing - 66 KV GIS & GIB | 2026-02-10 | 2026-07-09
BSPRELGENCB02 | PO Issuance - Capacitor Banks | 2026-02-10 | 2026-02-23
BSPRELGENES02 | Purchasing Request - Main Grounding Materials | 2026-02-10 | 2026-02-16
BSPRELGENES01 | Purchasing Request - Main Grounding Cables | 2026-02-10 | 2026-02-16
BSENELGENCB04 | 11 KV CAPACITOR BANK WIRING SCHEMATICS MATERIAL APPROVAL | 2026-02-10 | 2026-02-24
BSENELGENCB03 | 11 KV CAPACITOR BANK WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-02-10 | 2026-02-24
BSENELGENSA01 | Material submittal - Surge Arresters | 2026-02-09 | 2026-02-25
BSENELGENLV01 | Material submittal - LV CABLES | 2026-02-09 | 2026-02-25
BSENELGENLV02 | Material submittal - Control Cables | 2026-02-09 | 2026-02-25
BSENELGENSE01 | Material submittal - 66KV Cable Sealing End. | 2026-02-09 | 2026-02-25
BSENCVGENGR111 | Bulk EXCAVATION PLAN - Drawing Approval | 2026-02-06 | 2026-02-24
BSENELGENTL02 | Material approval - Telecommunication System | 2026-02-06 | 2026-02-24
BSENELGENSG04 | MV SWGR Schematic Drawing Material APPROVAL | 2026-02-06 | 2026-02-20
BSENELGI2G255 | 220KV BUILDING EQUIPMENT EARTHING LAYOUT & DETAILS - Drawing Approval | 2026-02-05 | 2026-02-23
BSENELGENGR68 | Soil resistively measurement Method of Statement - Drawing Approval | 2026-02-04 | 2026-02-20
BSENARCRBGR101 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - SECTIONS - Drawing Approval | 2026-02-03 | 2026-02-19
BSENARCRBGR91 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - ELEVATIONS - Drawing Approval | 2026-02-03 | 2026-02-19
BSENARCRBGR81 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - Roof Floor Plan - Drawing Approval | 2026-02-03 | 2026-02-19
BSENARCRBGR71 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - First Floor Plan - Drawing Approval | 2026-02-03 | 2026-02-19
BSENARCRBGR61 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - Ground Floor Plan - Drawing Approval | 2026-02-03 | 2026-02-19
BSENARCRBGR111 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - BASEMENT Floor Plan - Drawing Approval | 2026-02-03 | 2026-02-19
A1260 | SCS MATERIAL SUBMITTAL | 2026-02-02 | 2026-02-18
BSENELGENCP12 | Material submittal - Control & Protection | 2026-02-02 | 2026-02-18
BSENELGENCP16 | SCS WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-02-02 | 2026-02-16
BSENELGI1G106 | 66KV GIS BUILDING EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Approval | 2026-02-02 | 2026-02-18
BSPRELGENCP38 | PO Issuance - Transformers 40 | 2026-01-30 | 2026-02-28
A4410 | CONTROL & MV BUILDING STRUCTURAL FIRST FLOOR PLAN - Drawing Approval | 2026-01-30 | 2026-02-17
A4400 | CONTROL & MV BUILDING STRUCTURAL SCHEDULES & DETAILS - Drawing Approval | 2026-01-30 | 2026-02-17
A4390 | CONTROL & MV BUILDING STRUCTURAL ROOF FLOOR PLAN - Drawing Approval | 2026-01-30 | 2026-02-17
A4380 | CONTROL & MV BUILDING STRUCTURAL GROUND FLOOR PLAN - Drawing Approval | 2026-01-30 | 2026-02-17
A4370 | CONTROL & MV BUILDING STRUCTURAL SLAB ON GRADE - Drawing Approval | 2026-01-30 | 2026-02-17
A4360 | CONTROL & MV BUILDING STRUCTURAL FOUNDATION - Drawing Approval | 2026-01-30 | 2026-02-17
A4350 | CONTROL & MV BUILDING STRUCTURAL COLUMN & AXES - Drawing Approval | 2026-01-30 | 2026-02-17
A4330 | CONTROL & MV BUILDING STRUCTURAL DESIGN CALCULATION - Approval | 2026-01-30 | 2026-02-17
BSENELGI2G215 | 220KV BUILDING EQUIPMENT EARTHING LAYOUT & DETAILS - Drawing Submittal | 2026-01-29 | 2026-02-04
BSENELGI2G207 | 220KV GIS BUILDING EQUIPMENT ARRANGEMENTLAYOUT AND SECTIONS - Drawing Approval | 2026-01-29 | 2026-02-16
BSENCVGENGR01 | Bulk EXCAVATION PLAN - Drawing Submittal | 2026-01-28 | 2026-02-05
BSENELGENCP08 | 220/66/11 KV Substation Relay & Metering Diagram - Drawing Approval | 2026-01-28 | 2026-02-12
BSENELGENGR58 | Soil resistively measurement Method of Statement - Drawing Submittal | 2026-01-27 | 2026-02-03
BSENELGENVT01 | Material submittal - Three phase transformer 40 MVA with all accessories. | 2026-01-26 | 2026-02-10
BSENELGENDS14 | earthing system Material approval | 2026-01-23 | 2026-02-09
BSENELGENVT12 | Material approval -Three phase transformer 175 MVA with all accessories. | 2026-01-23 | 2026-02-09
A3570 | AC AUXILIARY SYSTEM SINGLE LINE DIAGRAM - Drawing Approval | 2026-01-23 | 2026-02-09
A3550 | 220V DC SYSTEM SINGLE LINE DIAGRAM - Drawing Approval | 2026-01-23 | 2026-02-09
A1990 | CONTROL & MV BUILDING STRUCTURAL FIRST FLOOR PLAN - Drawing Submittal | 2026-01-23 | 2026-01-29
A1980 | CONTROL & MV BUILDING STRUCTURAL SCHEDULES & DETAILS - Drawing Submittal | 2026-01-23 | 2026-01-29
A1970 | CONTROL & MV BUILDING STRUCTURAL ROOF FLOOR PLAN - Drawing Submittal | 2026-01-23 | 2026-01-29
A1960 | CONTROL & MV BUILDING STRUCTURAL GROUND FLOOR PLAN - Drawing Submittal | 2026-01-23 | 2026-01-29
A1950 | CONTROL & MV BUILDING STRUCTURAL SLAB ON GRADE - Drawing Submittal | 2026-01-23 | 2026-01-29
A1940 | CONTROL & MV BUILDING STRUCTURAL FOUNDATION PLAN - Drawing Submittal | 2026-01-23 | 2026-01-29
A1930 | CONTROL & MV BUILDING STRUCTURAL COLUMN & AXES - Drawing Submittal | 2026-01-23 | 2026-01-29
A1910 | CONTROL & MV BUILDING STRUCTURAL DESIGN CALCULATION - Submittal | 2026-01-23 | 2026-01-29
BSENARCRBGR51 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - SECTIONS - Drawing Submittal | 2026-01-23 | 2026-02-02
BSENARCRBGR41 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - ELEVATIONS - Drawing Submittal | 2026-01-23 | 2026-02-02
BSENARCRBGR31 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - Roof Floor Plan - Drawing Submittal | 2026-01-23 | 2026-02-02
BSENARCRBGR21 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - First Floor Plan - Drawing Submittal | 2026-01-23 | 2026-02-02
BSENARCRBGR11 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - Ground Floor Plan - Drawing Submittal | 2026-01-23 | 2026-02-02
BSENELGENCT02 | Material approval - Current & Voltage Transformer | 2026-01-23 | 2026-02-09
BSENELGENDS04 | Earthing material _ Material approval | 2026-01-23 | 2026-02-09
BSENELGENLT02 | Material approval - Line Trap | 2026-01-23 | 2026-02-09
BSENELGI2G214 | 220kV LCC WIRING SCHEMATICS MATERIAL APPROVAL | 2026-01-23 | 2026-02-05
BSENELGI2G201 | 220KV GIS BUILDING EQUIPMENT ARRANGEMENTLAYOUT AND SECTIONS - Drawing Submittal | 2026-01-23 | 2026-01-28
BSENELGI2G212 | Material approval - 220 KV GIS & GIB | 2026-01-23 | 2026-02-09
BSENELGENES03 | Material approval -Main Earthing System | 2026-01-23 | 2026-02-09
BSENELGENSG02 | Material approval - 11 KV MVSWGR ( S/S ) | 2026-01-23 | 2026-02-09
BSENELGENDS03 | Material approval - 123 & 36 kV EARTHING SWITCH Material Submittal (SIEYUAN) | 2026-01-23 | 2026-02-09
BSENELGENCB02 | Material approval - Capacitor Banks (9 MVAR) | 2026-01-23 | 2026-02-09
BSENELGI1G112 | Material approval - 66 KV GIS & GIB | 2026-01-23 | 2026-02-09
BSENELGI1G114 | 66kV LCC WIRING SCHEMATICS MATERIAL APPROVAL | 2026-01-23 | 2026-02-05
BSENELGENSG03 | MV SWGR Schematic Drawing Material Submittal | 2026-01-23 | 2026-02-05
BSENARCRBGR01 | CONTROL BUILDING ARCHITECTURAL DRAWINGS - BASEMENT Floor Plan - Drawing Submittal | 2026-01-23 | 2026-02-02
BSENELGI1G101 | 66KV GIS BUILDING EQUIPMENT ARRANGEMENT LAYOUT & SECTIONS - Drawing Submittal | 2026-01-23 | 2026-01-30
A3560 | 48V DC SYSTEM SINGLE LINE DIAGRAM - Drawing Approval | 2026-01-22 | 2026-02-06
BSENELGENCP04 | 220/66/11 KV Substation Relay & Metering Diagram - Drawing Submittal | 2026-01-21 | 2026-01-27
BSENELGENGR36 | 220/66/11 KV SUBSTATION OVERALL SINGLE LINE DIAGRAM - Drawing Approval | 2026-01-21 | 2026-02-05
BSENELGENTL01 | Material submittal - Telecommunication System | 2026-01-21 | 2026-02-05
BSPRELGENG202 | PO Issuance - 220 KV GIS & GIB | 2026-01-17 | 2026-02-01
BSPRELGENSG02 | PO Issuance - 11 KV MVSWGR ( S/S ) | 2026-01-16 | 2026-01-29
BSPRELGENLV06 | PO Issuance - LV/ Control Cables TERMINATIONS & ACCESSORIES | 2026-01-15 | 2026-02-13
A1160 | AC AUXILIARY SYSTEM SINGLE LINE DIAGRAM - Drawing Submittal | 2026-01-14 | 2026-01-22
A1150 | 48V DC SYSTEM SINGLE LINE DIAGRAM - Drawing Submittal | 2026-01-14 | 2026-01-21
A1140 | 220V DC SYSTEM SINGLE LINE DIAGRAM - Drawing Submittal | 2026-01-14 | 2026-01-22
BSPRELGENG102 | PO Issuance - 66 KV GIS & GIB | 2026-01-14 | 2026-01-29
A3710 | Control and protection panels base - Drawing Approval | 2026-01-12 | 2026-01-29
A3660 | 40MVA TRANSFORMER WIRING SCHEMATICS MATERIAL APPROVAL | 2026-01-12 | 2026-01-29
BSPRELGENCP28 | Purchasing Request - Transformers 40 | 2026-01-10 | 2026-01-23
BSPRELGENT702 | PO Issuance - Three phase transformer 175 MVA with all accessories. | 2026-01-09 | 2026-01-22
BSPRELGENTL02 | PO Issuance - Complete Telecommunication System With All accessories and Spare Parts | 2026-01-09 | 2026-01-16
BSPRELGENSA15 | PO Issuance - Surge Arresters | 2026-01-09 | 2026-02-07
BSENELGI2G213 | 220kV LCC WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-01-09 | 2026-01-22
BSENCVGENGR12 | SOIL INVESTIGATION REPORT - Approval | 2026-01-09 | 2026-01-28
BSENELGI1G113 | 66kV LCC WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-01-09 | 2026-01-22
A4020 | BOREHOLES LOCATION LAYOUT - Drawing Approval | 2026-01-07 | 2026-01-26
A5900 | Zero Level proposal - Drawing Approval | 2026-01-06 | 2026-01-23
BSENELGENDS4 | earthing system - Material Submittal | 2026-01-05 | 2026-01-22
BSENELGENVT2 | Material submittal - Three phase transformer 175 MVA with all accessories. | 2026-01-05 | 2026-01-22
A6030 | Start Engineering | 2026-01-05
A3500 | Zero Level proposal - Drawing Submittal | 2026-01-05 | 2026-01-05
A2090 | BOREHOLES LOCATION LAYOUT - Drawing Submittal | 2026-01-05 | 2026-01-06
A1300 | Control and protection panels base - Drawing Submittal | 2026-01-05 | 2026-01-09
A1250 | 40MVA TRANSFORMER WIRING SCHEMATICS MATERIAL SUBMITTAL | 2026-01-05 | 2026-01-09
A1110 | CONTROL & LV CABLE LIST - Drawing Submittal | 2026-01-05 | 2026-01-27
BSKDGNGENGR22 | Signing the contract | 2026-01-05
BSKDGNGENGR06 | Letter of Award | 2026-01-05
BSKDGNGENGR12 | LG for Advanced Payment | 2026-01-05
BSKDGNGENGR05 | Advanced Payment Foreign | 2026-01-05
BSKDGNGENGR03 | Advanced Payment Local | 2026-01-05
BSKDGNGENGR01 | Site Handover Free of Any Obstacles | 2026-01-05
BSPRELGENCP14 | Purchasing Request -Control & Protection Panels | 2026-01-05 | 2026-01-09
BSPRELGENT701 | Purchasing Request - Three phase transformer 175 MVA with all accessories. | 2026-01-05 | 2026-01-08
BSPRELGENSE01 | Purchasing Request -Cable Sealing End "HV" | 2026-01-05 | 2026-01-08
BSPRELGENTL01 | Purchasing Request - Complete Telecommunication System With All accessories and Spare Parts | 2026-01-05 | 2026-01-08
BSPRELGENSA03 | Purchasing Request - Surge Arresters | 2026-01-05 | 2026-01-08
BSPRELGENG201 | Purchasing Request - 220 KV GIS & GIB | 2026-01-05 | 2026-01-16
BSENELGI2G211 | Material submittal - 220 KV GIS & GIB | 2026-01-05 | 2026-01-22
BSENCVGENGR02 | SOIL INVESTIGATION REPORT - Submittal | 2026-01-05 | 2026-01-08
BSPRELGENLV03 | Purchasing Request - LV/ Control Cables TERMINATIONS & ACCESSORIES | 2026-01-05 | 2026-01-14
BSPRELGENSG01 | Purchasing Request - 11 KV MVSWGR ( S/S ) | 2026-01-05 | 2026-01-15
BSPRELGENCB01 | Purchasing Request - Capacitor Banks | 2026-01-05 | 2026-01-14
BSPRELGENCP01 | Purchasing Request - Control & Protection System | 2026-01-05 | 2026-01-08
BSPRELGENG101 | Purchasing Request - 66 KV GIS & GIB | 2026-01-05 | 2026-01-13
BSENELGENES01 | Material submittal - Main ground grid Conductor | 2026-01-05 | 2026-01-22
BSENELGENSG01 | Material submittal - 11 KV MVSWGR ( S/S ) | 2026-01-05 | 2026-01-22
BSENELGENDS01 | Material submittal - 123 & 36 kV EARTHING SWITCH Material Submittal (SIEYUAN) | 2026-01-05 | 2026-01-22
BSENELGENCT01 | Material submittal - Current & Voltage Transformer | 2026-01-05 | 2026-01-22
BSENELGENCB01 | Material submittal - Capacitor Banks (9 MVAR) | 2026-01-05 | 2026-01-22
BSENELGI1G111 | Material submittal - 66 KV GIS & GIB | 2026-01-05 | 2026-01-22
BSKDGNGENGR02 | LC Opening | 2026-01-05
BSENELGENGR24 | 220/66/11 KV SUBSTATION OVERALL SINGLE LINE DIAGRAM - Drawing Submittal | 2026-01-05 | 2026-01-16
BSKDGNGENGR04 | Commencement Date | 2026-01-05
BSENELGENDS02 | Earthing material - Material Submittal | 2026-01-05 | 2026-01-22
BSENELGENLT01 | Material submittal - Line Trap. | 2026-01-05 | 2026-01-22
BSMBCVGEN--01 | Mobilization & site Offices | 2026-01-05 | 2026-02-15